## Part I Main
Date:
Review and check the contract/agreement in accordance with this checklist and describe the results of the review and fill out this checklist.
Note: The following (a) to (k) means JICA's review point in the Procurement Guideline (Box 2: Points to be reviewed by JICA on the contract）. See the Chapter I (Section 1.05) for consultant and Chapter II (Section 1.06) for procurement of the products and services. ＊以下の(a)～(k)は調達ガイドラインのJICAの確認事項を示す。コンサルタントについては第1章(Section 1.05) 、物品又は役務 については第2章(Section 1.06)参照。
Note: The amendment of the contract/agreement shall be recorded by revising the check list in red . ＊修正契約の場合は概要表(チェックリスト）を朱書き修正して、記録すること。
| Items/Check points |  |  |  | Corresponding Clause （契約書対応条項） | Result
[6 empty] | Client/ Consultant | JICA
I | General Information on the Agreement/the Contract
| Type of Budget | □ Single Japanese fiscal year （単年度） Project whose budget of the Grant is appropriated in multiple Japanese fiscal years (Murtiple Japanese fiscal Year Project) （国債案件） □ A（□ D/D, □ Procurement/Construction（本体））□ B
| Type of Contract | □ Consulting Service
□ Construction
□ Procurement
□ Construction and Procurement Combined
Breakdown of the Contract/Agreement
In case of the Consultant Agreement, check the component(s) of the Project in Procurement of the Products and Services. コンサルタント契約の場合には、財及び役務の調達の項目についてもプロジェクトのコンポーネントを選択すること。
| Consulting Service | □ Detailed Design 詳細設計
□ Detailed Design, Bidding and Supervision 詳細設計、入札支援、施工・調達監理
□ Assistance in the start-up or operation and maintainace ソフトコンポーネント
| Procurement of the Products and Services | □ Construction works 施設建設
□ milestone type (マイルトーン方式）
□ progress type （出来高方式）
□ Procurement of Equipment 機材調達
□ payment on shipment (船積払）
□ payment on delivery （引渡払）
□ Installation works of Equipment （機材据付工事）
□ Operation training by the Contractor（操作指導）
□ Building of Ship 船舶建造
(d) The scope of the services or works is consistent with the purpose of the Grants and description of the project.
The scope of the services or works is consistent with the purpose of the Grants and description of the project.
II | Genral Information on the E/N and G/A
(a) The project title, signing date of the G/A and the E/N is consistent with the G/A.
| Name of Recipient Country/Client (Buyer) Country | name of the Client (Buyer)’s country
| Project Title | name of the project
| Client (Buyer)'s Name | name of the Client (Buyer)
Client (Buyer) is the same as the Recipient or the Executing Agency specified in the G/A.
Signing dateof the G/A and E/N and the end date of availability of the Grant
| (1) E/N | signing date: | 20**/**/**
|  | end date of availablity | 20**/**/**
| (2) G/A | signing date: | 20**/**/**
|  | end date of availablity | 20**/**/**
commencement date of each Term for Multiple Japanese Fiscal Year Project
|  | Term I | 20**/**/**
|  | Term II | 20**/**/**
|  | Term III | 20**/**/**
|  | Term IV | 20**/**/**
| (3) Amendment of G/A | signing date: | 20**/**/**
|  | extended end date of availablity | 20**/**/**
| Applicable Guideline | The Procurement Guidelines are the same as those specified in the G/A.
III | Genral Information on Eligibility :Consultant and Contractor (Supplier), country of origin
(e) Consultants, contractors, country of origin of the product and/or service meets the eligibility as specified in the G/A and the Procurement Guidelines.
Information on the Consultant, the Contractor and the Supplier
(1) Name of company
| (2) Contact Information | Department/Section in charge: Person in charge: tel: |  |  |  | － | － | － | －
The Consultant or Contractor(s) meets the eligibility as specified in the G/A and the Procurement Guidelines.
Information on the country of origin
The eligible source countries are limited to the eligible source countries specified in the bidding documents.
IV | Other Points to be reviewd by JICA
Period of execution
(c) The period of the execution of the service or work of the contract(s) does not exceed the terms of validity of the Grants as prescribed in the G/A. (i) The contract price and the period of the execution of the service or works are precisely and correctly worded.
Period of the execution of the service or works
| (1) signing date of the contract/agreement |  | 20**/**/**
| (2) end of the execution of the service or works (consulting service) end date of the Service Completion Period (procurement of the products and services) Time for Completion |  | 20**/**/**
(3) Effective conditions other than signing of the agreement/contract （署名以外の契約発効条件）
Note: The contract/agreement shall be amended within the original period of the execution of the service or works . ＊修正契約は原契約の履行期限内に行うこと。
Note: The period of the execution of ther service or works is properly set so as to secure appropriate time for completing payment procedures within the availability of the Grant. ＊履行期限はG/A供与期限内に支払手続きを完了するために必要な時間を確保し、適正な期間で設定すること。
Contract/Agreement Price & Payment
(b) The total amount of the contract including other contract(s) of the same project to be covered by the Grants does not exceed the amount of the Grants.
(1)Amount of the Grant (excluding the contingencies not concurred by JICA) （JICAが未同意の予備的経費を除く）
|  | Total | JPY | ***,***,***
Breakdown of each Term for Multiple Japanese Fiscal Year Project
|  | Term I | JPY | ***,***,***
|  | Term II | JPY | ***,***,***
|  | Term III | JPY | ***,***,***
|  | * Contingencies | JPY | ***,***,***
(2)Agreement/Contract amount to be covered by the Grant
|  | Total | JPY | ***,***,***
Breakdown of each Term for Multiple Japanese Fiscal Year Project
|  | Term I | JPY | ***,***,***
|  | Term II | JPY | ***,***,***
|  | Term III | JPY | ***,***,***
(3)Exsiting Agreement/Contract amount to be covered by the Grant （贈与資金充当（予定）分既契約済金額）
|  | Total | JPY***,***,***
Breakdown of each Term for Multiple Japanese Fiscal Year Project
|  | Term I | JPY | ***,***,***
|  | Term II | JPY | ***,***,***
|  | Term III | JPY | ***,***,***
(4)Balance ((1)-(2)-(3))
|  | Total | #VALUE!
Breakdown of each Term for Multiple Japanese Fiscal Year Project
|  | Term I | #VALUE!
|  | Term II | #VALUE!
|  | Term III | #VALUE!
(h) The currency, conditions and method of the payment is consistent with the terms and conditions set forth in the G/A and the Procurement Guidelines. (i) The contract price and the period of the execution of the service or works are precisely and correctly worded.
Contract Price
(1)The contract shall state clearly the total amount of fees to be paid to the consultant in Japanese yen using both words and figures.
(2) Total and subtotal amount of contract/agreement price are precisely added up. 契約金額の合計・小計が正しいこと。
(3)There is no discrepancy between the price in words and that in figures. 文字表記と数字標記に齟齬がないこと。
Note: Unite(JPY) and amount in figures shall be written in the same line. 単位記号（JPY)と数字が２行にまたがらないこと。（JPYと金額の間にスペースを空けない）
Conditions of Payment
(1) Payment shall be made in accordance with the criteria stipulated by JICA and the scope of the Project in No. 2 [Type and Scope of the Project] . JICAの定める支払条件の基準に従い、プロジェクト内容（コンサルティングサービスの内容、施設、機材（船積・引渡し、据付工事）、操作指導、ソフトコンポーネント等の有無）に従い、適切な支払い方法になっているか。
(2) The details of the payment conditions for partial payment are consistent with the scopes of the service or works. 部分払いの詳細は全体の業務内容と整合していること（重複して記載しないこと。特にマイルストーン、国債案件の場合）。
(3) The details and timing of the conditions for partial payment are consistent with the implementation schedule. 部分払いの詳細及び時期が実施工程と一致していること。
[Consulting Service]
(1)The advance payment assitance for the start-up or operation and maintenance is allowed for the service with its implementation period for more than four months (For Murtiple Japanese fiscal Year Project, more than four months in case of each Term). 4か月以上のソフコン実施期間がある場合は、前払いが可能。 （出来高表等により確認）
(2) Inspection & Search over before the expiry of the Defect Notification Period shall be paid after its completion. 瑕疵通知期間満了前検査（メーカー保証満了前検査を含む）は、当該業務の終了時点で支払われること。
[Consulting Sevice & Construction]
(1) There are no discrepancy from Consultant Agreement in terms of the type of payment (milestone or progress type) and the details of the conditions for partial payment. コンサルタント契約との間で支払方法（マイルストーン・出来高の別）及び部分払いの条件の詳細も一致していること。
Construction (Progress type)
(2)Expected work value for each term and partial payment is properly set in accordance with the payment criteria. 出来高の％設定は支払い条件に係る基準に準拠している（ターム、部分払いを含めて）。
Obligation under the E/N and G/A
(d) The rights and obligations of the Recipient and the consultant are in accordance with the E/N and G/A.
The obligations of the Client are properly stated in accordance with the E/N and G/A (including attachment of schedule 4 [Obligation of the Recipient].

## Part II Consultant
| Items/Check points | Corresponding Clause （契約書対応条項） | Result
|  |  | Client/ Consultant | JICA
(j) The provisions and sentences required to be included in accordance with the Procurement Guideline are properly and clearly stated. Note: The following number of Section means the relevant section in the Applicable Guidelines.
Section 1.07 Conflict of Interest
The conditions for not disqualifying or excluding the Consultant under Sub-Clause 5.2.2 are acceptable to JICA.
Section 1.08 Language
All documents relating to employment of consultants, including the contract, shall be prepared in one of the following languages, selected by the Recipient: [□ English, □ French or □ Spanish]
Section 4.02 Reference to the the Grants
The contract shall refer to the Grants in accordance with the Appicanble Guidelines
Section 4.03 Scope of the Project and of the Consulting Services
The consultants shall assist the Recipient in preparation of the safety requirements in accordance with the laws and regulations in the Government of the Recipient, relevant international standards, if any, and also in consideration of “the Guidance for the Management of Safety for Construction Works in Japanese ODA Projects”, and review the content of the plan for safety measures prepared by the Contractor for the project.
Section 4.15 Governing Laws
The contract shall stipulate which laws shall govern its interpretation and performance.
Othe sections
The other provisions and sentences required to be included in accordance with the Procurement Guideline are not deleted or modified in the Special Conditions of Agreement (SCA). 調達ガイドライン上定めるべきその他の条項及び文章がSCAにおいて削除又は修正されていないか。

## Part II Contractor
| Items/Check points | Corresponding Clause （契約書対応条項） | Result
|  |  | Client/ Consultant | JICA
(k) The provisions and sentences required to be included in accordance with the Procurement Guideline are properly and clearly stated. Note: The following number of Section means the relevant section in the Applicable Guidelines.
Section 4.15 Advance Payment Securities
(1) The percentage of the total payment to be made in advance, upon entry into effect of the contract, for mobilization and similar expenses shall be reasonable and specified in the bidding documents. (2) The bidding documents shall specify the arrangements for any security required for advance payments.
Section 4.15 Insurance
The contract shall state precisely the types and terms of insurance (e.g. liabilities to be covered and duration of the insurance) to be obtained by the successful bidder.
Section 4.18 Settlement of Disputes
The contract shall stipulate which laws shall govern its interpretation and performance.
Section 4.18 Governing Laws
The contract shall stipulate which laws shall govern its interpretation and performance.
Othe sections [Section 4.04 Conditions of Contract]
(j) The risks and liabilities among the parties shall be allocated in a balanced manner, and modification of such allocation in customary general conditions of contract shall be reasonable in view of smooth implementation of the project.
The other provisions and sentences required to be included in accordance with the Procurement Guideline are not deleted or modified in the Particular Conditions. The modification in the Particular Contiditions shall be reasonable in view of smooth implementation of the project and not affect the allocation of the risks and liabilities. 調達ガイドライン上定めるべきその他の条項及び文章が特記条件において削除又は修正されていないか、特記条件における修正は合理的なものであるか。リスクや責任の分配に影響を与えていないか。

## Part-III Amendment
Record of Amendment of the Contract/Agreement
Date of Amendment | The Clause amended/ to be amended | Contents of Amendment | Major amendments to be reviewed and concurred by JICA
|  |  | Concurrence date | Concurrence (verification) No.
Consultant
[sample] **/**/20** | SCA 1.1(Definition) Resident Supervisor | Original: Mr. A Amended:Mr. B
[sample] **/**/20** | SCA 6.2 (Payment) (2) | Original: The Agreement price to be paid from the Grant is:[ ******** million ******** thousand ******* Japanese Yen (JPY***,***,***) Amended:The Agreement price to be paid from the Grant is:[ ******** million ******** thousand ******* Japanese Yen (JPY***,***,***) | **/**/20** | 25-VJ-**B
Construction
Procurement of Equipment

## Part-IV Schedule of Payment
Note: For assistance in filling in this form, please refer to the "Example" tabs of this worksheet. （別タブの記入例を参照してください。単債用記入例と国債用記入例があります。） Note: "Terms of Payment" should be the same as specified in the contract document. In case of the project whose budget of the grant is appropriated in multiple Japanese fiscal years, please add the budget term (Term 1, Term 2…). (「Terms of Payment」欄には、契約書規定の支払条件を記入してください。また、国債案件の場合は、該当ターム（Term 1, Term 2…）を併記してください。） Note: In the "Payment Schedule" column, please specify the date(s) as follows; - Payment Schedule (original/revised): the date when the necessary documents are to be submitted to the company's main bank. - Actual Date of Payment: the date when the payment was executed/completed. （「支払請求予定時期」に記載する予定年月日は自社の取引銀行への支払書類提出予定日、実績は着金日を記入すること。）
20XX/XX/XX Revised 20XX/XX/XX
1. Consulting Services
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
(1)Service for the design, bidding and supervision stages
(a)Service for the design, bidding and supervision stages other than (b)
Advance Payment
First Interim Payment
Second Interim Payment
Final Payment
sub-total (a)
sub-total (b)
Sub-total (1)
(2) Service for the Assistance in the start-up or operation and maintenance Stage
Advance Payment
Final Payment
Sub-total (2)
Grand Total
2.1 Construction Works
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
Advance Payment
First Interim Payment
Second Interim Payment
Final Payment
Total
Operation training
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
2.2 Procurement of Equipment
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
A. Equipment
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
a. Payment on shipment
1st Shipment
2nd Shipment
sub-total (a)
b. Payment on delivery
1st Delivery
2nd Delivery
sub-total (b)
Grand Total
B. Installation
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
C. Operation training
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由

## Example_単債_Schedule of Payment
Note: "Terms of Payment" should be the same as specified in the contract document. In case of the project whose budget of the grant is appropriated in multiple Japanese fiscal years, please add the budget term (Term 1, Term 2…). (「Terms of Payment」欄には、契約書規定の支払条件を記入してください。また、国債案件の場合は、該当ターム（Term 1, Term 2…）を併記してください。） Note: In the "Payment Schedule" column, please specify the date(s) as follows; - Payment Schedule (original/revised): the date when the necessary documents are to be submitted to the company's main bank. - Actual Date of Payment: the date when the payment was executed/completed. （「支払請求予定時期」に記載する予定年月日は自社の取引銀行への支払書類提出予定日、実績は着金日を記入すること。）
20XX/XX/XX Revised 20XX/XX/XX Revised 20XX/XX/XX
1. Consulting Services
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
(1)Service for the design, bidding and supervision stages
(a)Service for the design, bidding and supervision stages other than (b)
Advance Payment | XXX,XXX | Concurrence of the Agreement by JICA | 1 MAY, 2022 (Original) 12 MAY, 2022(Actual)
First Interim Payment | XXX,XXX | Concurrence of all the contracts by JICA | 5 FEB, 2023 (Original) 5 MAR, 2023(Revised 1) 15 MAY, 2023(Revised 2) | Revised 1: Delay in EIA approval Revised 2: Bid failure
Second Interim Payment | XXX,XXX | Completion of the XX% of the construction work | 15 DEC, 2023 (Original)
Final Payment | XXX,XXX | Completion of the search over the defects for the construction before the expiry of Defect Notification Period | 15 DEC, 2024 (Original)
sub-total (a)
sub-total (b)
Sub-total (1)
(2) Service for the Assistance in the start-up or operation and maintenance Stage
Advance Payment
Final Payment
Sub-total (2)
Grand Total
2.1 Construction Works
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
Advance Payment
First Interim Payment
Second Interim Payment
Final Payment
Total
Operation training
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
2.2 Procurement of Equipment
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
A. Equipment
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
a. Payment on shipment
1st Shipment
2nd Shipment
sub-total (a)
b. Payment on delivery
1st Delivery
2nd Delivery
sub-total (b)
Grand Total
B. Installation
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
C. Operation training
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
★本Schedule of Paymentの当初作成日付を記入し、その後支払いスケジュールに変更が生じた場合は、更新した日付を記入してください。
【この吹き出し及び本紙内青字は説明と記入例です】
★本ページは更新有無にかかわらず、毎月10日までに、以下のとおりご提出ください。
（提出先：jicagl_report@jica.go.jp）
・施設建設案件：PMRの添付書類として提出
・機材案件（船舶案件含む）： - PMR提出月：PMRの添付書類として提出
- PMR提出のない月：本ページのみ提出
★なお、変更が生じた場合は、提出期限を待たずに速やかに更新版を提出ください。
★当初の請求予定時期（自社取引銀行への書類提出予定日）をOriginalとして記入し、変更を要する場合は変更後の請求予定時期をRevised 1, 2,3と追記してください。
★Actualとして、実際の着金日を追記ください。
★支払予定を変更する場合は、必ず変更となった理由を記載してください。

## Example_国債_Schedule of Payment
Note: "Terms of Payment" should be the same as specified in the contract document. In case of the project whose budget of the grant is appropriated in multiple Japanese fiscal years, please add the budget term (Term 1, Term 2…). (「Terms of Payment」欄には、契約書規定の支払条件を記入してください。また、国債案件の場合は、該当ターム（Term 1, Term 2…）を併記してください。） Note: In the "Payment Schedule" column, please specify the date(s) as follows; - Payment Schedule (original/revised): the date when the necessary documents are to be submitted to the company's main bank. - Actual Date of Payment: the date when the payment was executed/completed. （「支払請求予定時期」に記載する予定年月日は自社の取引銀行への支払書類提出予定日、実績は着金日を記入すること。）
|  |  | #NAME? | 20XX/XX/XX Revised 20XX/XX/XX Revised 20XX/XX/XX
1. Consulting Services
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
(1)Service for the design, bidding and supervision stages
(a)Service for the design, bidding and supervision stages other than (b)
Advance Payment | XXX,XXX | Concurrence of the Agreement by JICA (TermX) | 1 MAY, 2022 (Original) 12 MAY, 2022(Actual)
First Interim Payment | XXX,XXX | Concurrence of all the contracts by JICA (TermX) | 5 FEB, 2023 (Original) 5 MAR, 2023(Revised 1) 15 MAY, 2023(Revised 2) | Revised 1: Delay in EIA approval Revised 2: Bid failure
Second Interim Payment | XXX,XXX | Completion of the XX% of the construction work (TermX) | 15 DEC, 2023 (Original)
Final Payment | XXX,XXX | Completion of the search over the defects for the construction before the expiry of Defect Notification Period(Term X) | 15 DEC, 2025(Original)
sub-total (a)
sub-total (b)
Sub-total (1)
(2) Service for the Assistance in the start-up or operation and maintenance Stage
Advance Payment
Final Payment
Sub-total (2)
Grand Total
2.1 Construction Works
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
Advance Payment
First Interim Payment
Second Interim Payment
Final Payment
Total
Operation training
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
2.2 Procurement of Equipment
Time for Completion: |  | Date of concurrence:
Date of issue of Authorization to Pay (A/P): |  | Deadline of presentation of the required document stipulated in A/P:
A. Equipment
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
a. Payment on shipment
1st Shipment
2nd Shipment
sub-total (a)
b. Payment on delivery
1st Delivery
2nd Delivery
sub-total (b)
Grand Total
B. Installation
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
C. Operation training
| Amount 金額 | Terms of Payment 支払条件 | Payment Schedule (original/revised) and Actual Date of Payment 支払請求予定日/着金日 | Reason for Change in Payment Schedule 支払請求予定日 変更理由
★本Schedule of Paymentの当初作成日付を記入し、その後支払いスケジュールに変更が生じた場合は、更新した日付を記入してください。
【この吹き出し及び本紙内青字は説明と記入例です。】
★本ページは更新有無にかかわらず、毎月10日までに、以下のとおりご提出ください。
（提出先：jicagl_report@jica.go.jp）
・施設建設案件：PMRの添付書類として提出
・機材案件（船舶案件含む）： - PMR提出月：PMRの添付書類として提出
- PMR提出のない月：本ページのみ提出
★なお、変更が生じた場合は、提出期限を待たずに速やかに更新版を提出ください。
★当初の請求予定時期（自社取引銀行への書類提出予定日）をOriginalとして記入し、変更を要する場合は変更後の請求予定時期をRevised 1, 2,3と追記してください。
★Actualとして、実際の着金日を追記ください。
★支払予定を変更する場合は、必ず変更となった理由を記載してください。
【この吹き出し及び本紙内青字は説明と記入例です。】
★国債案件では、契約書上の「Payment Schedule」に規定している支払条件と、ターム情報を記入してください。ただし、国債案件でも、各支払条件にターム情報が規定されていない契約である場合は、ターム情報は記入不要です。