BIDDING DOCUMENTS

for

Procurement of

[insert identification of the Facilities] _______________________________

_______________________________

Employer: [insert name of Employer]

Country: [insert name of Country]

Project: [insert name of Project]

Loan No.: [insert number of Loan Agreement]

Table of Contents

Invitation for Bids: Following Prequalification	IFB-1

Invitation for Bids: Without Prequalification	IFB-1

Invitation for Second Stage Bids	IFB-1

PART 1 - Bidding Procedures

OPTION A: Single-Stage Two-Envelope Bidding

Section I.  Instructions to Bidders 	ITB-1

Section II.  Bid Data Sheet	BDS-1

Section III.  Evaluation and Qualification Criteria (Following Prequalification)	EQC-1

Section III.  Evaluation and Qualification Criteria (Without Prequalification)	EQC-1

OPTION B: Two-Stage One-Envelope Bidding

Section I.  Instructions to Bidders	ITB-1

Section II.  Bid Data Sheet	BDS-1

Section III.  Evaluation and Qualification Criteria (Following Prequalification)	EQC-1

Section III.  Evaluation and Qualification Criteria (Without Prequalification)	EQC-1

Section IV.  Bidding Forms	BF-1

Section V.  Eligible Source Countries of Japanese ODA Loans	ESC-1

PART 2 - Employer’s Requirements

Section VI.  Employer’s Requirements	ER-1

PART 3 - Conditions of Contract and Contract Forms

Section VII.  General Conditions (GC)	GC-1

Section VIII.  Particular Conditions	PC-1

Section IX.  Contract Forms	CF-1

Invitation for Bids: Following Prequalification

## Notes on Invitation for Bids The Invitation for Bids for contracts, subject to prequalification, is sent only to firms determined by the Employer to be qualified in accordance with the Employer’s prequalification procedure. This prequalification procedure must be reviewed and commented on by JICA if the potential contract is to be eligible for JICA financing (see the relevant Section of the Guidelines for Procurement under Japanese ODA Loans). Ideally, the Invitation for Bids is sent to the qualified Bidders at the time that the prequalification results are announced. For major plant, prequalification is in principle required. If prequalification is not used, the appropriate Invitation for Bids form shall be used. In case of Two-Stage One-Envelope Bidding procedure, the Bid Security is required at the Second Stage. Therefore, the request of a Bid Security shall be deleted from the Invitation for First Stage Bids. The Invitation for Bids should be consistent with the information contained in Section II - Bid Data Sheet.

##### Invitation for Bids

Date: [date of issuance of IFB]

Loan Agreement No: [insert number]

IFB No: [insert number]

Reference Identification No: [insert number]

1.	The [insert name of Borrower] has received a loan from Japan International Cooperation Agency (JICA) towards the cost of [insert name of Project].  It is intended that part of the proceeds of this loan will be applied to eligible payments under the Contract for [insert title of Contract].

2.	Bidding will be conducted through procedures in accordance with the applicable Guidelines for Procurement under Japanese ODA Loans, and is open to all Bidders from eligible source countries, as defined in the Loan Agreement.

3. 	The [insert name of the Employer] now invites sealed Bids from prequalified eligible Bidders for the construction and completion of [insert brief description of the Plant and Installation Services to be procured] (“the Facilities”). International Competitive Bidding will be conducted in accordance with JICA’s [insert “Single-Stage” or “Two-Stage”] Bidding Procedure

4.	Prequalified eligible Bidders may obtain further information from and inspect the Bidding Documents at the office of [insert name of appropriate purchasing unit] [insert mailing address, email address(es) and/or facsimile numbers of appropriate office for inquiry and issuance of the Bidding Documents].

5.	A complete set of the Bidding Documents may be purchased by interested prequalified Bidders on the submission of a written application to the address above and upon payment of a non-refundable fee of [insert amount in currency of Borrower’s country or in specified convertible currency].

6.	Bids must be delivered to the address above on or before [insert time] on [insert date] and must be accompanied by a Bid security of [insert fixed amount (same as that stated in Clause 21.1 of the Bid Data Sheet (BDS)].

7.	Bids will be opened in the presence of Bidders’ representatives who choose to attend at [insert time and date] at the office of [insert address of appropriate office].

[Insert name of office]

[Insert name of person in charge officer]

[Insert postal address] and/or [Insert street address]

[Insert telephone number, indicate country and city code]

[Insert facsimile number]

[Insert email address]

Invitation for Bids: Without Prequalification

## Notes on Invitation for Bids If Bids are invited openly from contractors without using a prequalification procedure, the Invitation for Bids should be issued directly to the public (see the relevant Section of the Guidelines for Procurement under Japanese ODA Loans): (a) as an advertisement in at least one newspaper of general circulation in the Borrower’s country; and (b) with sending copies of the invitation to JICA. The Invitation for Bids provides information that enables potential Bidders to decide whether to participate. Apart from a summary description of the Facilities, the Invitation for Bids should also indicate any important Bid evaluation criteria (for example, technical alternatives) or qualification requirement (for example, a requirement for a minimum level of experience in projects similar to that for which the Invitation for Bids is issued). In case of Two-Stage One-Envelope Bidding procedure, the Bid Security is required at the Second Stage. Therefore, the request of a Bid Security shall be deleted from the Invitation for First Stage Bids. The Invitation for Bids should be consistent with the information contained in Section II - Bid Data Sheet.

##### Invitation for Bids

Date: [date of issuance of IFB]

Loan Agreement No: [insert number]

IFB No: [insert number]

Reference Identification No: [insert number]

1.	The [insert name of Borrower] has received a loan from Japan International Cooperation Agency (JICA) towards the cost of [insert name of Project].  It is intended that part of the proceeds of this loan will be applied to eligible payments under the Contract for [insert title of Contract].

2.	Bidding will be conducted through procedures in accordance with the applicable Guidelines for Procurement under Japanese ODA Loans, and is open to all Bidders from eligible source countries, as defined in the Loan Agreement.

3. 	The [insert name of the Employer] now invites sealed Bids from eligible Bidders for the construction and completion of [insert brief description of the Plant and Installation Services to be procured] (“the Facilities”). International Competitive Bidding will be conducted in accordance with JICA's [insert “Single-Stage” or “Two-Stage”] Bidding Procedure.

4.	Interested eligible Bidders may obtain further information from and inspect the Bidding Documents at the office of [insert name of appropriate purchasing unit] [insert mailing address, email address(es), and/or facsimile numbers of appropriate office for inquiry and issuance of Bidding Documents].

5.	A complete set of the Bidding Documents may be purchased by interested Bidders on the submission of a written application to the address above and upon payment of a non-refundable fee of [insert amount in currency of Borrower’s country or in specified convertible currency].

6.	Bids must be delivered to the address above on or before [insert time] on [insert date] and must be accompanied by a Bid Security of [insert fixed amount (same as that stated in Clause 21.1 of the Bid Data Sheet (BDS)].

7.	Bids will be opened in the presence of Bidders’ representatives who choose to attend at [insert time and date] at the office of [insert address of appropriate office].

[Insert name of office]

[Insert name of person in charge officer]

[Insert postal address] and/or [Insert street address]

[Insert telephone number, indicate country and city code]

[Insert facsimile number]

[Insert email address]

Invitation for Second Stage Bids

## Notes on Invitation for Second Stage Bids The Invitation for Second Stage Bids is used in the Two-Stage One-Envelope Bidding procedure. It shall be sent to all Bidders who were found responsive after the First Stage Bid evaluation, inviting them to submit an updated technical Bid and a financial Bid. Two-Stage One-Envelope Bidding applies following a prequalification process or without such procedure. The Invitation for Bids “Following Prequalification” and “Without Prequalification” given above shall be used for inviting Bidders for the First Stage Bid.

Invitation for Second Stage Bids

Date: [date of issuance of Invitation for Second-Stage Bids]

Loan Agreement No: [insert number]

IFB No: [insert number]

Reference Identification No: [insert number]

To: [ insert name and address of the Bidder]

1.	We hereby inform you that you are invited to submit a sealed Second-Stage Bid for the execution and completion of the cited Contract for which you submitted a First Stage Bid on [insert date of submission of First Stage Bid], which was reviewed during the clarification meeting(s) held on [insert date(s)] and has been found technically responsive.

2.	Your Second Stage Bid should include an updated Technical Bid and a Price Bid based on attached amendment, if any, and on the modifications, if any, listed in the “Changes Required Pursuant to the First Stage Evaluation” Annex to the Memorandum of the clarification meeting(s) held with you on [insert date(s)].

3.	Second Stage Bids shall be submitted [insert time, date and address for Second Stage Bid submission] and will be opened in the presence of the Bidder’s representatives who choose to attend at [insert time, date and address for Second-Stage Bid opening].

4.	Second Stage Bids shall remain valid for [insert number of days] after the deadline for Bid submission prescribed above.

5.	All Second Stage Bids must be accompanied by a Bid Security in an amount of [insert fixed amount (same as that stated in Clause 36.1 of the Bid Data Sheet (BDS)].

6.	Please confirm receipt of this letter immediately in writing by email or facsimile. If you do not intend to bid, we would appreciate being so notified again in writing at your earliest opportunity.

Attachments: [insert title of amendments, if any, and the Memorandum of “Changes Required Pursuant to First Stage Evaluation]

[Insert name of office]

[Insert name of person in charge officer]

[Insert postal address] and/or [Insert street address]

[Insert telephone number, indicate country and city code]

[Insert facsimile number]

[Insert E-mail address]

PART 1 - Bidding Procedures

OPTION A:
Single-Stage Two-Envelope Bidding

Section I. Instructions to Bidders

## Notes on Instructions to Bidders Section I, Instructions to Bidders, provides the information necessary for Bidders to prepare responsive Bids in accordance with the requirements of the Employer. It also gives information on Bid submission, opening, and evaluation, and on the award of the Contract. The use of the Standard Instructions to Bidders set forth in Section I of these Standard Bidding Documents for the Procurement of Plant Design, Supply and Installation (version 1.0) published by JICA in February, 2013 (hereafter referred to as “Standard ITB”) is required in all Bidding Documents for Plant Design, Supply and Installation works financed by Japanese ODA Loans, and they shall be used without modification. Any necessary changes, acceptable to JICA, to address specific country and project issues, shall be introduced only through the Bid Data Sheet. The Instructions to Bidders will not be part of the Contract.

Section I.  Instructions to Bidders

[Note to the Employer: The instructions to Bidders governing all Single-Stage Two-Envelope bidding processes for Plant Design, Supply and Installation Contracts funded with Japanese ODA Loans are the Standard Instructions to Bidders included in Option A, Single-Stage Two-Envelope Bidding, of the Standard Bidding Documents for Procurement of Plant Design, Supply and Installation (SBD (Plant)) (version 1.0) published by JICA in February 2013.

A copy of the Standard Instructions to Bidders may be attached to the Bidding Documents prepared by the Employer for reference purposes only. If the Instructions to Bidders in the Bidding Documents prepared by the Employer contain modifications from the Standard Instructions to Bidders, JICA will not consider them valid and the Standard Instructions to Bidders, as defined above, shall apply.

Instead of attaching a copy of the Standard Instructions to Bidders, the Employer may use the following introductory text.]

The Instructions to Bidders governing this bidding process are the “Instructions to Bidders included in Option A, Single-Stage Two-Envelope Bidding, Section I,” of the Standard Bidding Documents for Procurement of Plant Design, Supply and Installation (version 1.0) published by JICA in February 2013. Those Instructions to Bidders are available on the JICA’s web site shown below:

http://www.jica.go.jp/english/our_work/types_of_assistance/oda_loans/oda_op_info/guide/tender/index.html

A copy of the Instructions to Bidders is not attached to these Bidding Documents.

Section II. Bid Data Sheet

## Notes on Bid Data Sheet Section II, Bid Data Sheet, shall be filled in by the Employer before issuance of the Bidding Documents. The Bid Data Sheet (BDS) contains information and provisions that are specific to a particular bidding process. The Employer must specify in the BDS only the information that the ITB request be specified in the BDS. All information shall be provided; no clause shall be left blank. To facilitate the preparation of the BDS, its clauses are numbered with the same numbers as those of the corresponding ITB clauses.

Bid Data Sheet

| A. General |  |
| --- | --- |
| ITB 1.1 | The number of the Invitation for Bids is : [insert number of the Invitation for Bids] |
| ITB 1.1 | The Employer is: [insert name of Employer] |
| ITB 1.1 | The name, identification and number of the lot(s) (contract(s)) comprising this ICB is: [insert name, identification and number of lot(s) (contract(s))] |
| ITB 2.1 | The Borrower is: [insert name of Borrower] |
| ITB 2.1 | The number of the Loan Agreement is: [insert Loan Agreement number] The amount of a Japanese ODA Loan is: [insert amount in Japanese Yen] The signed date of the Loan Agreement is: [insert signed date of Loan Agreement] |
| ITB 2.1 | The name of the Project is: [insert name of Project] |
| ITB 2.2 | The applicable Guidelines for Procurement under Japanese ODA Loans are those published in: [insert one of the following: April 2012, March 2009, or October 1999] |
| ITB 3.1(c) | A list of debarred firms and individuals is available at the World Bank’s website: www.worldbank.org/debarr |
| ITB 4.5 | This bidding [select “is” or “is not”, as appropriate] subject to prequalification. |
| B. Bidding Documents |  |
| ITB 7.1 | For clarification purposes only, the Employer’s address is: [insert the corresponding information as required below. This address may be the same as or different from that specified under ITB 24.1 for Bid submission.] Attention: [insert full name of person, if applicable] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: [insert name of country] Telephone: [insert telephone number, including country and city codes] Facsimile number: [insert facsimile number, including country and city codes] Electronic mail address: [insert email address, if applicable] |
| ITA 7.1 | Responses to any request for clarification, if any, [select “will” or “will not”, as appropriate] be published on the Employer’s web page indicated below. Web page: [Insert the Employer’s web page if responses to requests for clarifications will be published on the Employer’s web page, otherwise omit.] |
| ITB 7.4 | A pre-bid meeting _____ [insert “will” and insert the date, time and place information in the spaces provided below if a pre-bid meeting will take place, taking into consideration that the meeting should take place no later than four weeks before the deadline for Bid submission. Otherwise, insert “will not” and insert “Not Applicable” in the spaces provided below for the date, time and place] take place at the following date, time and place: Date: Time: Place: A site visit conducted by the Employer _______ [insert “will be” or “will not be”, as appropriate] organized. |
| ITB 8.2 | Addenda, if any, [select “will” or “will not”, as appropriate] be published on the Employer’s web page. |
| C. Preparation of Bids |  |
| ITB 10.1 | The language of the Bid is: [insert one of the following: Japanese, English, Spanish or French] |
| ITB 11.2 (l) | The Bidder shall submit with its Technical Bid the following additional documents: [List any additional documents not already listed in ITB 11.2 that must be submitted with the Bid. If no additional documents are to be submitted, insert “None”. ] |
| ITB 11.3 (d) | The Bidder shall submit with its Price Bid the following additional documents: [List any additional documents not already listed in ITB 11.3 that must be submitted with the Bid. If no additional documents are to be submitted, insert “None”.] |
| ITB 13.1 | [Use one of the following options as appropriate.] Alternative Bids are invited/permitted in accordance with: [ITB 13.2 and/or ITB 13.3 and/or ITB13.4] [Choose the ITB Clause(s) corresponding to the invited/permitted alternative(s) and specify the type(s) of alternative accepted.] [or] Alternative Bids are not permitted. |
| ITB 13.2 | [If alternatives to the Time Schedule are invited, insert the following provisions; otherwise, delete this Clause 13.2 of the BDS.] Alternatives to the Time Schedule are permitted. The evaluation method is as specified in Section III, Evaluation and Qualification Criteria. |
| ITB 13.4 | [If alternative technical solutions are invited, insert the parts for which they are permitted; otherwise, delete this Clause 13.4 of the BDS.] Alternative technical solutions are permitted for the following parts of the Plant and Installation Services: __________ as further detailed in Section VI, Employer’s Requirements. The evaluation method is as specified in Section III, Evaluation and Qualification Criteria. |
| ITB 16.1 (b) | The period following completion of Plant and Installation Services during which spare parts, special tools etc. shall be available, is [insert number of years as appropriate, normally two (2) years] _______. |
| ITB 18.1 | [Use one of the following options as appropriate.] Bidders shall quote for the entire Plant and Installation Services on a single responsibility basis. [or] Bidders shall quote for the following components or services on a single responsibility basis: [insert list of components or services] _______________________________________ [and/or] The following components or services will be provided under the responsibility of the Employer: [insert list of components or services] _______________________________________ |
| ITB18.5 | [The following provision should be included and the corresponding information inserted only if duties, taxes and other levies will be exempted, reimbursed, or paid by the Employer on behalf of the Contractor. Otherwise delete this BDS 18.5.] Duties, taxes and other levies indicated below shall be [choose one of the following: “exempted”, reimbursed, “paid by the Employer on behalf of the Contractor”, as appropriate.]: [List duties, taxes and other levies.] |
| ITB 18.5(a) | Named place of destination is: _______________ [insert destination] |
| ITB 18.5(d) | Named place of final destination is: ____________ [insert destination] [Note: When the named place of destination is the project site, the transportation costs for Schedule No. 1 items are covered under CIP and therefore will not be stated here. This schedule will cover only for items in Schedule No. 2. If the named place of destination is different from the site of installation (project site), then the transport cost from the named place of destination to project site for Schedule No. 1 shall be also included here.] |
| ITB 18.7 | The prices quoted by the Bidder shall be: [insert “fixed” or “adjustable”] |
| ITB 19.1 | The currency(ies) of the Bid shall be as follows: (a) Plant and equipment to be supplied from abroad shall be quoted entirely in: [insert Japanese Yen and/or other international trading currency or currencies]. (b) Plant and equipment to be supplied from within the Employer’s country shall be quoted in the currency of the Employer’s country: [insert currency of Employer’s country]. (c) Design and installation shall be quoted in either foreign and/or local currency, depending upon the currency in which the costs are to be incurred. |
| ITB 20.1 | The Bid validity period shall be _______ [insert number of days required for evaluation, approval and award plus contingency] days. [This period should be realistic, allowing sufficient time to evaluate the Bids, bearing in mind the complexity of the Facilities and the time required for obtaining references, clarifications, clearances and approvals (including JICA’s concurrence) and for notification of the award. Normally the validity period should not exceed 120 days.] |
| ITB 20.3 (a) | The Bid Price shall be adjusted by the following factor: [insert factor for adjustment] [The local currency portion of the Contract Price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract Price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If Adjustable Price is applied in accordance with BDS 18.7; Not Applicable. |
| ITB 20.3 (b) | The fixed portion of the Bid Price shall be adjusted by the following factor: [insert factor for adjustment] [The local currency portion of the fixed portion of the Contract Price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the fixed portion of the Contract Price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If there is no fixed portion of the Bid Price, or the entire price is fixed; Not Applicable. |
| ITB 21.1 | The amount and currency of the Bid Security shall be [insert amount and currency of the Bid Security. The amount should be approximately 2% of the estimated cost of the Contract.] |
| ITB 21.2 (d) | Other types of acceptable securities: [Insert names of other acceptable securities. Insert “None” if no other forms of Bid Securities besides those listed in ITB 21.2 (a) through (c) are acceptable.] |
| ITB 22.1 | In addition to the original of the Bid, the number of copies is: [insert number of copies] |
| ITB 22.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: [insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the Bid] |
| D. Submission and Opening of Bids |  |
| ITB 24.1 | For Bid submission purposes only, the Employer’s address is: [This address may be the same as or different from that specified under provision ITB 7.1 for clarifications.] Attention: [insert full name of person, if applicable] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: [insert name of country] The deadline for Bid submission is: Date: [insert day, month, and year, e.g., 15 June, 2013] Time: [insert time, and identify if a.m. or p.m., e.g., 10:30 a.m.] [The date and time should be the same as those provided in the Invitation for Bids, unless subsequently amended pursuant to ITB 24.2.] |
| ITB 27.1 | The Technical Bid opening shall take place at: Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City : [insert name of city or town] Country: [insert name of country] Date: [insert day, month, and year, e.g., 15 June, 2013] Time: [insert time, and identify if a.m. or p.m. e.g., 10:30 a.m.] [The date and time should be the same as those given for the deadline for submission of Bids (ITB 24).] |
| E. Evaluation, and Comparison of Bids |  |
| ITB 37.1 | The currency that shall be used for Bid evaluation and comparison purposes to convert all Bid Prices expressed in various currencies into a single currency is: [insert Japanese Yen or another single currency] The source of exchange rate shall be: [insert name of the source of exchange rates (e.g., the Central Bank in the Employer’s Country).] The date for the exchange rate shall be: [insert a date (day, month and year, e.g., 15 June , 2013), not earlier than thirty (30) days prior to, nor later than, the date for Technical Bid opening, specified in ITB 27.1] |

Section III. Evaluation and Qualification Criteria (Following Prequalification)

## Notes on Evaluation and Qualification Criteria This Section contains all the criteria that the Employer shall use to evaluate Bids and qualify Bidders. In accordance with ITB 32, ITB 35 and ITB 38, no other factors, methods or criteria shall be used. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

Evaluation and Qualification Criteria
(Following Prequalification)

1. 	Evaluation

1.1	Technical Evaluation

In addition to the criteria listed in ITB 35.1 (a) – (b) the following factors shall apply:

1.1.1	Personnel

The Bidder must demonstrate that it has the personnel for the key positions that meet the following requirements:

| No. | Position | Total Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | Project Manager |  |  |
| 2 | e.g. Chief Engineer(s)1 |  |  |
| 3 | e.g. Health & Safety (Accident Prevention) Officer2 |  |  |
| … |  |  |  |
| Notes for the Employer 1. Chief Engineer(s) or Section Manager(s) who is(are) responsible for the major activities should be evaluated. 2. The personnel for the key positions include an accident prevention officer, as appropriate. Alternative candidates for key positions should not be evaluated. Insert requirements for multiple contracts, if necessary. |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in Forms PER-1 and PER-2 in Section IV, Bidding Forms.

    - Equipment

The Bidder must demonstrate that it has the key equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number Required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |
| Notes for the Employer The items listed shall be limited to major items of equipment that are crucial to the proper and timely execution of the Contract, and items that Bidders may not readily be able to purchase, hire, or lease in the required time frame. Insert requirements for multiple contracts, if necessary. |  |  |

The Bidder shall provide further details of proposed items of equipment using Form EQU in Section IV, Bidding Forms.

    - Others

[Insert appropriate additional provisions, if any.]

＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿

1.2	Economic Evaluation

[Any adjustments in price that result from the procedures outlined below shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.”  Bid Prices quoted by Bidders shall remain unaltered.]

In addition to the criteria listed in ITB 38.2 (a) – (c) the following criteria shall apply.

1.2.1	Quantifiable nonmaterial nonconformities

[Pursuant to ITB 34.3 and ITB 38.2 (d), the cost of all quantifiable nonmaterial nonconformities or omissions (minor omissions or missing items) shall be evaluated. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of Bids.]

    - Other Factors

The following factors and methods will apply under ITB 38.2 (f):

(a)	Time Schedule

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities is: [insert number of days] _____ No credit will be given for earlier completion.

[The completion time specified shall be for the entire Plant and Installation Services or for parts or sections of the plant and services.]

or [where alternative time schedule is accepted, pursuant to ITB 13.2]

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities shall be between [insert number of days] ____________ minimum and [insert number of days] ____________ maximum.  The adjustment rate in the event of completion beyond the minimum period shall be [insert percentage in words and figures] _______ (%) for each week of delay from that minimum period. No credit will be given for completion earlier than the minimum designated period. Bids offering a completion date beyond the maximum designated period shall be rejected.

[One-fifth of a percent (0.2%) per week is a reasonable figure.  Alternatively, the rate may be a fixed amount per month, or pro rata per week, of delay related to the loss of benefits to the Employer.  The accepted period between the minimum and maximum time for completion should be such that the percentage or amount corresponding to the maximum period for completion should be less than or equal to the percentage or amount of liquidated damages specified in the PC in relation to GC Sub-Clause 26.2.]

(b)	Operating and Maintenance Costs

Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given hereafter, including the cost of spare parts for the initial period of operation stated below and based on prices furnished by each Bidder in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other employers similarly placed.  Such costs shall be added to the Bid Price for evaluation.

[Use one of the two options given below – delete the inapplicable option.]

Option 1: The operating and maintenance costs factors for calculation of the life cycle cost are:

(i)	number of years for life cycle [Insert life cycle period in years. The period should not exceed the period before a major overhaul of the facilities becomes necessary.]

(ii)	operating costs [Insert fuel and/or other input, unit cost for annual and total operational requirements.]

(iii)	maintenance costs, including the cost of spare parts for the initial period of operation, and

(iv)	a rate of [insert rate in words and figures] percent, to be used to discount to present value all annual future costs calculated under (ii) and (iii) above for the period specified in (i).

or

Option 2: Reference to the methodology specified in the Specification or elsewhere in the Bidding Documents

[Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Documents.]

The price of recommended spare parts quoted in Price Schedule No. 7 shall not be considered for evaluation.

(c)	Functional Guarantees of the Plant and Installation Services

The minimum (or maximum) requirements stated in the Specification for functional guarantees required in the Specification are:

| Functional Guarantee | Minimum (or Maximum, as appropriate) Requirement |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

For the purposes of evaluation, for each percentage point that the functional guarantee of the proposed Plant and Installation Services is below the norm specified in the Specification and in the above table, but above the minimum acceptable levels also specified therein, an adjustment of [insert amount in the currency of Bid evaluation] ___________________will be added to the Bid Price.  If the drop below the norm or the excess above the minimum acceptable levels is less than one percent, the adjustment will be prorated accordingly.

(d)	Work, services, facilities, etc., to be provided by the Employer

Where Bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the Bidding Documents, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the Contract.  Such costs shall be added to the Bid Price for evaluation.

(e)	Specific additional criteria

The following additional criteria will be used in the evaluation: [If applicable, insert a list of additional criteria.] __________________________________

The relevant evaluation method, if any, shall be as follows: [Insert the evaluation method.] _______________________________________________

    - Award Criteria for Multiple Contracts (ITB 38.4)

[Insert the following text in case of multiple contracts. Otherwise delete this EQC clause.

“Lots/Packages:

Bidders have the option to bid for any one or more lots/packages. Bids will be evaluated lot/package-wise, taking into account discounts offered, if any, for combined lots/packages. The Contract(s) will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer for combined lots/packages, subject to the selected Bidder(s) meeting the required qualification criteria for lot or combination of lots/packages as the case may be.”]

1.3	Alternatives Technical Solutions

Alternatives technical solutions, if invited in accordance with ITB 13.4, will be evaluated as follows: [Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Documents.]

2.	Qualification

(i)	Exchange Rate for Qualification Criteria

Wherever a Form in Section IV, Bidding Forms, requires a Bidder to state a monetary amount, Bidders should indicate the USD equivalent using the rate of exchange determined as follows:

- For turnover or financial data required for each year - Exchange rate prevailing on the last day of the respective calendar year.

- Value of single Contract - Exchange rate prevailing on the date of the Contract.

Exchange rates shall be taken from the publicly available source identified in BDS 37.1 or, in case such rates are not available in the source identified above, any other publicly available source acceptable to the Employer. Any error in determining the exchange rates may be corrected by the Employer.

(ii)	Qualification Criteria for Multiple Contracts

[Insert the following text in case of multiple contracts. Otherwise delete this Clause EQC 2 (ii).

“Criteria for qualification are the aggregate minimum requirements, or any other reasonable requirements set forth by the Employer, for the respective lots as specified under Financial Resources, Sub-Factors 2.2 (i) and (ii) below.”]

2.1	Update of Information

The Bidder shall continue to meet the criteria used at the time of prequalification regarding Eligibility, Historical Contract Non-Performance and Financial Situation.

2.2 Financial Resources

| Qualification Criteria |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - No. | - Factor/ Sub-Factor | - Requirement | - Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| ## 2.2 | ## Financial Resources | (i) The Bidder shall demonstrate that it has access to, or has available, liquid assets, unencumbered real assets, lines of credit, and other financial means (independent of any contractual advance payment) sufficient to meet the cash flow requirements estimated as USD [insert amount in USD]1 for the subject Contract(s) net of the Bidder’s other commitments. [insert requirements for multiple contracts, if necessary]. | Must meet requirement | Must meet requirement | Must meet [insert percentage] _________ percent 2 (_____%) of the requirement | Must meet [insert percentage] _________ percent3 (_____%) of the requirement | Form FIR - 1 |
|  |  | (ii) The Bidder shall also demonstrate, to the satisfaction of the Employer, that it has adequate sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments. [insert requirements for multiple contracts, if necessary]. | Must meet requirement | Must meet requirement | N/A | N/A | Form FIR - 1 and Form FIR - 2 |
| Notes for the Employer 1. Indicate the cash flow requirement for a number of months, determined as the total time needed by the Employer to pay a contractor’s invoice, allowing for (a) the actual time consumed for the works, from the beginning of the month invoiced, (b) the time needed by the Engineer to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delays. The total period should not exceed six (6) months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular Contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated Contract cost. 2. Usually not less than 25% of the requirement for each member of a JV. 3. Usually not less than 40% of the requirement for one member of a JV. |  |  |  |  |  |  |  |

2.3 	Subcontractors/manufacturers

Subcontractors/manufacturers for major items of supply or services identified in the prequalification document must meet or continue to meet the minimum criteria specified therein for each item.

Subcontractors/manufacturers for the following additional major items of supply or services must meet the following minimum criteria, herein listed for that item:

| Item No. | Description of Item | Minimum Criteria to be met |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

Failure to comply with this requirement will result in the rejection of the Subcontractor.

In the case of a Bidder who offers to supply and install major items of supply under the Contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using Form MAN provided in Section IV, Bidding Forms, showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and/or install that item in the Employer’s country. The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and ITB 5 and meets the minimum criteria listed above for that item.

Section III. Evaluation and Qualification Criteria (Without Prequalification)

## Notes on Evaluation and Qualification Criteria

This Section contains all the criteria that the Employer shall use to evaluate bids and qualify Bidders.  In accordance with ITB 32, ITB 35 and ITB 38, no other factors, methods or criteria shall be used. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

The “Notes for the Bidder” in this Section III, Evaluation and Qualification Criteria (Without Prequalification), shall be included in the actual Bidding Documents, prepared by the Employer.

Evaluation and Qualification Criteria
(Without Prequalification)

1. 	Evaluation

1.1	Technical Evaluation

In addition to the criteria listed in ITB 35.1 (a) – (b) the following factors shall apply:

1.1.1	Personnel

The Bidder must demonstrate that it has the personnel for the key positions that meet the following requirements:

| No. | Position | Total Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | Project Manager |  |  |
| 2 | e.g. Chief Engineer(s)1 |  |  |
| 3 | e.g. Health & Safety (Accident Prevention) Officer2 |  |  |
| … |  |  |  |
| Notes for the Employer 1. Chief Engineer(s) or Section Manager(s) who is(are) responsible for the major activities should be evaluated. 2. The personnel for the key positions include an accident prevention officer, as appropriate. Alternative candidates for key positions should not be evaluated. Insert requirements for multiple contracts, if necessary. |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in Forms PER-1 and PER-2 in Section IV, Bidding Forms.

1.1.2	Equipment

The Bidder must demonstrate that it has the key equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |
| Notes for the Employer 1. The items listed shall be limited to major items of equipment that are crucial to the proper and timely execution of the Contract, and items that Bidders may not readily be able to purchase, hire, or lease in the required time frame. 2. Insert requirements for multiple contracts, if necessary. |  |  |

The Bidder shall provide further details of proposed items of equipment using Form EQU in Section IV, Bidding Forms.

    - Others

[Insert appropriate additional provisions, if any.]

_______________________________________________________________

1.2	Economic Evaluation

[Any adjustments in price that result from the procedures outlined below shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.”  Bid Prices quoted by Bidders shall remain unaltered.]

In addition to the criteria listed in ITB 38.2 (a) – (c) the following criteria shall apply.

1.2.1	Quantifiable nonmaterial nonconformities

[Pursuant to ITB 34.3 and ITB 38.2 (d), the cost of all quantifiable nonmaterial nonconformities or omissions (minor omissions or missing items) shall be evaluated. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of Bids.]

    - Other Factors

The following factors and methods will apply under ITB 38.2 (f):

(a)	Time Schedule

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities is: [insert number of days]. No credit will be given for earlier completion.

[The completion time specified shall be for the entire Plant and Installation Services or for parts or sections of the plant and services.]

or [where alternative time schedule is accepted, pursuant to ITB 13.2]

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities shall be between [insert number of days] ____________ minimum and [insert number of days] ____________ maximum.  The adjustment rate in the event of completion beyond the minimum period shall be [insert percentage in words and figures] _______ (%) for each week of delay from that minimum period. No credit will be given for completion earlier than the minimum designated period. Bids offering a completion date beyond the maximum designated period shall be rejected.

[One-fifth of a percent (0.2%) per week is a reasonable figure.  Alternatively, the rate may be a fixed amount per month, or pro rata per week, of delay related to the loss of benefits to the Employer.  The accepted period between the minimum and maximum time for completion should be such that the percentage or amount corresponding to the maximum period for completion should be less than or equal to the percentage or amount of liquidated damages specified in the PC in relation to GC Sub-Clause 26.2.]

(b)	Operating and Maintenance Costs

Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given hereafter, including the cost of spare parts for the initial period of operation stated below and based on prices furnished by each Bidder in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other employers similarly placed.  Such costs shall be added to the Bid Price for evaluation.

[Use one of the two options given below – delete the inapplicable option.]

Option 1: The operating and maintenance costs factors for calculation of the life cycle cost are:

(i)	number of years for life cycle [Insert life cycle period in years. The period should not exceed the period before a major overhaul of the facilities becomes necessary.]

(ii)	operating costs [Insert fuel and/or other input, unit cost for annual and total operational requirements.]

(iii)	maintenance costs, including the cost of spare parts for the initial period of operation, and

(iv)	a rate of [insert rate in words and figures] percent, to be used to discount to present value all annual future costs calculated under (ii) and (iii) above for the period specified in (i).

or

Option 2: Reference to the methodology specified in the Specification or elsewhere in the Bidding Documents

[Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Documents.]

The price of recommended spare parts quoted in Price Schedule No. 7 shall not be considered for evaluation.

(c)	Functional Guarantees of the Plant and Installation Services

The minimum (or maximum) requirements stated in the Specification for functional guarantees required in the Specification are:

| Functional Guarantee | Minimum (or Maximum, as appropriate) Requirement |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

For the purposes of evaluation, for each percentage point that the functional guarantee of the proposed Plant and Installation Services is below the norm specified in the Specification and in the above table, but above the minimum acceptable levels also specified therein, an adjustment of [insert amount in the currency of Bid evaluation] ___________________will be added to the Bid Price.  If the drop below the norm or the excess above the minimum acceptable levels is less than one percent, the adjustment will be prorated accordingly.

(d)	Work, services, facilities, etc., to be provided by the Employer

Where Bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the Bidding Documents, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the Contract.  Such costs shall be added to the Bid Price for evaluation.

(e)	Specific additional criteria

The following additional criteria will be used in the evaluation: [If applicable, insert a list of additional criteria.]

_______________________________________________________________

The relevant evaluation method, if any, shall be as follows: [Insert the evaluation method.]

_______________________________________________________________

    - Award Criteria for Multiple Contracts (ITB 38.4)

[Insert the following text in case of multiple contracts. Otherwise delete this EQC clause.

“Lots/Packages:

Bidders have the option to bid for any one or more lots/packages. Bids will be evaluated lot/package-wise, taking into account discounts offered, if any, for combined lots/packages. The Contract(s) will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer for combined lots/packages, subject to the selected Bidder(s) meeting the required qualification criteria for lot or combination of lots/packages as the case may be.”]

1.3	Alternatives Technical Solutions

Alternatives technical solutions, if invited in accordance with ITB 13.4, will be evaluated as follows: _______ [Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Documents.]

2.	Qualification

(i)	Exchange Rate for Qualification Criteria

Wherever a Form in Section IV, Bidding Forms, requires a Bidder to state a monetary amount, Bidders should indicate the USD equivalent using the rate of exchange determined as follows:

- For turnover or financial data required for each year - Exchange rate prevailing on the last day of the respective calendar year.

- Value of single Contract - Exchange rate prevailing on the date of the Contract.

Exchange rates shall be taken from the publicly available source identified in BDS 37.1 or, in case such rates are not available in the source identified above, any other publicly available source acceptable to the Employer. Any error in determining the exchange rates may be corrected by the Employer.

(ii)	Qualification Criteria for Multiple Contracts

[Insert the following text in case of multiple Contracts. Otherwise delete this Clause EQC 2 (ii).

“Criteria for qualification are the aggregate minimum requirements, or any other reasonable requirements set forth by the Employer, for the respective lots as specified under Financial Situation and Experience, Sub-Factors 2.3.2, 2.3.3 (i), 2.3.3 (ii), 2.4.2 (a) and 2.4.2 (b) below.”]

| Eligibility and Qualification Criteria |  |  |  | Compliance Requirements |  |  |  | Documentation |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor /Sub-Factor | # Requirement |  | # Single Entity | # Joint Venture (existing or intended) |  |  | # Submission Requirements |  |
|  |  |  |  |  | # All Parties Combined | # Each Member | # One Member |  |  |
| 2.1 Eligibility |  |  |  |  |  |  |  |  |  |
| ## 2.1.1 | ## Nationality | Nationality in accordance with ITB 4.3. | Must meet requirement |  | N/A | Must meet requirement | N/A |  | Form ELI –1.1 and 1.2, with attachments |
| ## 2.1.2 | ## Conflict of Interest | No conflicts of interests as described in ITB 4.2. | Must meet requirement |  | N/A | Must meet requirement | N/A |  | Letter of Bid |
| ## 2.1.3 | ## JICA Ineligibility | Not having been declared ineligible by JICA as described in ITB 4.4. | Must meet requirement |  | N/A | Must meet requirement | N/A |  | Letter of Bid Form ACK |

| # Eligibility and Qualification Criteria |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - No. | Factor/ - Sub-Factor | - Requirement | - Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.2 Historical Contract Non-Performance |  |  |  |  |  |  |  |
| ## 2.2.1 | ## History of non-performing Contracts | Non-performance of a Contract(i) did not occur as a result of Contractor’s default since 1st January [insert year]1 | Must meet requirement(ii) | N/A | Must meet requirement(ii) | N/A | Form CON |
| ## 2.2.2 | ## Pending Litigation | ### All pending litigation shall in total not represent more than ______________ percent (___ %) [insert percentage figure]2 of the Bidder’s net worth and shall be treated as resolved against the Bidder. | Must meet requirement(ii) | N/A | Must meet requirement(ii) | N/A | Form CON |
| ## 2.2.3 | ## Litigation History | ### No consistent history of court/arbitral award decisions3 against the Bidder(iii) since 1st January [insert year] 4 | Must meet requirement(ii) | N/A | Must meet requirement(ii) | N/A | Form CON |
| Notes for the Bidder (i) Non-performance, as decided by the Employer, shall include all Contracts: (a) where non performance was not challenged by the Contractor, including through referral to the dispute resolution mechanism under the respective Contract, and (b) that were so challenged but fully settled against the Contractor. Non-performance shall not include Contracts where Employers decision was overruled by the dispute resolution mechanism. Non-performance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective Contract and where all appeal instances available to the Applicant have been exhausted. (ii) This requirement also applies to Contracts executed by the Bidder as a JV member. (iii) The Bidder shall provide accurate information on the related Bidding Form about any litigation or arbitration resulting from Contracts completed or ongoing under its execution over the last five (5) years. A consistent history of awards against the Bidder or any member of a joint venture may result in rejection of the Bid. |  |  |  |  |  |  |  |
| Notes for the Employer 1. Year should usually be one (1) or two (2) years prior to the Bid submission deadline. 2. The percentage should be normally within the range of 50% to 100% of a Bidder’s net worth. 3. The criterion for rejection should be that of numerous arbitral awards or court decisions against the Bidder, taking the number and amount of Contracts executed. As an indicative example, the occurrence of one (1) or two (2) adverse cases over five (5) years for a Contractor handling, on average, ten (10) Contracts simultaneously, should not be a cause for rejection. If dispute resolution is found relatively frequently in the business of the Bidder, it may indicate an attitude of the management of the firm that could be dangerous for the Employer if the Bidder were awarded the Contract, and further investigation with previous Employers may be warranted. 4. Year should usually be five (5) years prior to the Bid submission deadline. |  |  |  |  |  |  |  |

| Eligibility and Qualification Criteria |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor/ Sub-Factor | Requirement | - Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.3 Financial Situation |  |  |  |  |  |  |  |
| ## 2.3.1 | ## Financial Performance | The audited balance sheets or, if not required by the law of the Bidder’s country, other financial statements acceptable to the Employer, for the last [insert number of years]____ years1 shall be submitted and must demonstrate the current soundness of the Bidder’s financial position and its prospective long term profitability . As the minimum requirement, a Bidder’s net worth calculated as the difference between total assets and total liabilities should be positive2. | Must meet requirement | N/A | Must meet requirement | N/A | Form FIN – 1 with attachments |
| ## 2.3.2 | Average Annual Turnover | ### Minimum average annual turnover of [insert amount in USD]3__________________, calculated as total certified payments received for Contracts in progress and/or completed, within the last [insert number of years]______ years4 divided by [insert number of years] _______ years5. [insert requirements for multiple contracts, if necessary]. | Must meet requirement | Must meet requirement | Must meet [insert percentage] ________ percent6 (_____%) of the requirement | Must meet [insert percentage] _________ percent7 (_____%) of the requirement | Form FIN – 2 |
| ## 2.3.3 | Financial Resources | (i) The Bidder shall demonstrate that it has access to, or has available, liquid assets, unencumbered real assets, lines of credit, and other financial means (independent of any contractual advance payment) sufficient to meet the cash flow requirements estimated as USD [insert amount in USD]8 for the subject Contract(s) net of the Bidder’s other commitments. ### [insert requirements for multiple Contracts, if necessary] | Must meet requirement | Must meet requirement | Must meet [insert percentage] _________ percent 6 (_____%) of the requirement | Must meet [insert percentage] _________ percent7 (_____%) of the requirement | Form FIR - 1 |
|  |  | (ii) The Bidder shall also demonstrate, to the satisfaction of the Employer, that it has adequate sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments. [insert requirements for multiple Contracts, if necessary] | Must meet requirement | Must meet requirement | N/A | N/A | Form FIR – 1 and Form FIR - 2 |
| Notes for the Employer 1. Time period usually specified is five (5) years; it may be reduced to three (3) years minimum (in agreement with JICA) under special country circumstances, such as to provide opportunity for a newly privatized industry with limited period of existence, but with suitable experience, etc. Firms owned by individuals and partnerships may not be required to maintain audited balance sheets by the laws of their countries of origin; in such cases, the Employer may relax the audit requirement, but should request other acceptable financial statements. 2. The financial information provided by an Bidder should be reviewed in its entirety to allow a truly informed judgment, and the pass-fail decision on the financial position of the Applicant should be given on this basis. Any abnormal features which may lead to financial problems should alert the Employer to seek expert professional advice for further review and interpretation. 3. The amount stated should normally not be less than twice the estimated annual turnover in the proposed Contract (based on a straight-line projection of the Employer’s estimated cost, including contingencies, over the Contract duration). The multiplier of 2 may be reduced for very large Contracts but should not be less than 1.5. 4. The time period is normally five (5) years or more, but may be reduced to not less than three (3) years (in agreement with JICA) under special country circumstances, such as to provide opportunities for a newly privatized industry with only a short record of experience, etc. 5. Same number of years as in 4. above. 6. Usually not less than 25% of the requirement for each member of a JV. 7. Usually not less than 40% of the requirement for one member of a JV. 8. Indicate the cash flow requirement for a number of months, determined as the total time needed by the Employer to pay a Contractor’s invoice, allowing for (a) the actual time consumed for the works, from the beginning of the month invoiced, (b) the time needed by the Project Manager to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delays. The total period should not exceed six (6) months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular Contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated Contract cost. |  |  |  |  |  |  |  |

| Eligibility and Qualification Criteria |  |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. |  | Factor/ Sub-Factor | - Requirement | - Single Entity | Joint Venture (existing or intended) |  |  | - Submission Requirements |
|  |  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.4 Experience |  |  |  |  |  |  |  |  |
| ## 2.4.1 |  | ## General Experience | Experience under contracts in the role of prime contractor (single entity or JV member), Subcontractor, or management contractor(i) for at least the last [insert number of years] ________ years1 starting 1st January [insert year] ____. | Must meet requirement | N/A | Must meet requirement | N/A | Form EXP - 1 |
| 2.4.2 (a) |  | Specific Experience | A minimum number of [insert number of contracts]2 similar(ii) contracts that have been satisfactorily and substantially(iii) completed as a prime contractor (single entity or JV member)(iv) between 1st January [insert year]3 and the Bid submission deadline. [insert requirements for multiple Contracts, if necessary] | Must meet requirement | Must meet requirements(v) | N/A | N/A | Form EXP - 2(a) |
| ## 2.4.2 (b) | ## Specific Experience |  | For the above or other contracts completed and under implementation as prime contractor (single entity or JV member), management contractor or Subcontractor(vi) between 1st January [insert year]4 and the Bid submission deadline, a minimum experience in the following key activities successfully completed [list activities, as applicable]. [insert requirements for multiple Contracts, if necessary] (vii) | Must meet requirements (can be a specialist Subcontractor) | Must meet requirements (can be a specialist Subcontractor) | N/A | N/A | Form EXP - 2(b) |
| Notes for the Bidder (i) A management contractor is a firm which takes on the role of contract management as a “general” contractor of sort could do. It does not normally perform directly the work(s) associated with the Contract. Rather, it manages the work of other (sub) contractors while bearing full responsibility and risk for price, quality, and timely performance of the contract. (ii) The similarity shall be based on the physical size, complexity, methods/technology and/or other characteristics described in Section VI, Employer’s Requirements. Summation of number of small value Contracts (less than the value specified under requirement) to meet the overall requirement will not be accepted. (iii) Substantial completion shall be based on 80% or more works completed under the Contract. (iv) For contracts under which the Bidder participated as a JV member, only the Bidder’s share, by value, shall be considered to meet this requirement. (v) In case of a JV, the value of Contracts completed by its members shall not be aggregated to determine whether the requirement of the minimum value of a single Contract has been met. Instead, each Contract performed by each member shall satisfy the minimum value of a single Contract as required for single entity. In determining whether the JV meets the requirement of total number of Contracts, only the number of Contracts completed by all members each of value equal or more than the minimum value required shall be aggregated. (vi) For Contracts under which the Bidder participated as a JV member or Subcontractor, only the Bidder’s share shall be counted to meet this requirement. (vii) The minimum experience requirement for multiple Contracts will be the sum of the minimum requirements for respective individual contracts. |  |  |  |  |  |  |  |  |
| Notes for the Employer - The time period is normally five (5) years or more, but may be reduced to not less than three (3) years (in agreement with JICA) under special country circumstances, such as to provide opportunities for a newly privatized industry with only a short record of experience. - The range of contract numbers should be one (1) to three (3), depending on the size, value, nature and complexity of the subject contract, the exposure of the Employer to risk of contractor default, country conditions and history of similar works constructed in the past. - The time range is normally five (5) years, and may be extended up to a period of ten (10) years for large-scale projects. - Same as that stipulated in 3 above. |  |  |  |  |  |  |  |  |

2.5 	Subcontractors/manufacturers

Subcontractors/manufacturers for the following major items of supply or services must meet the following minimum criteria, herein listed for that item:

| Item No. | Description of Item | Minimum Criteria to be met |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

Failure to comply with this requirement will result in rejection of the Subcontractor.

In the case of a Bidder who offers to supply and install major items of supply under the Contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using Form MAN provided in Section IV, Bidding Forms, showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and install that item in the Employer’s country. The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and ITB 5 and meets the minimum criteria listed above for that item.

OPTION B:
Two-Stage One-Envelope Bidding

Section I. Instructions to Bidders

## Notes on Instructions to Bidders Section I, Instructions to Bidders, provides the information necessary for Bidders to prepare responsive Bids in accordance with the requirements of the Employer. It also gives information on Bid submission, opening, and evaluation, and on the award of the Contract. The use of the Standard Instructions to Bidders set forth in Section I of these Standard Bidding Documents for the Procurement of Plant Design, Supply and Installation (version 1.0) published by JICA in February, 2013 (hereafter referred to as “Standard ITB”) is required, in all Bidding Documents for Plant Design, Supply and Installation works financed under Japanese ODA Loans, and they shall be used without modification. Any necessary changes, acceptable to JICA, to address specific country and project issues, shall be introduced only through the Bid Data Sheet. The Instructions to Bidders will not be part of the Contract.

Section I.  Instructions to Bidders

[Note to the Employer: The instructions to Bidders governing all Two-Stage One-Envelope bidding processes for Plant Design, Supply and Installation Contracts funded with Japanese ODA Loans are the Standard Instructions to Bidders included in Option B, Two-Stage One-Envelope Bidding, of the Standard Bidding Documents for Procurement of Plant Design, Supply and Installation (SBD (Plant)) (version 1.0) published by JICA in February 2013.

A copy of the Standard Instructions to Bidders may be attached to the Bidding Documents prepared by the Employer for reference purposes only. If the Instructions to Bidders in the Bidding Documents prepared by the Employer contain modifications from the Standard Instructions to Bidders, JICA will not consider them valid and the Standard Instructions to Bidders, as defined above, shall apply.

Instead of attaching a copy of the Standard Instructions to Bidders, the Employer may use the following introductory text.]

The Instructions to Bidders governing this bidding process are the “Instructions to Bidders included in Option B, Two-Stage One-Envelope Bidding, Section I,” of the Standard Bidding Documents for Procurement of Plant Design, Supply and Installation (version 1.0) published by JICA in February 2013. Those Instructions to Bidders are available on the JICA’s web site shown below:

http://www.jica.go.jp/english/our_work/types_of_assistance/oda_loans/oda_op_info/guide/tender/index.html

A copy of the Instructions to Bidders is not attached to these Bidding Documents.

Section II. Bid Data Sheet

## Notes on Bid Data Sheet Section II, Bid Data Sheet, shall be filled in by the Employer before issuance of the Bidding Documents. The Bid Data Sheet (BDS) contains information and provisions that are specific to a particular bidding process. The Employer must specify in the BDS only the information that the ITB request be specified in the BDS. All information shall be provided; no clause shall be left blank. To facilitate the preparation of the BDS, its clauses are numbered with the same numbers as those of the corresponding ITB clauses.

Bid Data Sheet

| A. General |  |
| --- | --- |
| ITB 1.1 | The number of the Invitation for Bids is : [insert number of the Invitation for Bids] |
| ITB 1.1 | The Employer is: [insert name of Employer] |
| ITB 1.1 | The name, identification and number of lot(s) (contract(s)) comprising this ICB is: [insert name, number and identification of lot(s) (contract(s))] |
| ITB 2.1 | The Borrower is: [insert name of Borrower] |
| ITB 2.1 | The number of the Loan Agreement is: [insert Loan Agreement Number] The amount of a Japanese ODA Loan is: [insert amount in Japanese Yen] The signed date of the Loan Agreement is: [insert signed date of Loan Agreement] |
| ITB 2.1 | The name of the Project is: [insert name of the Project] |
| ITB 2.2 | The applicable Guidelines for Procurement under Japanese ODA Loans are those published in: [insert one of the following: April 2012, March 2009, or October 1999] |
| ITB 3.1(c) | A list of debarred firms and individuals is available at the World Bank’s website: www.worldbank.org/debarr |
| ITB 4.5 | This bidding [select “is” or “is not”, as appropriate] subject to prequalification. |
| B. Bidding Documents |  |
| ITB 7.1 | For clarification purposes only, the Employer’s address is: [insert the corresponding information as required below. This address may be the same as or different from that specified under ITB 20.1 for Bid submission.] Attention: [insert full name of person, if applicable] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: [insert name of country] Telephone: [insert telephone number, including country and city codes] Facsimile number: [insert facsimile number, including country and city codes] Electronic mail address: [insert email address, if applicable] |
| ITA 7.1 | Responses to any request for clarification, if any, [select “will” or “will not”, as appropriate] be published on the Employer’s web page indicated below. Web page: [Insert the Employer’s web page if responses to requests for clarifications will be published on the Employer’s web page, otherwise omit.] |
| ITB 7.4 | A pre-bid meeting _____ [insert “will” and insert the date, time and place information in the spaces provided below if a pre-bid meeting will take place, taking into consideration that the meeting should take place no later than four weeks before the deadline for Bid submission. Otherwise, insert “will not” and insert “Not Applicable” in the spaces provided below for the date, time and place] take place at the following date, time and place: Date: Time: Place: A site visit conducted by the Employer ________ [insert “will be” or “will not be”, as appropriate] organized. |
| ITB 8.2 | Addenda, if any, [select “will” or “will not”, as appropriate] be published on the Employer’s web page. |
| ITB 10.1 | The language of the Bid is: [insert one of the following: “Japanese”, “English”, “Spanish” or “French”] |
| C1. First Stage Bids: Preparation |  |
| ITB 11.1 (j) | The Bidder shall submit with its First Stage Bid the following additional documents: [List any additional documents not already listed in ITB 11.1 that must be submitted with the First Stage Bid. If no additional documents are to be submitted, insert “None”.] |
| ITB 16.1 (b) | The period following completion of Plant and Installation Services during which spare parts, special tools etc. shall be available, is [insert number of years as appropriate, normally two (2) years] _____ |
| ITB 18.1 | In addition to the original of the First Stage Bid, the number of copies is: [insert number of copies] |
| ITB 18.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: [insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the Bid] |
| C2. First Stage Bids: Submission and Opening |  |
| ITB 20.1 | For First Stage Bid submission purposes only, the Employer’s address is: [This address may be the same as or different from that specified under provision ITB 7.1 for clarifications] Attention: [insert full name of person, if applicable] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: [insert name of country] The deadline for First Stage Bid submission is: Date: [insert day, month, and year, e.g., 15 June, 2013] Time: [insert time, and identify if a.m. or p.m. e.g., 10:30 a.m.] [The date and time should be the same as those provided in the Invitation for Bids, unless subsequently amended pursuant to ITB 20.2.] |
| ITB 23.1 | The First Stage Bid opening shall take place at: Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City : [insert name of city or town] Country: [insert name of country] Date: [insert day, month, and year, e.g., 15 June, 2013] Time: [insert time, and identify if a.m. or p.m. e.g., 10:30 a.m.] [The date and time should be the same as those given for the deadline for submission of Bids (ITB 20).] |
| E1. Second Stage Bid Preparation |  |
| ITB 31.1 (k) | The Bidder shall submit with its Second Stage Bid the following additional documents: [List any additional document not already listed in ITB 31.1 that must be submitted with the Second Stage Bid. If no additional documents are to be submitted, insert “None”.] |
| ITB 33.1 | [Use one of the following options as appropriate.] Bidders shall quote for the entire Plant and Installation Services on a single responsibility basis. [or] Bidders shall quote for the following components or services on a single responsibility basis: [insert list of components or services] _______________________________________ [and/or] The following components or services will be provided under the responsibility of the Employer: [insert list of components or services] _______________________________________ |
| ITB33.4 | [The following provision should be included and the corresponding information inserted only if duties, taxes and other levies will be exempted, reimbursed, or paid by the Employer on behalf of the Contractor. Otherwise delete this BDS 33.4.] Duties, taxes and other levies indicated below shall be [choose one of the following: “exempted”, reimbursed, “paid by the Employer on behalf of the Contractor”, as appropriate.]: [List duties, taxes and other levies.] |
| ITB 33.4(a) | Named place of destination is: ______ [insert destination] |
| ITB 33.4(d) | Named place of final destination is: ______ [insert destination] [Note: When the named place of destination is the project site, the transportation costs for Schedule No. 1 items are covered under CIP and therefore will not be stated here. This schedule will cover only for items in Schedule No. 2. If the named place of destination is different from the site of installation (project site), then the transport cost from the named place of destination to project site for Schedule No. 1 shall be also included here.] |
| ITB 33.6 | The prices quoted by the Bidder shall be: [insert “fixed” or “adjustable”]. |
| ITB 34.1 | The currency(ies) of the Bid shall be as follows: - Plant and equipment to be supplied from abroad shall be quoted entirely in: [insert Japanese Yen and/or other international trading currency or currencies]. - Plant and equipment to be supplied from within the Employer’s country shall be quoted in the currency of the Employer’s country: [insert currency of Employer’s country]. - Design and installation shall be quoted in either foreign and/or local currency, depending upon the currency in which the costs are to be incurred. |
| ITB 35.1 | The Second Stage Bid validity period shall be ______ days. [insert number of days required for evaluation, approval and award plus contingency] [This period should be realistic, allowing sufficient time to evaluate the Bids, bearing in mind the complexity of the Facilities and the time required for obtaining references, clarifications, clearances, and approvals (including the JICA’s concurrence) and for notification of the award. Normally the validity period should not exceed 120 days.] |
| ITB 35.3 (a) | The Bid Price shall be adjusted by the following factor: [insert factor for adjustment] [The local currency portion of the Contract Price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract Price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If Adjustable Price is applied in accordance with BDS 33.6; Not Applicable. |
| ITB 35.3 (b) | The fixed portion of the Bid Price shall be adjusted by the following factor: [insert factor for adjustment] [The local currency portion of the fixed portion of the Contract Price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the fixed portion of the Contract Price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If there is no fixed portion of the Bid Price, or the entire price is fixed; Not Applicable. |
| ITB 36.1 | The amount and currency of the Bid Security shall be: [insert amount and currency of the Bid Security. The amount should be approximately 2% of the estimated cost of the Contract.] |
| ITB 36.2 (d) | Other types of acceptable securities: [Insert names of other acceptable securities. Insert “None” if no other forms of Bid Securities besides those listed in ITB 36.2 (a) through (c) are acceptable.] |
| ITB 37.1 | In addition to the original of the Second Stage Bid, the number of copies is: [insert number of copies] |
| ITB 37.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: ___________________________________________ [insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the Bid] |
| E3. Second Stage Bids: Evaluation and Comparison |  |
| ITB 49.1 | The currency that shall be used for Bid evaluation and comparison purposes to convert all Bid Prices expressed in various currencies into a single currency is: [insert Japanese Yen or another single currency] __________________________________________ The source of exchange rate shall be: [insert name of the source of exchange rates (e.g., the Central Bank in the Employer’s Country)] The date for the exchange rate shall be: [insert a date (day, month and year, e.g., 15 June , 2013), not earlier than 30 days prior to, nor later than, the date for Second Stage Bid opening specified in ITB 42.1 ] |

Section III. Evaluation and Qualification Criteria (Following Prequalification)

Notes on Evaluation and Qualification Criteria

This Section contains all the criteria that the Employer shall use to evaluate Bids and qualify Bidders.  In accordance with ITB 27, ITB 28, ITB 50 and ITB 52, no other factors, methods or criteria shall be used. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

Evaluation and Qualification Criteria
(Following Prequalification)

First Stage Bids

1. 	Evaluation

In addition to the criteria listed in ITB 28.1 (a) – (c) the following factors shall apply:

1.1	Personnel

The Bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements:

| No. | Position | Total Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | Project Manager |  |  |
| 2 | e.g. Chief Engineer(s)1 |  |  |
| 3 | e.g. Health & Safety (Accident Prevention) Officer2 |  |  |
| … |  |  |  |
| Notes for the Employer 1. Chief Engineer(s) or Section Manager(s) who is(are) responsible for the major activities should be evaluated. 2. The personnel for the key positions include an accident prevention officer, as appropriate. Alternative candidates for key positions should not be evaluated.. Insert requirements for multiple contracts, if necessary. |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in Forms PER-1 and PER-2 in Section IV, Bidding Forms.

1.2	Equipment

The Bidder must demonstrate that it has the key equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |
| Notes for the Employer 1. The items listed shall be limited to major items of equipment that are crucial to the proper and timely execution of the Contract, and items that Bidders may not readily be able to purchase, hire, or lease in the required time frame. 2. Insert requirements for multiple contracts, if necessary. |  |  |

The Bidder shall provide further details of proposed items of equipment using Form EQU in Section IV, Bidding Forms.

1.3	Others

[Insert appropriate additional provisions, if any.]

2. 	Qualification

(i)	Exchange Rate for Qualification Criteria

Wherever a Form in Section IV, Bidding Forms, requires a Bidder to state a monetary amount, Bidders should indicate the USD equivalent using the rate of exchange determined as follows:

- For turnover or financial data required for each year - Exchange rate prevailing on the last day of the respective calendar year.

- Value of single Contract - Exchange rate prevailing on the date of the Contract.

Exchange rates shall be taken from the publicly available source identified in BDS 49.1 or, in case such rates are not available in the source identified above, any other publicly available source acceptable to the Employer. Any error in determining the exchange rates may be corrected by the Employer.

(ii)	Qualification Criteria for Multiple Contracts

[Insert the following text in case of multiple Contracts. Otherwise delete this Clause EQC 2 (ii).

“Criteria for qualification are the aggregate minimum requirements, or any other reasonable requirements set forth by the Employer, for the respective lots as specified under Financial Resources, Sub-Factors 2.2 (i) and (ii) below.”]

2.1	Update of Information

The Bidder shall continue to meet the criteria used at the time of prequalification regarding Eligibility, Historical Contract Non-Performance and Financial Situation.

2.2      Financial Resources

| Qualification Criteria |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor/ Sub-Factor | - Requirement | - Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| ## 2.2 | ## Financial Resources | (i) The Bidder shall demonstrate that it has access to, or has available, liquid assets, unencumbered real assets, lines of credit, and other financial means (independent of any contractual advance payment) sufficient to meet the cash flow requirements estimated as USD [insert amount in USD]1 for the subject contract(s) net of the Bidder’s other commitments. [insert requirements for multiple Contracts, if necessary] | Must meet requirement | Must meet requirement | Must meet [insert percentage] _________ percent 2 (_____%) of the requirement | Must meet [insert percentage] _________ percent3 (_____%) of the requirement | Form FIR - 1 |
|  |  | (ii) The Bidder shall also demonstrate, to the satisfaction of the Employer, that it has adequate sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments. [insert requirements for multiple Contracts, if necessary]. | Must meet requirement | Must meet requirement | N/A | N/A | Form FIR - 1 and Form FIR - 2 |
| Notes for the Employer 1. Indicate the cash flow requirement for a number of months, determined as the total time needed by the Employer to pay a Contractor’s invoice, allowing for (a) the actual time consumed for the works, from the beginning of the month invoiced, (b) the time needed by the Engineer to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delay. The total period should not exceed six (6) months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular Contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated Contract cost. 2. Usually not less than 25% of the requirement for each member of a JV. 3. Usually not less than 40% of the requirement for one member of a JV. |  |  |  |  |  |  |  |

2.3	Subcontractors/Manufacturers

Subcontractors/manufacturers for major items of supply or services identified in the prequalification documents must meet or continue to meet the minimum criteria specified therein for each item.

Subcontractors/manufacturers for the following additional major items of supply or services must meet the following minimum criteria, herein listed for that item:

| Item No. | Description of Item | Minimum Criteria to be met |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

Failure to comply with this requirement will result in rejection of the Subcontractor.

In the case of a Bidder who offers to supply and install major items of supply under the Contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using Form MAN provided in Section IV, Bidding Forms, showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and/or install that item in the Employer’s country. The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and ITB 5 and meets the minimum criteria listed above for that item.

Second Stage Bids

1. 	Evaluation

1.1	Economic Evaluation

[Any adjustments in price that result from the above procedures shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.”  Bid Prices quoted by Bidders shall remain unaltered.]

1.1.1	Quantifiable nonmaterial nonconformities

[Pursuant to ITB 47.3 and ITB 50.3 (d), the cost of all quantifiable nonmaterial nonconformities or omissions (minor omissions or missing items) shall be evaluated. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of Bids.]

    - Other Factors

The following factors and methods will apply under ITB 50.3 (f):

(a)	Time Schedule:

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities is: [insert number of days] _____. No credit will be given for earlier completion.

[The completion time specified shall be for the entire Plant and Installation Services or for parts or sections of the plant and services.]

or

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities shall be between [insert number of days] _______ minimum and [insert number of days] _______ maximum.  The adjustment rate in the event of completion beyond the minimum period shall be [insert percentage in words and figures] ______ (%) for each week of delay from that minimum period. No credit will be given for completion earlier than the minimum designated period. Bids offering a completion date beyond the maximum designated period shall be rejected.

[One-fifth of a percent (0.2%) per week is a reasonable figure.  Alternatively, the rate may be a fixed amount per month, or pro rata per week, of delay related to the loss of benefits to the Employer.  The accepted period between the minimum and maximum time for completion should be such that the percentage or amount corresponding to the maximum period for completion should be less than or equal to the percentage or amount of liquidated damages specified in the PC in relation to GC Sub-Clause 26.2.]

(b)	Operating and Maintenance Costs

Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given hereafter, including the cost of spare parts for the initial period of operation stated below and based on prices furnished by each Bidder in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other Employers similarly placed.  Such costs shall be added to the Bid Price for evaluation.

[Use one of the two options given below – delete the inapplicable option.]

Option 1: The operating and maintenance costs factors for calculation of the life cycle cost are:

(i)	number of years for life cycle: [Insert life cycle period in years. The period should not exceed the period before a major overhaul of the facilities becomes necessary.] _________________

(ii)	operating costs: [Insert fuel and/or other input, unit cost for annual and total operational requirements.] _________________

(iii)	maintenance costs, including the cost of spare parts for the initial period of operation, and

(iv)	a rate of [insert rate in words and figures] percent, to be used to discount to present value all annual future costs calculated under (ii) and (iii) above for the period specified in (i).

or

Option 2: Reference to the methodology specified in the Specification or elsewhere in the Bidding Documents

[Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Documents.]

The price of recommended spare parts quoted in Price Schedule No. 7 shall not be considered for evaluation.

(c)	Functional Guarantees of the Plant and Installation Services

The minimum (or maximum) requirements stated in the Specification for functional guarantees required in the Specification are:

| Functional Guarantee | Minimum (or Maximum, as appropriate) Requirement |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

For the purposes of evaluation, for each percentage point that the functional guarantee of the proposed Plant and Installation Services is below the norm specified in the Specification and in the above table, but above the minimum acceptable levels also specified therein, an adjustment of [insert amount in the currency of Bid evaluation] _______________ will be added to the Bid Price. If the drop below the norm or the excess above the minimum acceptable levels is less than one percent, the adjustment will be prorated accordingly.

(d)	Work, services, facilities, etc., to be provided by the Employer

Where Bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the Bidding Documents, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the Contract.  Such costs shall be added to the Bid Price for evaluation.

(e)	Specific additional criteria

The following additional criteria will be used in the evaluation: [If applicable, insert a list of additional criteria which may also be included as amendments in the Invitation for Second Stage Bids.]

____________________________________________________________________________

The relevant evaluation method shall be as follows: [Insert the evaluation method.]

____________________________________________________________________________

    - Award Criteria for Multiple Contracts (ITB 50.5)

[Insert the following text in case of multiple contracts. Otherwise delete this EQC clause.

“Lots/Packages:

Bidders have the option to bid for any one or more lots/packages. Bids will be evaluated lot/package-wise, taking into account discounts offered, if any, for combined lots/packages. The Contract(s) will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer for combined lots/packages, subject to the selected Bidder(s) meeting the required qualification criteria for lot or combination of lots/packages as the case may be.”]

Section III. Evaluation and Qualification Criteria (Without Prequalification)

Notes on Evaluation and Qualification Criteria

This Section contains all the criteria that the Employer shall use to evaluate Bids and qualify Bidders.  In accordance with ITB 27, ITB 28, ITB 50 and ITB 52, no other factors, methods or criteria shall be used. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

The “Notes for the Bidder” in this Section III, Evaluation and Qualification Criteria (Without Prequalification), shall be included in the actual Bidding Documents, prepared by the Employer.

Evaluation and Qualification Criteria
(Without Prequalification)

First Stage Bids

1. 	Evaluation

In addition to the criteria listed in ITB 28.1 (a) – (c) the following factors shall apply:

1.1	Personnel

The Bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements:

| No. | Position | Total Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | Project Manager |  |  |
| 2 | e.g. Chief Engineer(s)1 |  |  |
| 3 | e.g. Health & Safety (Accident Prevention) Officer2 |  |  |
| … |  |  |  |
| Notes for the Employer 1. Chief Engineer(s) or Section Manager(s) who is(are) responsible for the major activities should be evaluated. 2. The personnel for the key positions include an accident prevention officer, as appropriate. Alternative candidates for key positions should not be evaluated. Insert requirements for multiple contracts, if necessary. |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in Forms PER-1 and PER-2 in Section IV, Bidding Forms.

1.2	Equipment

The Bidder must demonstrate that it has the key equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |
| Notes for the Employer 1. The items listed shall be limited to major items of equipment that are crucial to the proper and timely execution of the Contract, and items that Bidders may not readily be able to purchase, hire, or lease in the required time frame. 2. Insert requirements for multiple contracts, if necessary. |  |  |

The Bidder shall provide further details of proposed items of equipment using Form EQU in Section IV, Bidding Forms.

1.3	Others

[Insert appropriate additional provisions, if any.]

＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿＿

2.	Qualification

(i)	Exchange Rate for Qualification Criteria

Wherever a Form in Section IV, Bidding Forms, requires a Bidder to state a monetary amount, Bidders should indicate the USD equivalent using the rate of exchange determined as follows:

- For turnover or financial data required for each year - Exchange rate prevailing on the last day of the respective calendar year.

- Value of single Contract - Exchange rate prevailing on the date of the Contract.

Exchange rates shall be taken from the publicly available source identified in BDS 49.1 or, in case such rates are not available in the source identified above, any other publicly available source acceptable to the Employer. Any error in determining the exchange rates may be corrected by the Employer.

(ii)	Qualification Criteria for Multiple Contracts

[Insert the following text in case of multiple Contracts. Otherwise delete this Clause EQC 2 (ii).

“Criteria for qualification are the aggregate minimum requirements, or any other reasonable requirements set forth by the Employer, for the respective lots as specified under Financial Situation and Experience, Sub-Factors 2.3.2, 2.3.3 (i), 2.3.3 (ii), 2.4.2 (a) and 2.4.2 (b) below.”]

| Eligibility and Qualification Criteria |  |  | Compliance Requirements |  |  |  |  |  |  | Documentation |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor/ Sub-Factor | # Requirement |  | # Single Entity | # Joint Venture (existing or intended) |  |  |  | # Submission Requirements |  |  |
|  |  |  |  |  | # All Parties Combined |  | # Each Member | # One Member |  |  |  |
| 2.1 Eligibility |  |  |  |  |  |  |  |  |  |  |  |
| ## 2.1.1 | ## Nationality | Nationality in accordance with ITB 4.3. |  | Must meet requirement | N/A | Must meet requirement |  | N/A |  |  | Form ELI –1.1 and 1.2, with attachments |
| ## 2.1.2 | ## Conflict of Interest | No conflicts of interests as described in ITB 4.2. |  | Must meet requirement | N/A | Must meet requirement |  | N/A |  |  | Letter of Bid |
| ## 2.1.3 | ## JICA Ineligibility | Not having been declared ineligible by JICA as described in, ITB 4.4. |  | Must meet requirement | N/A | Must meet requirement |  | N/A |  |  | Letter of Bid Form ACK |

| # Eligibility and Qualification Criteria |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor/ Sub-Factor | Requirement | Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.2 Historical Contract Non-Performance |  |  |  |  |  |  |  |
| ## 2.2.1 | ## History of non-performing Contracts | Non-performance of a contract(i) did not occur as a result of contractor’s default since 1st January [insert year]1 | Must meet requirement(ii) | N/A | Must meet requirement(ii) | N/A | Form CON |
| ## 2.2.2 | ## Pending Litigation | ### All pending litigation shall in total not represent more than ______________ percent (___ %) [insert percentage figure]2 of the Bidder’s net worth and shall be treated as resolved against the Bidder. | Must meet requirement(ii) | N/A | Must meet requirement(ii) | N/A | Form CON |
| ## 2.2.3 | ## Litigation History | ### No consistent history of court/arbitral award decisions3 against the Bidder(iii) since 1st January [insert year] 4 | Must meet requirement(ii) | N/A | Must meet requirement(ii) | N/A | Form CON |
| Notes for the Bidder (i) Non-performance, as decided by the Employer, shall include all contracts (a) where non-performance was not challenged by the Contractor, including through referral to the dispute resolution mechanism under the respective Contract, and (b) that were so challenged but fully settled against the Contractor. Non-performance shall not include Contracts where Employers decision was overruled by the dispute resolution mechanism. Non-performance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective Contract and where all appeal instances available to the Applicant have been exhausted. (ii) This requirement also applies to Contracts executed by the Bidder as a JV member. (iii) The Bidder shall provide accurate information on the related Bidding Form about any litigation or arbitration resulting from Contracts completed or ongoing under its execution over the last five (5) years. A consistent history of awards against the Bidder or any member of a joint venture may result in rejection of the Bid. |  |  |  |  |  |  |  |
| Notes for the Employer 1. Year should usually be one (1) or two (2) years prior to the Bid submission deadline. 2. The percentage should be normally within the range of 50% to 100% of a Bidder’s net worth. 3. The criterion for rejection should be that of numerous arbitral awards or court decisions against the Bidder, taking the number and amount of Contracts executed. As an indicative example, the occurrence of one (1) or two (2) adverse cases over five (5) years for a Contractor handling, on average, ten (10) Contracts simultaneously, should not be a cause for rejection. If dispute resolution is found relatively frequently in the business of the Bidder, it may indicate an attitude of the management of the firm that could be dangerous for the Employer if the Bidder were awarded the Contract, and further investigation with previous Employers may be warranted. 4. Year should usually be five (5) years prior to the Bid submission deadline. |  |  |  |  |  |  |  |

| Eligibility and Qualification Criteria |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor/ Sub-Factor | Requirement | Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.3 Financial Situation |  |  |  |  |  |  |  |
| ## 2.3.1 | ## Financial Performance | The audited balance sheets or if not required by the law of the Bidder’s country, other financial statements acceptable to the Employer, for the last [insert number of years]____ years1 shall be submitted and must demonstrate the current soundness of the Bidder’s financial position and its prospective long term profitability . As the minimum requirement, an Bidder’s net worth calculated as the difference between total assets and total liabilities should be positive2. | Must meet requirement | N/A | Must meet requirement | N/A | Form FIN - 1 with attachments |
| ## 2.3.2 | Average Annual Turnover | ### Minimum average annual turnover of [insert amount in USD]3__________________, calculated as total certified payments received for contracts in progress and/or completed, within the last [insert number of years] ______ years4 divided by [insert number of years] _______ years5. [insert requirements for multiple Contracts, if necessary]. | Must meet requirement | Must meet requirement | Must meet [insert percentage] ________ percent6 (_____%) of the requirement | Must meet [insert percentage] _________ percent7 (_____%) of the requirement | Form FIN - 2 |
| ## 2.3.3 | ## Financial Resources | (i) The Bidder shall demonstrate that it has access to, or has available, liquid assets, unencumbered real assets, lines of credit, and other financial means (independent of any contractual advance payment), sufficient to meet the cash flow requirements estimated as USD [insert amount in USD]8 for the subject contract(s) net of the Bidder’s other commitments. [insert requirements for multiple Contracts, if necessary] | Must meet requirement | Must meet requirement | Must meet [insert percentage] _________ percent 6 (_____%) of the requirement | Must meet [insert percentage] _________ percent7 (_____%) of the requirement | Form FIR - 1 |
|  |  | (ii) The Bidder shall also demonstrate, to the satisfaction of the Employer, that it has adequate sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments. [insert requirements for multiple Contracts, if necessary] | Must meet requirement | Must meet requirement | N/A | N/A | Form FIR – 1 and Form FIR - 2 |
| Notes for the Employer 1. Time period usually specified is five (5) years; it may be reduced to three (3) years minimum (in agreement with JICA) under special country circumstances, such as to provide opportunity for a newly privatized industry with limited period of existence, but with suitable experience, etc. Firms owned by individuals and partnerships may not be required to maintain audited balance sheets by the laws of their countries of origin; in such cases, the Employer may relax the audit requirement, but should request other acceptable financial statements. 2. The financial information provided by an Bidder should be reviewed in its entirety to allow a truly informed judgment, and the pass-fail decision on the financial position of the Applicant should be given on this basis. Any abnormal features which may lead to financial problems should alert the Employer to seek expert professional advice for further review and interpretation. 3. The amount stated should normally not be less than twice the estimated annual turnover in the proposed Contract (based on a straight-line projection of the Employer’s estimated cost, including contingencies, over the Contract duration). The multiplier of 2 may be reduced for very large Contracts but should not be less than 1.5. 4. The time period is normally five (5) years or more, but may be reduced to not less than three (3) years (in agreement with JICA) under special country circumstances, such as to provide opportunities for a newly privatized industry with only a short record of experience, etc. 5. Same number of years as in 4. above. 6. Usually not less than 25% of the requirement for each member of a JV. 7. Usually not less than 40% of the requirement for one member of a JV. 8. Indicate the cash flow requirement for a number of months, determined as the total time needed by the Employer to pay a Contractor’s invoice, allowing for (a) the actual time consumed for the works, from the beginning of the month invoiced, (b) the time needed by the Project Manager to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delays. The total period should not exceed six (6) months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular Contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated Contract cost. |  |  |  |  |  |  |  |

| Eligibility and Qualification Criteria |  |  | # Compliance Requirements |  |  |  | # Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor/ Sub-Factor | Requirement | - Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.4 Experience |  |  |  |  |  |  |  |
| ## 2.4.1 | ## General Experience | Experience under contracts in the role of prime contractor (single entity or JV member) Subcontractor, or management contractor(i) for at least the last [insert number of years]________ years1 starting 1st January [insert year]____. | Must meet requirement | N/A | Must meet requirement | N/A | Form EXP- 1 |
| 2.4.2 (a) | Specific Experience | A minimum number of [insert number of contracts]2 similar(ii) contracts that have been satisfactorily and substantially(iii) completed as a prime contractor (single entity or JV member)(iv) between 1st January [insert year]3and the Bid submission deadline. [insert requirements for multiple Contracts, if necessary] | Must meet requirement | Must meet requirements(v) | N/A | N/A | Form EXP - 2(a) |
| ## 2.4.2 (b) | ## Specific Experience | For the above or other contracts completed and under implementation as prime contractor (single entity or JV member), management contractor or Subcontractor(vi) between 1st January [insert year]4 and the Bid submission deadline, a minimum experience in the following key activities successfully completed [list activities, as applicable] [insert requirements for multiple Contracts, if necessary] (vii) | Must meet requirements (can be a specialist Subcontractor) | Must meet requirements (can be a specialist Subcontractor) | N/A | N/A | Form EXP - 2(b) |
| Notes for the Bidder (i) A management contractor is a firm which takes on the role of contract management as a “general” contractor of sort could do. It does not normally perform directly the work(s) associated with the Contract. Rather, it manages the work of other (sub) contractors while bearing full responsibility and risk for price, quality, and timely performance of the contract. (ii) The similarity shall be based on the physical size, complexity, methods/technology and/or other characteristics described in Section VI, Employer’s Requirements. Summation of number of small value contracts (less than the value specified under requirement) to meet the overall requirement will not be accepted. (iii) Substantial completion shall be based on 80% or more works completed under the Contract. (iv) For Contracts under which the Bidder participated as a JV member, only the Bidder’s share, by value, shall be considered to meet this requirement. (v) In case of a JV, the value of Contracts completed by its members shall not be aggregated to determine whether the requirement of the minimum value of a single Contract has been met. Instead, each Contract performed by each member shall satisfy the minimum value of a single Contract as required for single entity. In determining whether the JV meets the requirement of total number of Contracts, only the number of Contracts completed by all members each of value equal or more than the minimum value required shall be aggregated. (vi) For Contracts under which the Bidder participated as a JV member or Subcontractor, only the Bidder’s share shall be counted to meet this requirement. (vii) The minimum experience requirement for multiple Contracts will be the sum of the minimum requirements for respective individual Contracts. |  |  |  |  |  |  |  |
| Notes for the Employer - The time period is normally five (5) years or more, but may be reduced to not less than three (3) years (in agreement with JICA) under special country circumstances, such as to provide opportunities for a newly privatized industry with only a short record of experience. - The range of contract numbers should be one (1) to three (3), depending on the size, value, nature and complexity of the subject Contract, the exposure of the Employer to risk of Contractor default, country conditions and history of similar works constructed in the past. - The time range is normally five (5) years, and may be extended up to a period of ten (10) years for large-scale projects. - Same as that stipulated in 3 above. |  |  |  |  |  |  |  |

2.5	Subcontractors/Manufacturers

Subcontractors/manufacturers for the following major items of supply or services must meet the following minimum criteria, herein listed for that item:

| Item No. | Description of Item | Minimum Criteria to be met |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |

Failure to comply with this requirement will result in rejection of the Subcontractor.

In the case of a Bidder who offers to supply and install major items of supply under the Contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using Form MAN provided in Section IV, Bidding Forms, showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and install that item in the Employer’s country. The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and ITB 5 and meets the minimum criteria listed above for that item.

Second Stage Bids

1.	Evaluation

1.1	Economic Evaluation

[Any adjustments in price that result from the procedures outlined below shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.”  Bid Prices quoted by Bidders shall remain unaltered.]

    - Quantifiable nonmaterial nonconformities

[Pursuant to ITB 47.3 and ITB 50.3 (d), the cost of all quantifiable nonmaterial nonconformities or omissions (minor omissions or missing items) shall be evaluated. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of Bids.]

    - Other Factors

The following factors and methods will apply under ITB 50.3(f):

- Time Schedule:

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities is: [insert number of days] _____. No credit will be given for earlier completion.

[The completion time specified shall be for the entire Plant and Installation Services or for parts or sections of the plant and services.]

or

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining time for completion of pre-commissioning activities shall be between [insert number of days] ________ minimum and [insert number of days] ________ maximum.  The adjustment rate in the event of completion beyond the minimum period shall be [insert percentage in words and figures] _______ (%) for each week of delay from that minimum period. No credit will be given for completion earlier than the minimum designated period. Bids offering a completion date beyond the maximum designated period shall be rejected.

[One-fifth of a percent (0.2%) per week is a reasonable figure.  Alternatively, the rate may be a fixed amount per month, or pro rata per week, of delay related to the loss of benefits to the Employer.  The accepted period between the minimum and maximum time for completion should be such that the percentage or amount corresponding to the maximum period for completion should be less than or equal to the percentage or amount of liquidated damages specified in the PC in relation to GC Sub-Clause 26.2.]

- Operating and Maintenance Costs

Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given hereafter, including the cost of spare parts for the initial period of operation stated below and based on prices furnished by each Bidder in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other Employers similarly placed.  Such costs shall be added to the Bid Price for evaluation.

[Use one of the two options given below – delete the inapplicable option.]

Option 1: The operating and maintenance costs factors for calculation of the life cycle cost are:

(i)	number of years for life cycle [Insert life cycle period in years. The period should not exceed the period before a major overhaul of the facilities becomes necessary.] ______________________________________

(ii)	operating costs [Insert fuel and/or other input, unit cost for annual and total operational requirements.] ________________________________,

(iii)	maintenance costs, including the cost of spare parts for the initial period of operation, and

(iv)	a rate of [insert rate in words and figures] percent, to be used to discount to present value all annual future costs calculated under (ii) and (iii) above for the period specified in (i).

or

Option 2: Reference to the methodology specified in the Specification or   elsewhere in the Bidding Documents

[Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Documents.]

The price of recommended spare parts quoted in Price Schedule No. 7 shall not be considered for evaluation.

- Functional Guarantees of the Plant and Installation Services

The minimum (or maximum) requirements stated in the Specification for functional guarantees required in the Specification are:

| Functional Guarantee | Minimum (or Maximum, as appropriate) Requirement |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

For the purposes of evaluation, for each percentage point that the functional guarantee of the proposed Plant and Installation Services is below the norm specified in the Specifications and in the above table, but above the minimum acceptable levels also specified therein, an adjustment of [insert amount in the currency of Bid evaluation] ___________ will be added to the Bid Price. If the drop below the norm or the excess above the minimum acceptable levels is less than one percent, the adjustment will be prorated accordingly.

- Work, services, facilities, etc., to be provided by the Employer

Where Bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the Bidding Documents, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the Contract.  Such costs shall be added to the Bid Price for evaluation.

- Specific additional criteria

The following additional criteria will be used in the evaluation: [If applicable, insert a list of additional criteria which may also be included as amendments in the Invitation for Second Stage Bids.]

_______________________________________________________________________________

The relevant evaluation method shall be as follows: [Insert the evaluation method.]

__________________________________________________________________

    - Award Criteria for Multiple Contracts (ITB 50.5)

[Insert the following text in case of multiple contracts. Otherwise delete this EQC clause.

“Lots/Packages:

Bidders have the option to bid for any one or more lots/packages. Bids will be evaluated lot/package-wise, taking into account discounts offered, if any, for combined lots/packages. The Contract(s) will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer for combined lots/packages, subject to the selected Bidder(s) meeting the required qualification criteria for lot or combination of lots/packages as the case may be.”]

Section IV. Bidding Forms

## Notes on Bidding Forms The Employer shall include in the Bidding Documents all Bidding Forms that the Bidder shall fill out and include in its Bid. As specified in this section, these Forms are the Letter of Technical Bid, the Letter of Price Bid for Single-Stage Bidding, the Letter of First Stage Bid and the Letter of Second Stage Bid for Two-Stage Bidding, the Bid Security, Price Schedules, Technical Proposal Forms and the Bidder’s Qualification Information Forms.

Table of Forms

Single-Stage Bidding	3

Letter of Technical Bid	3

Letter of Price Bid	5

Two-Stage Bidding	7

Letter of First Stage Bid	7

Letter of Second Stage Bid	9

Price Schedules	11

Schedule No. 1.  Plant and Mandatory Spare Parts Supplied from Abroad	13

Schedule No. 2.  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country	14

Schedule No. 3.  Design Services	15

Schedule No. 4.  Installation and Other Services	16

Schedule No. 5.  Provisional Sums	17

Schedule No. 6. Grand Summary	18

Schedule No. 7.  Recommended Spare Parts	19

Price Adjustment	20

Technical Proposal	22

Site Organization	23

Method Statement	24

Mobilization Schedule	25

Construction Schedule	26

Plant	27

Safety Plan	28

Form FUNC: Functional Guarantee	29

Form PER -1: Proposed Personnel	30

Form PER -2: Resume of Proposed Personnel	31

Form EQU: Equipment	33

Form SUB: Proposed Subcontractors for Major Items of Plant and Installation Services	34

Form MAN: Manufacturer's Authorization	35

Others - Time Schedule	36

Others - Commercial or contractual aspects of the Bidding Documents that the Bidder would like to discuss with the Employer during clarifications	37

Bidder’s Qualification	38

Form ELI - 1: Bidder Information	40

Form ELI - 2: Bidder’s Party Information	41

Form CON: Historical Contract Non-Performance	42

Form FIN - 1: Financial Situation	45

Form FIN - 2: Average Annual Turnover	47

Form FIR - 1: Financial Resources	48

Form FIR - 2: Current Contract Commitments	49

Form EXP - 1: General Construction Experience	50

Form EXP - 2(a): Specific Experience	51

Form EXP - 2(b): Experience in Key Activities	53

Form ACK Acknowledgement of Compliance with the Guidelines for Procurement  under Japanese ODA Loans	55

Form of Bid Security (Bank Guarantee)	57

Form of Bid Security (Bid Bond)	59

Single-Stage Bidding

Letter of Technical Bid

Date: [insert date of Bid submission]

Loan Agreement No.: [insert number]

IFB No.: [insert number]

Alternative No.: [insert identification No. if this is a Bid for an alternative]

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB 8): [insert the number and issuing date of each Addendum];

- We, including any Subcontractors/ manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5;

- We, including any Subcontractors/ manufacturers, for any part of the Contract, have no conflict of interest in accordance with ITB 4;

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services];

- Our Bid shall be valid for a period of  [specify the number of calendar days] days from the date fixed for the Bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- We are not participating, as a Bidder or as a Subcontractor/ manufacturers, in more than one Bid in this bidding process in accordance with ITB 4.2 (c), other than alternative Bids submitted in accordance with ITB 13; and

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

- Name of the Bidder*[insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder** [insert complete name of person duly authorized to sign the Bid]

- Title of the person signing the Bid [insert complete title of the person signing the Bid]

Signature of the person named above [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

*: In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Single-Stage Bidding

Letter of Price Bid

Date: [insert date of Bid submission]

Loan Agreement No.: [insert number]

IFB No.: [insert number]

Alternative No.: [insert identification No. if this is a Bid for an alternative]

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB 8): [insert the number and issuing date of each Addendum];

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services];

- The total price of our Bid, excluding any discounts offered in item (d) below is:

In case of only one lot, total price of the Bid [insert the total price of the Bid in words and figures, indicating the various amounts and the respective currencies]

[In case of multiple lots, insert the total price of each lot]

[In case of multiple lots, insert the total price of all lots (sum of all lots)];

- The discounts offered and the methodology for their application are:

The discounts offered are: [specify in detail each discount offered]

The exact method of calculations to determine the net price after application of discounts is shown below: [specify in detail the method that shall be used to apply the discounts];

- Our Bid shall be valid for a period of [specify the number of calendar days] days from the date fixed for the Bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- If our Bid is accepted, we commit to obtain a Performance Security in accordance with the Bidding Documents;

- We understand that this Bid, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding Contract between us, until a formal Contract is prepared and executed; and

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- Name of the Bidder*[insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder** [insert complete name of person duly authorized to sign the Bid]

- Title of the person signing the Bid [insert complete title of the person signing the Bid]

Signature of the person named above [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

*: In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Two-Stage Bidding

Letter of First Stage Bid

Date: [insert date of Bid submission]

Loan Agreement No.: [insert number]

IFB No.: [insert number]

Alternative No.: [insert identification No. if this is a Bid for an alternative]

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB 8): [insert the number and issuing date of each Addendum];

- We, including any Subcontractors/ manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4;

- We, including any Subcontractors/ manufacturers, for any part of the Contract, have no conflict of interest in accordance with ITB 4;

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services];

- We are not participating, as a Bidder or as a Subcontractor/ manufacturers, in more than one Bid in this bidding process in accordance with ITB 4.2 (c), other than alternative Bids submitted in accordance with ITB 13;

- We further undertake, if invited to do so by you, and at our own cost, to attend a clarification meeting at a place of your choice, for the purpose of reviewing our First Stage Bid and duly noting all amendments and additions thereto, and noting omissions therefrom that you may require; and

- We further undertake, upon receiving your written invitation, to proceed with the preparation of our Second Stage Bid, updating our First Stage Bid in accordance with the requirements from the Memorandum of the clarification meeting, and completing our Second Stage Bid for supplying the Plant and Installation Services.

- Name of the Bidder*[insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder** [insert complete name of person duly authorized to sign the Bid]

- Title of the person signing the Bid [insert complete title of the person signing the Bid]

Signature of the person named above [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

*: In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Two-Stage Bidding

Letter of Second Stage Bid

Date: [insert date of Bid submission]

Loan Agreement No.: [insert number]

IFB No.: [insert number]

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB 8): [insert the number and issuing date of each Addendum], and your requirements incorporated in the Memorandum of the clarification meeting held between us on [insert date], 	 and amendments issued in accordance with ITB 30.1 (a): [insert the number and issuing date of each amendments, if any];

- We, including any Subcontractors/ manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5;

- We, including any Subcontractors/ manufacturers, for any part of the Contract, have no conflict of interest in accordance with ITB 4;

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the Memorandum and the amendments of the Bidding Documents pursuant First Stage Evaluation, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services];

- The price of our Bid, excluding any discounts offered in item (d) below is:

In case of only one lot, total price of the Bid [insert the total price of the Bid in words and figures, indicating the various amounts and the respective currencies]

[In case of multiple lots, insert the total price of each lot]

[In case of multiple lots, insert the total price of all lots (sum of all lots)];

- The discounts offered and the methodology for their application are:

The discounts offered are: [specify in detail each discount offered]

The exact method of calculations to determine the net price after application of discounts is shown below: [specify in detail the method that shall be used to apply the discounts];

- Our Bid shall be valid for a period of  [specify the number of calendar days] days from the date fixed for the submission deadline for the Second Stage Bids as stipulated in the Letter of Invitation for Second Stage Bids, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- If our Bid is accepted, we commit to obtain a Performance Security in accordance with the Bidding Documents;

- We are not participating, as a Bidder or as a Subcontractor/ manufacturers, in more than one Bid in this bidding process in accordance with ITB 4.2 (c);

- We understand that this Bid, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding Contract between us, until a formal Contract is prepared and executed; and

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

- Name of the Bidder*[insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder** [insert complete name of person duly authorized to sign the Bid]

- Title of the person signing the Bid [insert complete title of the person signing the Bid]

Signature of the person named above [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

*: In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Price Schedules

Notes on Prices Schedules General 1. The Price Schedules are divided into separate Schedules as follows: Schedule No. 1: Plant (including Mandatory Spare Parts) Supplied from Abroad Schedule No. 2: Plant (including Mandatory Spare Parts) Supplied from Within the Employer’s Country Schedule No. 3: Design Services Schedule No. 4: Installation and Other Services Schedule No. 5: Provisional Sums Schedule No. 6: Grand Summary Schedule No. 7: Recommended Spare Parts (Spare parts for Operation and Maintenance) 2. The Schedules do not generally give a full description of the Plant to be supplied and the services to be performed under each item. Bidders shall be deemed to have read the Employer’s Requirements and other sections of the Bidding Documents and reviewed the Drawings to ascertain the full scope of the requirements included in each item prior to filling in the rates and prices. The entered rates and prices shall be deemed to cover the full scope as aforesaid, including overheads and profit. 3. If Bidders are unclear or uncertain as to the scope of any item, they shall seek clarification in accordance with ITB 7 prior to submitting their Bid. Pricing 4. Prices shall be filled in indelible ink, and any alterations necessary due to errors, etc., shall be initialed by the Bidder. As specified in the Bid Data Sheet and Particular Conditions of Contract, prices shall be fixed and firm for the duration of the Contract, or prices shall be subject to adjustment in accordance with the corresponding Appendix (Price Adjustment) to the Contract Agreement. 5. Bid Prices shall be quoted in the manner indicated and in the currencies specified in the Instructions to Bidders in the Bidding Documents. For each item, Bidders shall complete each appropriate column in the respective Schedules, giving the price breakdown as indicated in the Schedules. Prices given in the Schedules against each item shall be for the scope covered by that item as detailed in Section VI (Employer’s Requirements) or elsewhere in the Bidding Documents. 6. Payments will be made to the Contractor in the currency or currencies indicated under each respective item. 7. When requested by the Employer for the purposes of making payments or partial payments, valuing variations or evaluating claims, or for such other purposes as the Employer may reasonably require, the Contractor shall provide the Employer with a breakdown of any composite or lump sum items included in the Schedules.

Schedules of Rates and Prices

Schedule No. 1.  Plant and Mandatory Spare Parts Supplied from Abroad

| Item | Description | Code1 | Qty. | Unit Price2 |  | Total Price2 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | CIP |  |
|  |  |  | (1) | (2) | (3) | (1) x (3) |
| TOTAL (to Schedule No. 6. Grand Summary) |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |
| 1 Bidders shall enter a code representing the country of origin of all imported plant and equipment. 2 Specify currency in accordance with specifications in Bid Data Sheet under ITB 19.1 in Single-Stage Bid, or ITB 34.1 in Two-Stage Bid. Create and use as many columns for Unit Price and Total Price as there are currencies. |  |  |  |  |  |  |

Country of Origin Declaration Form

| Item | Description | Code | Country |
| --- | --- | --- | --- |

Schedule No. 2.  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country

| Item | Description |  |  | Qty. |  | Unit Price1 |  | Total Price1 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (1) |  | (2) |  | (1) x (2) |  |
| TOTAL (to Schedule No. 6. Grand Summary) |  |  |  |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 19.1 in Single-Stage Bid, or ITB 34.1 in Two-Stage Bid. |  |  |  |  |  |  |  |  |  |

Schedule No. 3.  Design Services

| Item | Description |  | Qty. | Unit Price1 |  |  |  | Total Price1 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Foreign Currency Portion |  | Local Currency Portion |  | Foreign |  | Local |
|  |  |  | (1) | (2) |  | (3) |  | (1) x (2) |  | (1) x (3) |
| TOTAL (to Schedule No. 6. Grand Summary) |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Name of Bidder |  |  |  |  |  |  |
|  |  |  |  | Signature of Bidder |  |  |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 19.1 in Single-Stage Bid, or ITB 34.1 in Two-Stage Bid. |  |  |  |  |  |  |  |  |  |  |

Schedule No. 4.  Installation and Other Services

| Item | Description | Qty. | Unit Price1 |  |  | Total Price1 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Foreign Currency Portion |  | Local Currency Portion | Foreign |  | Local |
|  |  | (1) | (2) |  | (3) | (1) x (2) |  | (1) x (3) |
| TOTAL (to Schedule No. 6. Grand Summary) |  |  |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 19.1 in Single-Stage Bid, or ITB 34.1 in Two-Stage Bid. |  |  |  |  |  |  |  |  |

Schedule No. 5.  Provisional Sums

| Item | Description |  | Amount |  |
| --- | --- | --- | --- | --- |
|  |  |  | Local | Foreign |
| Cost of Dispute Board1 |  |  |  |  |
| TOTAL (to Schedule No. 6. Grand Summary ) |  |  |  |  |
|  |  | Name of Bidder | ____________________ |  |
|  |  | Signature of Bidder | ____________________ |  |
| 1 One-half of the Employer’s cost estimate of the Dispute Board shall be included in the Provisional Sums. Contractor’s overhead and profits shall not be included in this amount. |  |  |  |  |

Schedule No. 6. Grand Summary

| Item | Description |  |  |  | Total Price1 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Foreign | Local |  |
|  | Total Schedule No. 1. Plant, and Mandatory Spare Parts Supplied from Abroad |  |  |  |  |  |  |
|  | Total Schedule No. 2. Plant, and Mandatory Spare Parts Supplied from Within the Employer’s Country |  |  |  |  |  |  |
|  | Total Schedule No. 3. Design Services |  |  |  |  |  |  |
|  | Total Schedule No. 4. Installation and Other Services |  |  |  |  |  |  |
|  | Total Schedule No. 5. Provisional Sums |  |  |  |  |  |  |
| TOTAL (to Bid Form) |  |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |  |
|  |  | Signature of Bidder |  |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 19.1 in Single-Stage Bidding, or ITB 34.1 in Two-Stage Bidding. Create and use as many columns for Foreign Currency requirement as there are foreign currencies. |  |  |  |  |  |  |  |

Schedule No. 7.  Recommended Spare Parts

| Item | Description |  | Qty. | Unit Price |  |  | Total Price |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | CIF or CIP (foreign parts) |  | EXW (local parts) |  |  |
|  |  |  | (1) | (2) |  | (3) | (1) x (2) or(3) |  |
|  |  |  | Name of Bidder |  |  |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |  |  |

Price Adjustment

Where the Contract Period (excluding the Defects Liability Period) exceeds eighteen (18) months, it is normal procedure that prices payable to the Contractor shall be subject to adjustment during the performance of the Contract to reflect changes occurring in the cost of labor and material components. In such cases the Bidding Documents shall include in this form a formula of the following general type, pursuant to GC Sub-Clause 11.2. Where Contracts are of a shorter duration than eighteen (18) months, the following provision shall not be included. Instead, it shall be indicated under this form that the prices are to remain firm and fixed for the duration of the Contract.

Sample Price Adjustment Formula

Prices payable to the Contractor, in accordance with the Contract, shall be subject to adjustment during performance of the Contract to reflect changes in the cost of labor and material components, in accordance with the following formula:

P1=P0´(a+bL1L0+cM1M0)−P0

in which:

P1	=	adjustment amount payable to the Contractor

P0	=	Contract Price (base price)

a	=	percentage of fixed element in Contract Price (a =   %)

b	=	percentage of labor component in Contract Price (b =  %)

c	=	percentage of material and equipment component in Contract Price (c =  %)

L0, M0  =  labor and material/equipment component indices or reference prices in the country of origin on the Base Date

L1, M1	=	labor and material/equipment component indices applicable to the appropriate industry in the country of origin on the date of adjustment, for adjustments related to Plant and components supplied under Schedules No.1, No.2 and No.3; and, in case of adjustment for Installation Services provided under Schedule No.4, indices or reference prices applicable to the appropriate industry in the country of origin on the month the Installation Services were provided.

N.B.  a+b+c= 100%.

[The Bidder shall propose the coefficients b and c in its Bid. The formula, including all coefficients, shall be determined and finalized at Contract negotiations.]

Conditions Applicable To Price Adjustment

The Bidder shall indicate the source of labor and materials indices and the base date indices in its Bid.

| Item | Source of Indices Used | Base Date Indices |
| --- | --- | --- |

The Base Date shall be the date twenty eight (28) days prior to: [insert “the Bid submission deadline” or “the submission deadline for Second Stage Bids”, as appropriate].

For Plant or components supplied under Schedules No.1, No.2 and No.3, the date of adjustment shall be the mid-point of the sequences shown in the Program of Performance submitted by the Bidder, pursuant to GC 18.2, for design or manufacture of the Plant or components.

In respect of Installation Services provided under Schedule No.4, the adjustment shall apply to the monthly measured value of work performed by the Contractor during the preceding month. The adjustment shall be made monthly to the payments for Installation Services effected as provided in Appendix 1 of the Contract Agreement.

The following conditions shall apply:

(a)	No price increase will be allowed beyond the original delivery date unless covered by an extension of time awarded by the Employer under the terms of the Contract.  No price increase will be allowed for periods of delay for which the Contractor is responsible.  The Employer will, however, be entitled to any price decrease occurring during such periods of delay.

(b)	If the currency in which the Contract Price, P0, is expressed is different from the currency of the country of origin of the labor and/or materials indices, a correction factor will be applied to avoid incorrect adjustments of the Contract Price.  The correction factor shall correspond to the ratio of exchange rates between the two currencies on the base date and the date for adjustment as defined above.

(c)	No price adjustment shall be payable on the portion of the Contract Price paid to the Contractor as an advance payment.

[For complex Plant and Installation Services involving several sources of supply and/or a substantial amount of installation works, a family of formulas may be necessary, with provision for the usage of Contractor’s equipment in the works formula.]

Technical Proposal

- Site Organization

- Method Statement

- Mobilization Schedule

- Construction Schedule

- Plant

- Safety Plan

- Functional Guarantee

- Personnel

- Contractor’s Equipment

- Proposed Subcontractors for Major Items of Plant and Installation Services

- [Others]

Site Organization

[Insert Technical Proposal for Site Organization.]

Method Statement

[Insert Technical Proposal for Method Statement.]

Mobilization Schedule

[Insert Technical Proposal for Mobilization Schedule.]

Construction Schedule

[Insert Technical Proposal for Construction Schedule.]

Plant

[Insert Technical Proposal for Plant.]

Safety Plan

[Insert Technical Proposal for Safety Plan.]

Form FUNC: Functional Guarantee

[The Bidder shall copy in the left column of the table below, the identification of each functional guarantee required in the Specification and stated by the Employer in para. 1.2.2 (c) of Section III. Evaluation and Qualification Criteria for Single-Stage Bidding, or in para. 1.1.2 (c) of Section III. Evaluation and Qualification Criteria for Two-Stage Bidding, Second Stage Evaluation, and in the right column, provide the corresponding value for each functional guarantee of the proposed plant and equipment.]

| Required Functional Guarantee | Value of Functional Guarantee of the Proposed Plant and Equipment |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

Form PER -1: Proposed Personnel

Date: [insert day, month, year]

Bidder’s Legal Name: [insert full name]

Joint Venture Party Legal Name: [insert full name]

IFB No.: [insert number]

Page [insert page number] of [insert total number] pages

[The Bidder shall provide the names of suitably qualified personnel to meet the specified requirements stated in Section III, Evaluation and Qualification Criteria, Clause 1.1.1 for Single-Stage Bidding or Clause 1.1 for Two-Stage Bidding.]

| 1. | Title of position* |
| --- | --- |
|  | Name |
| 2. | Title of position* |
|  | Name |
| 3. | Title of position* |
|  | Name |
| 4. | Title of position* |
|  | Name |

*As listed in Section III.

Form PER -2: Resume of Proposed Personnel

Date: [insert day, month, year]

Bidder’s Legal Name: [insert full name]

Joint Venture Party Legal Name: [insert full name]

IFB No.: [insert number]

Page [insert page number] of [insert total number] pages

[The Bidder shall provide the data on the experience of the personnel indicated in Form PER-1, in the form below.]

Name of Bidder

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

[Summarize professional experience over the last 20 years, in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.]

| From | To | Company / Project / Position / Relevant technical and management experience |
| --- | --- | --- |

Form EQU: Equipment

Date: [insert day, month, year]

Bidder’s Legal Name: [insert full name]

Joint Venture Party Legal Name: [insert full name]

IFB No.: [insert number]

Page [insert page number] of [insert total number] pages

[The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III, Evaluation and Qualification Criteria, Clause 1.1.2 for Single-Stage Bidding or Clause 1.2 for Two-Stage Bidding. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.]

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment  Owned  Rented  Leased  Specially manufactured |  |

- Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

Form SUB: Proposed Subcontractors for Major Items of Plant and Installation Services

A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or manufacturers are proposed for carrying out the item of the facilities indicated.  Bidders are free to propose more than one for each item.

| Major Items of Plant and Installation Services | Proposed Subcontractors/Manufacturers | Nationality |
| --- | --- | --- |

Form MAN: Manufacturer's Authorization

[The Bidder shall require the Manufacturer to fill in this Form in accordance with the instructions indicated. This letter of authorization should be signed by a person with the proper authority to sign documents that are binding on the Manufacturer.]

Date: [insert date (as day, month and year) of Bid Submission]

IFB No.: [insert number of bidding process]

To:  [insert complete name of Purchaser]

WHEREAS

We [insert complete name of Manufacturer or Manufacturer’s authorized agent], who are official manufacturers of [insert type of goods manufactured], having factories at [insert full address of Manufacturer’s factories], do hereby authorize [insert complete name of Bidder] to submit a Bid the purpose of which is to provide the following goods, manufactured by us [insert name and/or brief description of the goods], and to subsequently negotiate and sign the Contract.

We hereby extend our full guarantee and warranty in accordance with Clause 27, Defect Liability, of the General Conditions of Contract, with respect to the goods offered by the above firm.

Name: [insert complete name of person signing the Bid]

In the capacity of [insert legal capacity of person signing the bid]

Signed: [insert signature of person whose name and capacity are shown above]

Duly authorized to sign the bid for and on behalf of: [insert complete name of Bidder]

Dated on ____________ day of __________________, _______ [insert date of signing]

Others - Time Schedule

[To be used by Bidders when alternative Time for Completion is invited or proposed.]

Others - Commercial or contractual aspects of the Bidding Documents that the Bidder would like to discuss with the Employer during clarifications

[To be used by Bidders - Two Stage Bidding only.]

Bidder’s Qualification

[When preparing the Bidding Documents, the Employer shall choose one of the options below, selecting the relevant Forms and including them in the Bidding Documents, depending on whether prequalification was carried out prior to bidding, or whether Bidder’s qualification will be assessed at the bidding stage.]

[Option 1: Bidder’s Qualification following Prequalification]

1. Update of Information

In accordance with Section III, Evaluation and Qualification Criteria, Clause 2.1, the Bidder shall update the information given during the corresponding prequalification exercise to demonstrate that he continues to meet the criteria used at the time of prequalification using the following forms included hereunder:

(a)	Eligibility

Form ELI - 1: Bidder Information

Form ELI - 2: Bidder’s Party Information

(b)	Historical Contract Non-Performance

Form CON: Historical Contract Non-Performance

(c)	Financial Situation

Form FIN - 1: Financial Situation

Form FIN - 2: Average Annual Turnover

2. Financial Resources

Bidders shall also provide information on their financial resources, to meet the requirement in Section III, Evaluation and Qualification Criteria, Clause 2.2, using the following forms:

Form FIR - 1: Financial Resources

Form FIR - 2: Current Contract Commitments

[Option 2: Bidder’s Qualification without Prequalification]

To establish its qualification to perform the Contract in accordance with Section III, Evaluation and Qualification Criteria, the Bidder shall provide the information requested in the corresponding Information Sheets included hereunder:

| - Form ELI - 1: | Bidder Information |
| --- | --- |
| - Form ELI - 2: | Bidder’s Party Information |
| - Form CON: | Historical Contract Non-Performance |
| - Form FIN - 1: | Financial Situation |
| - Form FIN - 2: | Average Annual Construction Turnover |
| - Form FIR - 1: | Financial Resources |
| - Form FIR - 2: | Current Contract Commitments |
| - Form EXP - 1: | General Construction Experience |
| - Form EXP - 2(a): | Specific Construction Experience |
| - Form EXP - 2(b): | Construction Experience in Key Activities |

Form ELI - 1: Bidder Information

Date: [insert day, month, year]

IFB No.: [insert number]

Page [insert page number] of [insert total number] pages

[The Bidder shall provide the following information.]

1. Bidder’s legal name:[insert full name]

2. In case of JV, legal name of the representative member and of each member: [insert full name of each member in the JV and specify the representative member]

3. Bidder’s actual or intended country of registration: [insert country of registration]

4. Bidder’s actual or intended year of incorporation: [insert year of incorporation]

5. Bidder’s legal address in country of registration: [insert street/number/town or city/country]

6. Bidder’s authorized representative information Name: [insert full name] Address: [inset street/number/town or city/country] Telephone/Fax numbers: [insert telephone/fax numbers, including country and city codes] Email Address: [insert E-mail address]

7. Attached are copies of original documents of:  Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of legal entity named above, in accordance with ITB 4.3.  In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB 4.1. 8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form ELI - 2: Bidder’s Party Information

Date: [insert day, month, year]

IFB No.: [insert number]

Page [insert page number] of [insert total number] pages

[The following form is additional to Form ELI-1, and shall be completed to provide information relating to each JV member (in case the Bidder is a JV) as well as any specialist Subcontractor proposed to be used by the Bidder for any part of the Contract resulting from this process.]

1. Bidder’s legal name: [insert full name]

2. Bidder's Party legal name: [insert full name of Bidder’s Party]

3. Bidder's Party country of registration: [insert country of registration]

4. Bidder’s Party year of incorporation: [insert year of incorporation]

5. Bidder’s Party legal address in country of registration: [insert street/number/town or city/country]

6. Bidder’s Party authorized representative information Name: [insert full name] Address: [insert street/number/town or city/country] Telephone/Fax numbers: [insert telephone/fax numbers, including country and city codes] E-mail address: [insert E-mail address]

7. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above, in accordance with ITB 4.3. 8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form CON: Historical Contract Non-Performance

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

1. History of Non-Performing Contracts

| Non-Performing Contracts |  |  |  |
| --- | --- | --- | --- |
|  Contract non-performance did not occur since 1st January [insert year], in accordance with the Prequalification criteria, or Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.1, as appropriate.  Contract(s) not performed since 1st January [insert year], in accordance with the Prequalification criteria, or Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.1, as appropriate, is(are) indicated below: |  |  |  |
| Year | Non- performed portion of Contract | Contract Identification | Total Contract Amount (current value, currency, exchange rate and USD equivalent) |
| [insert year] | [insert amount and percentage] | - Contract Identification: [indicate complete Contract name, number, and any other identification] - Name of Employer: [insert full name] - Address of Employer: [insert street/city/country] - Reason(s) for non performance: [indicate main reason(s)] | [insert amount] |

2. Pending Litigation

| Pending Litigation |  |  |  |  |
| --- | --- | --- | --- | --- |
|  No pending litigation in accordance with the Prequalification criteria, or Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.2, as appropriate. |  |  |  |  |
|  Pending litigation in accordance with the Prequalification criteria, or Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.2, as appropriate, is indicated below: |  |  |  |  |
| Year of dispute | Amount in dispute (currency) | Outcome as Percentage of Net Worth | Contract Identification | Total Contract Amount (current value, currency, exchange rate and USD equivalent) |
| [insert year] | [insert amount] | [insert percentage] | - Contract Identification: [indicate complete Contract name, number, and any other identification] - Name of Employer: [insert full name] - Address of Employer: [insert street/ city/ country] - Matter in dispute: [indicate main issues in dispute] - Status of dispute: [indicate if it is being treated by the Adjudicator, under Arbitration or being dealt with by the Judiciary] | [insert amount] |

3. Litigation History

| Litigation History |  |  |
| --- | --- | --- |
|  No court/arbitral award decisions against the Bidder since 1st January [insert year], in accordance with the Prequalification criteria, or Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.3, as appropriate. |  |  |
|  Court/arbitral award decisions against the Bidder since 1st January [insert year], in accordance with the Prequalification criteria, or Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.3, as appropriate, are indicated below: |  |  |
| Year of award | Contract Identification | Total Contract Amount (current value, currency, exchange rate and USD equivalent) |
| [insert year] | - Contract Identification: [indicate complete Contract name, number, and any other identification - Name of Employer: [insert full name] - Address of Employer: [insert street/city/country] - Matter in dispute: [indicate main issues in dispute] - Party who initiated the dispute: [indicate “Employer” or “Contractor”] - Status of dispute: [indicate if it is being treated by the Adjudicator, under Arbitration or being dealt with by the Judiciary] | [insert amount] |

Form FIN - 1: Financial Situation

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

1. Financial data

| Type of Financial information in (currency) | Historic information for previous [insert number] years (amount, currency, exchange rate, USD equivalent) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| Statement of Financial Position (Information from Balance Sheet) |  |  |  |  |  |
| Total Assets (TA) |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |
| Information from Income Statement |  |  |  |  |  |
| Total Revenue (TR) |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |
| Profits After Taxes (PAT) |  |  |  |  |  |

2. Financial documents

The Bidder and its Parties shall provide copies of the financial statements for [number of years] years pursuant to the Prequalification Criteria or Section III, Evaluation and Qualifications Criteria, Sub-factor 2.3.1. The financial statements shall:

(a) 	reflect the financial situation of the Bidder or in case of JV member, of each member, and not an affiliated entity  (such as parent company or group member).

(b)	be independently audited or certified in accordance with local legislation.

(c)	be complete, including all notes to the financial statements.

(d)	correspond to accounting periods already completed and audited.

	Attached are copies of financial statements for the [number of years] years required above; and complying with the requirements.

Form FIN - 2: Average Annual Turnover

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

| Annual Turnover Data (Construction only) |  |  |  |
| --- | --- | --- | --- |
| Year | Amount and Currency | Exchange rate | USD equivalent |
| [indicate year] | [insert amount and indicate currency] | [insert applicable exchange rate] | [insert amount in USD equivalent] |
| Average Annual Construction Turnover * |  |  |  |

* Total USD equivalent for all years divided by the total number of years, in accordance with the Prequalification criteria, or Section III, Evaluation and Qualification Criteria, Sub-Factor 2.3.2, as appropriate.

Form FIR - 1: Financial Resources

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

[Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject Contract or Contracts as indicated in Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2 (Following Prequalification), or Sub-Factor 2.3.3 (Without Prequalification), as appropriate.]

| Financial Resources |  |  |
| --- | --- | --- |
| No. | Source of financing | Amount (USD equivalent) |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |

Form FIR - 2: Current Contract Commitments

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

[Bidders and each member of a JV should provide information on their current commitments on all Contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for Contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued, in accordance with Section III, Evaluation and Qualification Criteria, Clause 2.2 (Following Prequalification), or Sub-Factor 2.3.3 (Without Prequalification), as appropriate.]

| Current Contract Commitments |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Name of Contract | Employer’s Contact Address, Tel, Fax | Value of Outstanding Work [Current USD Equivalent] | Estimated Completion Date | Average Monthly Invoicing Over Last Six Months [USD/month)] |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |

Form EXP - 1: General Experience

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

[Identify Contracts that demonstrate continuous work over the past [number] years pursuant to Section III, Evaluation and Qualification Criteria, Sub-Factor 2.4.1. List Contracts chronologically, according to their commencement (starting) dates.]

| General Experience |  |  |  |
| --- | --- | --- | --- |
| Starting Year | Ending Year | Contract Identification | Role of Bidder |
| [indicate year] | [indicate year] | - Contract name: [insert full name] - Brief description of the works performed by the Bidder: [describe works performed briefly] - Amount of Contract: [insert amount, currency, exchange rate and USD equivalent] - Name of Employer: [indicate full name] - Address: [indicate street/number/town or city/country] | [insert "Prime Contractor”(Single entity or JV member) or "Subcontractor” or "Management Contractor”] |

Form EXP - 2(a): Specific Experience

[The following table shall be filled in for Contracts performed by the Bidder and by each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

[Fill out one (1) form per Contract, in accordance with Section III, Evaluation and Qualification Criteria (Without Prequalification), Sub-Factor 2.4.2(a).]

| Similar Contract No. [insert number] of [insert number of similar Contracts required] | Information |  |  |
| --- | --- | --- | --- |
| Contract Identification | [insert Contract name and reference identification number, if applicable] |  |  |
| Award date | [insert day, month, year, e.g., 15 June, 2015] |  |  |
| Completion date | [insert day, month, year, e.g., 03 October, 2017] |  |  |
| Role in Contract | Prime Contractor Only |  |  |
| Total Contract Amount | [insert Contract amount(s) and currency(ies)] |  | USD [insert exchange rate and total Contract amount in USD equivalent] |
| If member in a JV, specify participation in total Contract amount | [insert percentage of participation] | [insert amount(s) and currency(ies) of participation] | USD [insert exchange rate and amount of participation in USD equivalent] |
| Employer's Name | [insert full name] |  |  |
| Address Telephone/fax number E-mail | [indicate street/number/town or city/country] [insert telephone/fax numbers, including country and city area codes] [insert E-mail address, if available] |  |  |

| Similar Contract No. [insert number of similar Contracts required] | Information |
| --- | --- |
| Description of the similarity in accordance with Sub-Factor 2.4.2(a) of Section III: |  |
| 1. Physical size of required works items | [insert physical size of items] |
| 2. Complexity | [insert description of complexity] |
| 3. Methods/Technology | [insert specific aspects of the methods/technology involved in the Contract] |
| 4. Other Characteristics | [insert other characteristics as described in Section VI, Employer’s Requirements] |

Form EXP - 2(b): Experience in Key Activities

[The following table shall be filled in for Contracts performed by the Bidder and by each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name: [insert full name]

Subcontractor’s Legal Name: [insert full name]
IFB No.: [insert number]

Page [insert page number] of [insert total number] pages

[Fill out one (1) form per Contract, in accordance with Section III, Evaluation and Qualification Criteria (Without Prequalification), Sub-Factor 2.4.2(b).]

1.	Key Activity No. (1): [insert brief description of the Activity, emphasizing its specificity]

Total Quantity of Activity under the Contract: _____________________________________

| Contract with Similar Key Activities Information |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item | Information |  |  |  |  |  |
| Contract Identification | [insert Contract name and number, if applicable] |  |  |  |  |  |
| Award date | [insert day, month, year, e.g., 15 June, 2015] |  |  |  |  |  |
| Completion date | [insert day, month, year, e.g., 03 October, 2017] |  |  |  |  |  |
| Role in Contract [check the appropriate box] | Prime Contractor |  |  | Management Contractor  |  | Sub-contractor  |
|  | Single  | JV member  |  |  |  |  |
| Total Contract Amount | [insert Contract amount(s) and currency(ies)] |  |  | USD [insert Exchange rate and total Contract amount in USD equivalent] |  |  |
| Quantity (as applicable) performed under the Contract per year or part of the year [insert extent of participation indicating actual quantity of key activity successfully completed in the role performed] | Total quantity in the Contract (i) |  | Percentage participation (ii) |  | Actual Quantity Performed (i) x (ii) |  |
| Year 1 |  |  |  |  |  |  |
| Year 2 |  |  |  |  |  |  |
| Year 3 |  |  |  |  |  |  |
| Year 4 |  |  |  |  |  |  |
| Employer’s Name | [insert full name] |  |  |  |  |  |
| Address Telephone/fax number E-mail | [indicate street / number / town or city / country] [insert telephone/fax numbers, including country and city area codes] [insert E-mail address, if available] |  |  |  |  |  |

2.  Activity No. (2) _____

3.  Activity No. (3) _____

Form ACK
Acknowledgement of Compliance with the Guidelines for Procurement 
under Japanese ODA Loans

A) I, [insert name and position of authorized signatory], being duly authorized by [insert name of Bidder/members of joint venture (“JV”)] (hereinafter referred to as the “Bidder”) to execute this Acknowledgement of Compliance with Guidelines for Procurement under Japanese ODA Loans, hereby certify on behalf of the Bidder and myself that all information provided in the Bid submitted by the Bidder for [insert Loan No and name of the Project] is true, correct and accurate to the best of the Bidder’s and my knowledge and belief.  I further certify, on behalf of the Bidder, that:

    - the Bid has been prepared and submitted in full compliance with the terms and conditions set forth in the Guidelines for Procurement under Japanese ODA Loans (hereinafter referred to as the “Guidelines”); and

    - the Bidder has not, directly or indirectly, taken any action which is or constitutes a corrupt, fraudulent, collusive or coercive act or practice in violation of the Guidelines and is not subject to any conflict of interest as stipulated in the relevant section of the Guidelines.

<If debarment for more than one year by the World Bank Group is NOT imposed, use the following sentence B).>

B)	I certify that the Bidder has NOT been debarred by the World Bank Group for more than one year since the date of issuance of Invitation for Bids.

<If debarment for more than one year by the World Bank Group has been imposed BUT three (3) years have passed since the date of such debarment decision, use the following sentence B’).>

B’)	I certify that the Bidder has been debarred by the World Bank Group for a period more than one year BUT that on the date of issuance of Invitation for Bids at least three (3) years had passed since the date of such debarment decision.  Details of the debarment are as follows:

| name of the debarred firm | starting date of debarment | ending date of debarment | reason for debarment |
| --- | --- | --- | --- |

- I certify that the Bidder will not enter into a subcontract with a firm which has been debarred by the World Bank Group for a period more than one year, unless on the date of the subcontract at least three (3) years have passed since the date of such debarment decision.

- I certify, on behalf of the Bidder, that if selected to undertake services in connection with the Contract, the Bidder shall carry out such services in continuing compliance with the terms and conditions of the Guidelines.

- I further certify, on behalf of the Bidder, that if the Bidder is requested, directly or indirectly, to engage in any corrupt or fraudulent action under any applicable law, such as the payment of a rebate, at any time during a process of public procurement,  negotiations, execution or implementation of contract (including amendment thereof), the Bidder shall report all relevant facts regarding such request to the relevant section in JICA (details of which are specified below) in a timely manner.

JICA’s information desk on fraud and corruption (A report can be made to either of the offices identified below.)

(1)  JICA Headquarters: Legal Affairs Division, General Affairs Department

URL: https://www2.jica.go.jp/en/odainfo/index.php

Tel: +81 (0)3 5226 8850

(2) JICA XX office

Tel:

The Bidder acknowledges and agrees that the reporting obligation stated above shall NOT in any way affect the Bidder’s responsibilities, obligations or rights, under relevant laws, regulations, contracts, guidelines or otherwise, to disclose or report such request or other information to any other person(s) or to take any other action, required to or allowed to, be taken by the Bidder. The Bidder further acknowledges and agrees that JICA is not involved in or responsible for the procurement process in any way.

- If any of the statements made herein  is subsequently proven to be untrue or incorrect based on facts subsequently determined, or if any of the warranties or covenants made herein is not complied with, the Bidder will accept, comply with, and not object to any remedies taken by the Employer  and any sanctions imposed by or actions taken by JICA.

_____________________________ Authorized Signatory

[Insert name of signatory; title]

For and on behalf of [Insert name of the Bidder]

Date:

Form of Bid Security (Bank Guarantee)

[Guarantor letterhead or SWIFT identifier code]

Beneficiary:  [Employer to insert its name and address]

IFB No.: [Employer to insert number of Invitation for Bids]

Date: [insert date of issue]

BID GUARANTEE No.: [insert guarantee reference number]

Guarantor: [insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of the Bidder, which in the case of a joint venture shall be the name of the joint venture (whether legally constituted or prospective) or the names of all members thereof] (hereinafter called “the Applicant”) has submitted or will submit to the Beneficiary its Bid (hereinafter called “the Bid”) for the execution of [insert description of Contract] under Loan Agreement No. [insert Loan Agreement Number].

Furthermore, we understand that, according to the Beneficiary’s conditions, Bids must be supported by a bid guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in words, (insert amount in figures)]  upon receipt by us of the Beneficiary’s complying demand, supported by the Beneficiary’s statement, whether in the demand itself or a separate signed document accompanying or identifying the demand, stating that either the Applicant:

(a) 	has withdrawn its Bid during the period of Bid validity set forth in the Applicant’s Letter of Bid (hereinafter called “the Bid Validity Period”), or any extension thereto provided by the Applicant; or

(b) 	having been notified of the acceptance of its Bid by the Beneficiary during the Bid Validity Period or any extension thereto provided by the Applicant,  (i) fails to execute the Contract Agreement, or (ii) fails to furnish the Performance Security, in accordance with the Instructions to Bidders of the Beneficiary’s Bidding Documents.

This guarantee will expire and shall be returned to the Applicant: (a) if the Applicant is the successful Bidder, upon our receipt of copies of the Contract Agreement signed by the Applicant and the Performance Security issued to the Beneficiary in relation to such Contract Agreement; or (b) if the Applicant is not the successful Bidder, upon the earlier of (i) our receipt of a copy of the Beneficiary’s notification to the Applicant of the results of the bidding process; or (ii) twenty-eight (28) days after the end of the Bid Validity Period.

Consequently, any demand for payment under this guarantee must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458.

[signature(s)]

[Note:  All italicized text is for use in preparing this form and shall be deleted from the final product.]

Form of Bid Security (Bid Bond)

BOND NO. [insert Bond No.]

BY THIS BOND [insert name of Bidder] as Principal (hereinafter called “the Principal”), and [insert name, legal title, and address of surety], authorized to transact business in [insert name of country of Employer], as Surety (hereinafter called “the Surety”), are held and firmly bound unto [insert name of Employer] as Obligee (hereinafter called “the Employer”) in the sum of [insert amount of Bond in words and figures], for the payment of which sum, well and truly to be made, we, the said Principal and Surety, bind ourselves, our successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Principal has submitted a written Bid to the Employer dated the [insert day] day of [insert month], 20 [insert year], for the construction of [insert name of Contract] (hereinafter called the “Bid”).

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that if the Principal:

- withdraws its Bid during the period of Bid validity specified in the Form of Bid; or

- having been notified of the acceptance of its Bid by the Employer during the period of Bid validity; (i) fails or refuses to execute the Contract Form, if required; or (ii) fails or refuses to furnish the Performance Security in accordance with the Instructions to Bidders;

then the Surety undertakes to immediately pay to the Employer up to the above amount upon receipt of the Employer’s first written demand, without the Employer having to substantiate its demand, provided that in its demand the Employer shall state that the demand arises from the occurrence of any of the above events, specifying which event(s) has occurred.

The Surety hereby agrees that its obligation will remain in full force and effect up to and including the date twenty-eight (28) days after the date of expiration of the Bid validity as stated in the Invitation for Bid or extended by the Employer at any time prior to this date, notice of which extension(s) to the Surety being hereby waived.

IN TESTIMONY WHEREOF, the Principal and the Surety have caused these presents to be executed in their respective names this [insert day]  day of [insert month] 20 [insert year].

Principal: _______________________	Surety: _____________________________
	Corporate Seal (where appropriate)

_______________________________	____________________________________
(Signature)	(Signature)

(Printed name and title)	(Printed name and title)

Section V.  Eligible Source Countries of Japanese ODA Loans

[Specify the Eligible Source Countries.]

PART 2 - Employer’s Requirements

Section VI. Employer’s Requirements

## Notes on Employer’s Requirements This Section contains the Scope, the Specifications, the Drawings, Supplementary Information that describe the Facilities and Forms to be used during the implementation of the Contract. In a design, supply and install approach, the design is to be done by the Contractor. No detailed technical specification as is normal practice is developed at the pre-bid stage. However, the Employer does and must know what it wants and must communicate its needs to the Bidders. Hence, this section on Employer’s Requirements replaces the usual Technical Specifications of a more traditional approach. To enable Bidders to submit responsive Bids and subsequently for the Bids received to be evaluated in an equitable manner, the Employer must take its requirements as clearly and as precisely as possible. The Employer’s Requirements must therefore, specify exactly the particular requirements of the completed Facilities. Where the performance of the completed Facilities could be measured in quantitative terms such as production output of a manufacturing plant or maximum generating capacity of a power station, the Employer’s Requirements should not only clearly specify the desired output/capacity, but also the upper and lower acceptable limits of variation from the desired capacity. It will also be necessary to specify the tests that will be carried out on completion of the Facilities to verify compliance with the requirements specified. The Employer’s Requirements should also clearly specify what associated or incidental services and goods must be supplied by the Contractor. For example, the Contractor may be required to train the Employer’s Personnel and to supply consumable or spare parts as listed in a schedule. While this section of the Bidding Documents should endeavor to define the Employer’s Requirements as precisely as possible, care must be taken to avoid overspecifying details to the extent that the flexibility and potential benefits associated with a design, supply and install Contract are seriously eroded or threatened. This section on Employer’s Requirements should, therefore, be carefully prepared on behalf of the Employer by suitably-qualified engineers who are familiar with the requirements and with the technical aspect of the required Facilities. For a JICA-financed design, supply and install Contract to be procured through International Competitive Bidding procedures, the Employer’s Requirements must be drawn up to permit the widest, possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials and performance of the Facilities. Only if this is done, will the objectives of economy and efficiency, non-discrimination and transparency in procurement be realized, the responsiveness of Bids be ensured and the subsequent task of Bid evaluation facilitated. The Employer’s Requirements should stipulate that all goods and materials to be incorporated in the Facilities are new, unused, of the most recent or current models and incorporate all recent improvements in design and materials. As for the drafting of the Specification, care must be taken when drafting the Employer’s Requirements to ensure that the requirements are not restrictive. Recognized international standards should be used as much as possible for the description of goods, materials and workmanship. Where other particular standards are specified, whether national standards of the Borrower’s country or other standards, it should be stated that goods, materials and workmanship meeting other authoritative standards and which promise to ensure equal or higher quality than the standards specified, will also be acceptable. Where a brand name of a product is specified, it should always be qualified with the terms “or equivalent”. For a design, supply and install Contract, no detailed drawings would generally be available at the pre-bid stage. It would, however, be useful to include such conceptual drawings as are appropriate to supplement or help explain the general concept of the Employer’s needs.

Table of Contents

Scope of Supply of Plant and Installation Services by the Contractor	1

Specification	1

Forms and Procedures	1

Form of Completion Certificate	1

Form of Operational Acceptance Certificate	1

Change Order Procedure and Forms	1

Change Order Procedure	1

Annex 1.  Request for Change Proposal	1

Annex 2.  Estimate for Change Proposal	1

Annex 3.  Acceptance of Estimate	1

Annex 4.  Change Proposal	1

Annex 5.  Change Order	1

Annex 6.  Pending Agreement Change Order	1

Annex 7.  Application for Change Proposal	1

Annex 8.  Change Order log	1

Drawings	1

Supplementary Information	1

Scope of Supply of Plant and Installation Services by the Contractor

[Insert scope.]

Specification

[Insert the specifications.]

Forms and Procedures

Form of Completion Certificate

Date:	[insert date]

Loan Agreement No:	[insert number]

IFB No:	[insert number]

[Name of Contract]

To: [Name and address of Contractor]

Dear Sirs,

Pursuant to GC Clause 24 (Completion of the Facilities) of the General Conditions of the Contract entered into between yourselves and the Employer dated [insert date] , relating to the [brief description of the Facilities] ,  we hereby notify you that the following part(s) of the Facilities was(were) complete on the date specified below, in accordance with the terms of the Contract.

1.	Description of the Facilities or part thereof: [insert description]

2.	Date of Completion: [insert date]

However, you are required to complete the outstanding items listed in the attachment hereto as soon as practicable.

This letter does not relieve you of your obligation to complete the execution of the Facilities in accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,

Title

(Project Manager)

Form of Operational Acceptance Certificate

Date:	[insert date]

Loan Agreement No:	[insert number]

IFB No:	[insert number]

[Name of Contract]

To: [Name and address of Contractor]

Dear Sirs,

Pursuant to GC Sub-Clause 25.3 (Operational Acceptance) of the General Conditions of the Contract entered into between yourselves and the Employer dated [insert date], relating to the [brief description of the Facilities], we hereby notify you that the Functional Guarantees of the following part(s) of the Facilities were satisfactorily attained on the date specified below.

1.	Description of the Facilities or part thereof: [insert description]

2.	Date of Operational Acceptance: [insert date]

This letter does not relieve you of your obligation to complete the execution of the Facilities in accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,

Title

(Project Manager)

Change Order Procedure and Forms

Date:	[insert date]

Loan Agreement No:	[insert number]

IFB No:	[insert number]

CONTENTS

1.	General

2.	Change Order Log

3.	References for Changes

ANNEXES

Annex 1	Request for Change Proposal

Annex 2	Estimate for Change Proposal

Annex 3	Acceptance of Estimate

Annex 4	Change Proposal

Annex 5	Change Order

Annex 6	Pending Agreement Change Order

Annex 7	Application for Change Proposal

Annex 8	Change Order log

Change Order Procedure

1.	General

This section provides samples of procedures and forms for implementing changes in the Facilities during the performance of the Contract in accordance with GC Clause 39 (Change in the Facilities) of the General Conditions of the Contract.

2.	Change Order Log

The Contractor shall keep an up-to-date Change Order log to show the current status of Requests for Change and Changes authorized or pending, as Annex 8.  Entries of the Changes in the Change Order log shall be made to ensure that the log is up-to-date.  The Contractor shall attach a copy of the current Change Order Log in the monthly progress report to be submitted to the Employer.

3.	References for Changes

(1)	Request for Change as referred to in GC Clause 39 shall be serially numbered CR-X-nnn.

(2)	Estimate for Change Proposal as referred to in GC Clause 39 shall be serially numbered CN-X-nnn.

(3)	Acceptance of Estimate as referred to in GC Clause 39 shall be serially numbered CA-X-nnn.

(4)	Change Proposal as referred to in GC Clause 39 shall be serially numbered CP-X-nnn.

(5)	Change Order as referred to in GC Clause 39 shall be serially numbered CO-X-nnn.

Note:	(a)	Requests for Change issued from the Employer’s Home Office and the Site representatives of the Employer shall have the following respective references:

Home Office	CR-H-nnn

Site	CR-S-nnn

(b)	The above number “nnn” is the same for Request for Change, Estimate for Change Proposal, Acceptance of Estimate, Change Proposal and Change Order.

Annex 1.  Request for Change Proposal

(Employer’s Letterhead)

To: [insert Contractor’s name and address]	Date: [insert date]

Attention: [insert name and title]

Contract Name: [insert Contract name]

Contract Number: [insert Contract number]

Dear Sirs,

With reference to the captioned Contract, you are requested to prepare and submit a Change Proposal for the Change noted below in accordance with the following instructions within [insert number of days] days of the date of this letter [or on or before (date)].

1.	Title of Change: [insert title] ________________________

2.	Change Request No.: [insert number] ________________________

3.	Originator of Change:  Employer: [insert name of Employer] ________________________

Contractor (by Application for Change Proposal No. [insert number])________________________

4.	Brief Description of Change: [insert description] ________________________

5.	Facilities and/or Item No. of equipment related to the requested Change: [insert description] ________________________

6.	Reference drawings and/or technical documents for the request of Change:

Drawing No./Document No.	Description

7.	Detailed conditions or special requirements on the requested Change:  ________________

8.	General Terms and Conditions:

(a)	Please submit your estimate to us showing what effect the requested Change will have on the Contract Price.

(b)	Your estimate shall include your claim for the additional time, if any, for completion of the requested Change.

(c)	If you have any opinion negative to the adoption of the requested Change in connection with the conformability to the other provisions of the Contract or the safety of the Plant or Facilities, please inform us of your opinion in your proposal of revised provisions.

(d)	Any increase or decrease in the work of the Contractor relating to the services of its personnel shall be calculated.

(e)	You shall not proceed with the execution of the work for the requested Change until we have accepted and confirmed the amount and nature in writing.

(Employer’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 2.  Estimate for Change Proposal

(Contractor’s Letterhead)

To: [insert Employer’s Name and address] 	Date: [insert date]

Attention: [insert name and title]

Contract Name: [insert Contract name]

Contract Number: [insert Contract number]

Dear Sirs,

With reference to your Request for Change Proposal, we are pleased to notify you of the approximate cost of preparing the below-referenced Change Proposal in accordance with GC Sub-Clause 39.2.1 of the General Conditions of the Contract.  We acknowledge that your agreement to the cost of preparing the Change Proposal, in accordance with GC Sub-Clause 39.2.2 of the General Conditions of the Contract, is required before estimating the cost for change work.

1.	Title of Change: [insert title] ________________________

2.	Change Request No./Rev.: [insert number] ____________________________

3.	Brief Description of Change: [insert description] __________________________

4.	Scheduled Impact of Change: [insert description] ___________________________

5.	Cost for Preparation of Change Proposal: [insert cost] ______________

(a)	Engineering	(Amount)

(i)	Engineer		 hrs x 	 rate/hr =

(ii)	Draftsperson		 hrs x 	 rate/hr =

Sub-total		 hrs

Total Engineering Cost

(b)	Other Cost

Total Cost (a) + (b)

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 3.  Acceptance of Estimate

(Employer’s Letterhead)

To: [insert Contractor’s name and address] 	Date: [insert date]

Attention: [insert name and title]

Contract Name: [insert Contract name]

Contract Number: [insert Contract number]

Dear Sirs,

We hereby accept your Estimate for Change Proposal and agree that you should proceed with the preparation of the Change Proposal.

1.	Title of Change: [insert title] ___________________________

2.	Change Request No./Rev.: [insert number] _______________________________

3.	Estimate for Change Proposal No./Rev.: [insert number] ________________________

4.	Acceptance of Estimate No./Rev.: [insert number] _______________________________

5.	Brief Description of Change: [insert description] _______________________________

6.	Other Terms and Conditions:  In the event that we decide not to order the Change accepted, you shall be entitled to compensation for the cost of preparation of Change Proposal described in your Estimate for Change Proposal mentioned in 3 above, in accordance with GC Clause 39 of the General Conditions of the Contract.

(Employer’s Name)

(Signature)

(Name and Title of signatory)

Annex 4.  Change Proposal

(Contractor’s Letterhead)

To: [insert Employer’s Name and address] 	Date: [insert date]

Attention: [insert name and title]

Contract Name: [insert Contract name]

Contract Number: [insert Contract number]

Dear Sirs,

In response to your Request for Change Proposal No. [insert number], we hereby submit our proposal as follows:

1.	Title of Change: [insert title] _______________________________

2.	Change Proposal No./Rev.: [insert number] ______________________________

3.	Originator of Change: Employer: [insert name of Employer] ________________________

Contractor: [insert name of Contractor] _____________________

4.	Brief Description of Change: [insert description] _______________________________

5.	Reasons for Change: [insert reason] ______________________________

6.	Facilities and/or Item No. of Equipment related to the requested Change: [insert description] _______________________________

7.	Reference drawings and/or technical documents for the requested Change:

Drawing/Document No.	Description

8.	Estimate of increase/decrease to the Contract Price resulting from Change Proposal:

(Amount)

(a)	Direct material

(b)	Major construction equipment

(c)	Direct field labor (Total 	 hrs)

(d)	Subcontracts

(e)	Indirect material and labor

(f)	Site supervision

(g)	Head office technical staff salaries

Process engineer		 hrs @ 	 rate/hr

Project engineer		 hrs @ 	 rate/hr

Equipment engineer		 hrs @ 	 rate/hr

Procurement		 hrs @ 	 rate/hr

Draftsperson		 hrs @ 	 rate/hr

Total		 hrs

(h)	Extraordinary costs (computer, travel, etc.)

(i)	Fee for general administration, 	 % of Items

(j)	Taxes and customs duties

Total lump sum cost of Change Proposal

(Sum of items (a) to (j))

Cost to prepare Estimate for Change Proposal

(Amount payable if Change is not accepted)

9.	Additional time for Completion required due to Change Proposal

10.	Effect on the Functional Guarantees

11.	Effect on the other terms and conditions of the Contract

12.	Validity of this Proposal:  within [number] days after receipt of this Proposal by the Employer

13.	Other terms and conditions of this Change Proposal:

(a)	You are requested to notify us of your acceptance, comments or rejection of this detailed Change Proposal within [number] days from your receipt of this Proposal.

(b)	The amount of any increase and/or decrease shall be taken into account in the adjustment of the Contract Price.

(c)	Contractor’s cost for preparation of this Change Proposal:

[Note: This cost shall be reimbursed by the Employer in case of Employer’s withdrawal or rejection of this Change Proposal without default of the Contractor in accordance with GC 39 of the General Conditions of the Contract.]

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 5.  Change Order

(Employer’s Letterhead)

To: [insert Contractor’s name and address]	Date: [insert date]

Attention: [insert name and title]

Contract Name: [insert Contract name]

Contract Number: [insert Contract number]

Dear Sirs,

We approve the Change Order for the Facilities specified in the Change Proposal (No. [insert number]), and agree to adjust the Contract Price, Time for Completion and/or other conditions of the Contract in accordance with GC Clause 39 of the General Conditions of the Contract.

1.	Title of Change: [insert title] _______________________________

2.	Change Request No./Rev.: [insert number] _______________________________

3.	Change Order No./Rev.: [insert number] _______________________________

4.	Originator of Change:	Employer: [insert name of Employer] ________________________

Contractor: [insert name of Contractor] ____________________

5.	Authorized Price:

Ref. No.: [insert number] __________________________	Date: [insert date]______________

Foreign currency portion: [insert amount] __________ plus Local currency portion: [insert amount] __________

6.	Adjustment of Time for Completion

None	Increase [insert number] days	               Decrease [insert number] days

7.	Other effects, if any

Authorized by:  		Date:

(Employer)

Accepted by:  		Date:

(Contractor)

Annex 6.  Pending Agreement Change Order

(Employer’s Letterhead)

To: [insert Contractor’s name and address] 	Date: [insert date]

Attention: [insert name and title]

Contract Name: [insert Contract name]

Contract Number: [insert Contract number]

Dear Sirs,

We instruct you to carry out the work in the Change Order detailed below in accordance with Clause 39 of the General Conditions.

1.	Title of Change: [insert title] ______________________________

2.	Employer’s Request for Change Proposal No./Rev.: [insert number] __________________ dated: [insert date] __________

3.	Contractor’s Change Proposal No./Rev.: [insert number] ___________________________ dated: [insert date] __________

4.	Brief Description of Change: [insert description] _______________________________

5.	Facilities and/or Item No. of equipment related to the requested Change: [insert description] _______________________________

6.	Reference Drawings and/or technical documents for the requested Change:

Drawing/Document No.	Description

7.	Adjustment of Time for Completion:

8.	Other change in the Contract terms:

9.	Other terms and conditions:

(Employer’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 7.  Application for Change Proposal

(Contractor’s Letterhead)

To: [insert Employer’s Name and address] 	Date: [insert date]

Attention: [insert name and title]

Contract Name: [insert Contract name]

Contract Number: [insert Contract number]

Dear Sirs,

We hereby propose that the below-mentioned work be treated as a Change in the Facilities.

1.	Title of Change: [insert title] _______________________________

2.	Application for Change Proposal No./Rev.: [insert number] ______	dated:  [insert date] _______________________________

3.	Brief Description of Change: [insert description] _______________________________

4.	Reasons for Change: [insert reason] _______________________________

5.	Order of Magnitude Estimation (in the currencies of the Contract): [insert amount] ___

6.	Scheduled Impact of Change: [insert scheduled impact] ______________________________

7.	Effect on Functional Guarantees, if any: [insert effect, if any] _________________________

8.	Appendix:

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 8.  Change Order log

[The Contractor shall prepare an up-to-date Change Order log, in accordance with Clause 2 of the Change Order Procedure, and attach a copy of it to the monthly progress report to be submitted to the Employer.]

Drawings

[It is customary to bind the drawings in a separate volume, which is often larger than other volumes of the Contract documents.  The size will be dictated by the scale of the drawings, which must not be reduced to the extent that details are rendered illegible.

A simplified map showing the location of the Site in relation to the local geography, including major roads, posts, airports, and railroads, is helpful.

The drawings, even if not fully developed, must show sufficient details to enable Bidders to understand the type and complexity of the work involved.]

Supplementary Information

[Insert any supplementary information.]

PART 3 - Conditions of Contract and Contract Forms

Section VII. General Conditions (GC)

## Notes on General Conditions The Conditions of Contract comprise two parts: (a) Standard General Conditions – GC (Section VII of the Bidding Documents); and (b) Particular Conditions – PC (Section VIII of the Bidding Documents). The General Conditions set forth in Part 3, Section VII of these Standard Bidding Documents for Procurement of Plant Design, Supply and Installation (version 1.0) issued by JICA in February, 2013 (hereinafter referred to as “Standard GC”), are based on the Model Form of International Contract for Process Plant Construction published by the Engineering Advancement Association of Japan (ENAA). The GC contain general clauses to be applied to all Contracts. The use of these Standard GC, in all Bidding Documents/Contracts for Procurement of Plant Design, Supply and Installation works financed by Japanese ODA Loans is required, and they shall be used without any modification. If the General Conditions in the Bidding Documents/Contracts prepared by the Employer contain modifications from the Standard GC, JICA will not consider them valid and the Standard GC, as defined above, shall apply. The GC in this Section, read in conjunction with the Particular Conditions in Section VIII and other documents listed therein, should be a complete document expressing all the rights and obligations of the contracting Parties. Any amendments and additions to the General Conditions, specific to the Contract in hand, should be introduced in the Particular Conditions. A number of such Particular Conditions, applicable to the above Conditions of Contract, are included in Section VIII. The Particular Conditions (PC) take precedence over the General Conditions—see Article 1.2 (Order of Precedence) of the Contract Agreement. Whoever drafts the PC should be thoroughly familiar with the provisions of the GC and with any specific requirements of the Contract. Legal advice is recommended when amending provisions or drafting new ones. Clause numbers in the PC correspond to those in the GC.

Section VII. General Conditions (GC)

[Note to the Employer: The General Conditions governing Contracts funded with Japanese ODA Loans  are the Standard General Conditions of Contract  (hereinafter referred to as “Standard GC”) set forth in Part 3, Section VII of these Standard Bidding Documents for Procurement of Plant Design, Supply and Installation (version 1.0) (SBD (Plant)) published by JICA in February, 2013.

A copy of the Standard GC may be attached to Bidding Documents/Contracts prepared by the Employer for reference purposes only. If the General Conditions in the Bidding Documents/Contracts prepared by the Employer contain modifications from the Standard GC, JICA will not consider these General Conditions valid and the Standard GC, as defined above, shall apply.

Instead of attaching a copy of the Standard GC, the Employer may use the following introductory text.]

The General Conditions governing this Contract are the Standard General Conditions of Contract set forth in Part 3, Section VII of the Standard Bidding Documents for Procurement of Plant Design, Supply and Installation (version 1.0)) published by JICA in February, 2013. Those General Conditions of Contract are available on the JICA’s web site shown below:

http://www.jica.go.jp/english/our_work/types_of_assistance/oda_loans/oda_op_info/guide/tender/index.html

A copy of these General Conditions is not attached to these Bidding Documents/this Contract.

APPENDIX

A	General Conditions of Dispute Board Agreement

1.	Definitions

Each “Dispute Board Agreement” is a tripartite agreement by and between:

(a) the “Employer”;

(b) the “Contractor”; and

(c) the “Member” who is defined in the Dispute Board Agreement as being:

(i)  the sole member of the Dispute Board (“DB”) and, where this is the case, all references to the “Other Members” do not apply, or

(ii)  one of the three persons who are jointly called the DB and, where this is the case, the other two persons are called the “Other Members”.

The Employer and the Contractor have entered (or intend to enter) into a contract, which is called the “Contract” and is defined in the Dispute Board Agreement, which incorporates this Appendix. In the Dispute Board Agreement, words and expressions which are not otherwise defined shall have the meanings assigned to them in the Contract.

2.	General Provisions

Unless otherwise stated in the Dispute Board Agreement, it shall take effect on the latest of the following dates:

(a)	the Commencement Date defined in the Contract,

(b)  	when the Employer, the Contractor and the Member have each signed the Dispute Board Agreement, or

(c) 	when the Employer, the Contractor and each of the Other Members (if any) have respectively each signed a dispute board agreement.

This employment of the Member is a personal appointment. At any time, the Member may give not less than seventy (70) days’ notice of resignation to the Employer and to the Contractor, and the Dispute Board Agreement shall terminate upon the expiry of this period.

3.	Warranties

The Member warrants and agrees that he/she is and shall be impartial and independent of the Employer, the Contractor and the Project Manager. The Member shall promptly disclose, to each of them and to the Other Members (if any), any fact or circumstance which might appear inconsistent with his/her warranty and agreement of impartiality and independence.

When appointing the Member, the Employer and the Contractor relied upon the Member’s representations that he/she is:

(a) 	experienced in the work which the Contractor is to carry out under the Contract,

(b)	 experienced in the interpretation of contract documentation, and

(c) 	fluent in the language for communications defined in the Contract.

4.	General Obligations of the Member

The Member shall:

(a) 	have no interest financial or otherwise in the Employer, the Contractor or the Project Manager, nor any financial interest in the Contract except for payment under the Dispute Board Agreement;

(b) 	not previously have been employed as a consultant or otherwise by the Employer, the Contractor or the Project Manager, except in such circumstances as were disclosed in writing to the Employer and the Contractor before they signed the Dispute Board Agreement;

(c) 	have disclosed in writing to the Employer, the Contractor and the Other Members (if any), before entering into the Dispute Board Agreement and to his/her best knowledge and recollection, any professional or personal relationships with any director, officer or employee of the Employer, the Contractor or the Project Manager, and any previous involvement in the overall project of which the Contract forms part;

(d)  	not, for the duration of the Dispute Board Agreement, be employed as a consultant or otherwise by the Employer, the Contractor or the Project Manager, except as may be agreed in writing by the Employer, the Contractor and the Other Members (if any);

(e)	comply with the annexed procedural rules and with GC Sub-Clause 45.3;

(f)	not give advice to the Employer, the Contractor, the Employer’s Personnel or the Contractor’s Personnel concerning the conduct of the Contract, other than in accordance with the annexed procedural rules;

(g)	not while a Member enter into discussions or make any agreement with the Employer, the Contractor or the Project Manager regarding employment by any of them, whether as a consultant or otherwise, after ceasing to act under the Dispute Board Agreement;

(h)	ensure his/her availability for all site visits and hearings as are necessary;

(i)	become conversant with the Contract and with the progress of the Facilities (and of any other parts of the project of which the Contract forms part) by studying all documents received which shall be maintained in a current working file;

(j)	treat the details of the Contract and all the DB’s activities and hearings as private and confidential, and not publish or disclose them without the prior written consent of the Employer, the Contractor and the Other Members (if any); and

(k)	be available to give advice and opinions, on any matter relevant to the Contract when requested by both the Employer and the Contractor, subject to the agreement of the Other Members (if any).

5.	General Obligations of the Employer and the Contractor

The Employer, the Contractor, the Employer’s Personnel and the Contractor’s Personnel shall not request advice from or consultation with the Member regarding the Contract, otherwise than in the normal course of the DB’s activities under the Contract and the Dispute Board Agreement. The Employer and the Contractor shall be responsible for compliance with this provision, by the Employer’s Personnel and the Contractor’s Personnel respectively.

The Employer and the Contractor undertake to each other and to the Member that the Member shall not, except as otherwise agreed in writing by the Employer, the Contractor, the Member and the Other Members (if any):

(a)	be appointed as an arbitrator in any arbitration under the Contract;

(b)	be called as a witness to give evidence concerning any dispute before arbitrator(s) appointed for any arbitration under the Contract; or

(c)	be liable for any claims for anything done or omitted in the discharge or purported discharge of the Member’s functions, unless the act or omission is shown to have been in bad faith.

The Employer and the Contractor hereby jointly and severally indemnify and hold the Member harmless against and from claims from which he is relieved from liability under the preceding paragraph.

Whenever the Employer or the Contractor refers a dispute to the DB under GC Sub-Clause 45.3, which will require the Member to make a site visit and attend a hearing, the Employer or the Contractor shall provide appropriate security for a sum equivalent to the reasonable expenses to be incurred by the Member. No account shall be taken of any other payments due or paid to the Member.

6.	Payment

The Member shall be paid as follows, in the currency named in the Dispute Board Agreement:

(a)	a retainer fee per calendar month, which shall be considered as payment in full for:

(i)	being available on twenty-eight (28) days’ notice for all site visits and hearings;

(ii)	becoming and remaining conversant with all project developments and maintaining relevant files;

(iii) 	all office and overhead expenses including secretarial services, photocopying and office supplies incurred in connection with his duties; and

(iv) 	all services performed hereunder except those referred to in sub-paragraphs (b) and (c) of this Clause.

The retainer fee shall be paid with effect from the last day of the calendar month in which the Dispute Board Agreement becomes effective; until the last day of the calendar month in which the Operational Acceptance Certificate is issued for the whole of the Facilities.

With effect from the first day of the calendar month following the month in which Operational Acceptance Certificate is issued for the whole of the Facilities, the retainer fee shall be reduced by one third. This reduced fee shall be paid until the first day of the calendar month in which the Member resigns or the Dispute Board Agreement is   otherwise terminated.

(b) 	a daily fee which shall be considered as payment in full for:

(i) 	each day or part of a day up to a maximum of two days’ travel time in each direction for the journey between the Member’s home and the site, or another location of a meeting with the Other Members (if any);

(ii) 	each working day on site visits, hearings or preparing decisions; and

(iii) 	each day spent reading submissions in preparation for a hearing.

(c)  	all reasonable expenses including necessary travel expenses (air fare in less than first class, hotel and subsistence and other direct travel expenses) incurred in connection with the Member’s duties, as well as the cost of telephone calls, courier charges, faxes and telexes: a receipt shall be required for each item in excess of five percent of the daily fee referred to in sub-paragraph (b) of this Clause;

(d)	any taxes properly levied in the Country on payments made to the Member (unless a national or permanent resident of the Country) under this Clause 6.

The retainer and daily fees shall be as specified in the Dispute Board Agreement. Unless it specifies otherwise, these fees shall remain fixed for the first twenty-four (24) calendar months, and shall thereafter be adjusted by agreement between the Employer, the Contractor and the Member, at each anniversary of the date on which the Dispute Board Agreement became effective.

If the Parties fail to agree on the retainer fee or the daily fee the appointing entity or official named in the PC shall determine the amount of the fees to be used.

The Member shall submit invoices for payment of the monthly retainer and air fares quarterly in advance. Invoices for other expenses and for daily fees shall be submitted following the conclusion of a site visit or hearing. All invoices shall be accompanied by a brief description of activities performed during the relevant period and shall be addressed to the Contractor.

The Contractor shall pay each of the Member’s invoices in full within fifty-six (56) calendar days after receiving each invoice and shall apply to the Employer (in the Statements under the Contract) for reimbursement of one-half of the amounts of these invoices. The Employer shall then pay the Contractor in accordance with the Contract.

If the Contractor fails to pay to the Member the amount to which he/she is entitled under the Dispute Board Agreement, the Employer shall pay the amount due to the Member and any other amount which may be required to maintain the operation of the DB; and without prejudice to the Employer’s rights or remedies. In addition to all other rights arising from this default, the Employer shall be entitled to reimbursement of all sums paid in excess of one-half of these payments, plus all costs of recovering these sums and financing charges calculated at the rate specified in accordance with GC Sub-Clause 12.3.

If the Member does not receive payment of the amount due within seventy (70) days after submitting a valid invoice, the Member may (i) suspend his/her services (without notice) until the payment is received, and/or (ii) resign his/her appointment by giving notice under Clause 7.

7.	Termination

At any time: (i) the Employer and the Contractor may jointly terminate the Dispute Board Agreement by giving forty-two (42) days’ notice to the Member; or (ii) the Member may resign as provided for in Clause 2.

If the Member fails to comply with the Dispute Board Agreement, the Employer and the Contractor may, without prejudice to their other rights, terminate it by notice to the Member. The notice shall take effect when received by the Member.

If the Employer or the Contractor fails to comply with the Dispute Board Agreement, the Member may, without prejudice to his other rights, terminate it by notice to the Employer and the Contractor. The notice shall take effect when received by them both.

Any such notice, resignation and termination shall be final and binding on the Employer, the Contractor and the Member. However, a notice by the Employer or the Contractor, but not by both, shall be of no effect.

8.	Default of the Member

If the Member fails to comply with any of his obligations under Clause 4 concerning his impartiality or independence in relation to the Employer or the Contractor, he/she shall not be entitled to any fees or expenses hereunder and shall, without prejudice to their other rights, reimburse each of the Employer and the Contractor for any fees and expenses received by the Member and the Other Members (if any), for proceedings or decisions (if any) of the DB which are rendered void or ineffective by the said failure to comply.

9.	Disputes

Any dispute or claim arising out of or in connection with this Dispute Board Agreement, or the breach, termination or invalidity thereof, shall be finally settled by institutional arbitration. The arbitration shall be conducted under the Rules of Arbitration of the International Chamber of Commerce by one arbitrator appointed in accordance with these Rules of Arbitration.

## Annex

## DISPUTE BOARD GUIDELINES

1. 	Unless otherwise agreed by the Employer and the Contractor, the DB shall visit the site at intervals of not more than one hundred forty (140) days, including times of critical construction events, at the request of either the Employer or the Contractor. Unless otherwise agreed by the Employer, the Contractor and the DB, the period between consecutive visits shall not be less than seventy (70) days, except as required to convene a hearing as described below.

2. 	The timing of and agenda for each site visit shall be as agreed jointly by the DB, the Employer and the Contractor, or in the absence of agreement, shall be decided by the DB. The purpose of site visits is to enable the DB to become and remain acquainted with the progress of the Contract and of any actual or potential problems or claims, and, as far as reasonable, to prevent potential problems or claims from becoming disputes.

3.  	Site visits shall be attended by the Employer, the Contractor and the Project Manager and shall be co-ordinated by the Employer in co-operation with the Contractor. The Employer shall ensure the provision of appropriate conference facilities and secretarial and copying services. At the conclusion of each site visit and before leaving the site, the DB shall prepare a report on its activities during the visit and shall send copies to the Employer and the Contractor.

4.  	The Employer and the Contractor shall furnish to the DB one copy of all documents which the DB may request, including Contract documents, progress reports, variation instructions, certificates and other documents pertinent to the performance of the Contract. All communications between the DB and the Employer or the Contractor shall be copied to the other Party. If the DB comprises three persons, the Employer and the Contractor shall send copies of these requested documents and these communications to each of these persons.

5.  	If any dispute is referred to the DB in accordance with GC Sub-Clause 45.3, the DB shall proceed in accordance with GC Sub-Clause 45.3 and these Guidelines. Subject to the time allowed to give notice of a decision and other relevant factors, the DB shall:

(a)  	act fairly and impartially as between the Employer and the Contractor, giving each of them a reasonable opportunity of putting his case and responding to the other’s case, and

(b)  	adopt procedures suitable to the dispute, avoiding unnecessary delay or expense.

6.  	The DB may conduct a hearing on the dispute, in which event it will decide on the date and place for the hearing and may request that written documentation and arguments from the Employer and the Contractor be presented to it prior to or at the hearing.

7. 	 Except as otherwise agreed in writing by the Employer and the Contractor, the DB shall have power to adopt an inquisitorial procedure, to refuse admission to hearings or audience at hearings to any persons other than representatives of the Employer, the Contractor and the Project Manager, and to proceed in the absence of any Party who received notice of the hearing; but shall have discretion to decide whether and to what extent this power may be exercised.

8.       The Employer and the Contractor empower the DB, among other things, to:

(a) 	establish the procedure to be applied in deciding a dispute,

(b) 	decide upon the DB’s own jurisdiction, and as to the scope of any dispute referred to it,

(c) 	conduct any hearing as it thinks fit, not being bound by any rules or procedures other than those contained in the Contract and these Guidelines,

(d) 	take the initiative in ascertaining the facts and matters required for a decision,

(e)	make use of its own specialist knowledge, if any,

(f) 	decide upon the payment of financing charges in accordance with the Contract,

(g) 	decide upon any provisional relief such as interim or conservatory measures,

(h) 	open up, review and revise any certificate, decision, determination, instruction, opinion or valuation of the Project Manager, relevant to the dispute, and

(i)  	appoint, should the DB so consider necessary and the Parties agree, a suitable expert at the cost of the Parties to give advice on a specific matter relevant to the dispute.

9.  	The DB shall not express any opinions during any hearing concerning the merits of any arguments advanced by the Parties. Thereafter, the DB shall make and give its decision in accordance with GC Sub-Clause 45.3, or as otherwise agreed by the Employer and the Contractor in writing. If the DB comprises three persons:

(a)  	it shall convene in private after a hearing, in order to have discussions and prepare its decision;

(b)  	it shall endeavour to reach a unanimous decision: if this proves impossible the applicable decision shall be made by a majority of the Members, who may require the minority Member to prepare a written report for submission to the Employer and the Contractor; and

(c) 	 if a Member fails to attend a meeting or hearing, or to fulfil any required function, the other two Members may nevertheless proceed to make a decision, unless:

(i)	either the Employer or the Contractor does not agree that they do so, or

(ii) 	the absent Member is the chairman and he/she instructs the other Members to not make a decision.

Section VIII.  Particular Conditions

## Notes on Particular Conditions The Particular Conditions (PC) complement the General Conditions (GC) to specify data and contractual requirements linked to the special circumstances of the country, the Employer, or the overall project. Whenever there is a conflict, the provisions herein shall prevail over those in the GC.

## Particular Conditions

## Table of Clauses

PC 1.	Definitions	1

PC 5.	Law and Language	1

PC 7.	Scope of Facilities	1

PC 8.	Time for Commencement and Completion	1

PC 11.	Contract Price	1

PC 13. 	Securities	1

PC 22.	Installation	1

PC 25.	Commissioning and Operational Acceptance	1

PC 26.	Completion Time Guarantee	1

PC 30.	Limitation of Liability	1

PC 45.	Disputes and Arbitration	1

Particular Conditions

| PC 1. Definitions |  |
| --- | --- |
| PC 1.1 | The Employer is: [insert Employer’s name] The Project Manager is: [insert Project Manager’s name ] |
| PC 5. Law and Language |  |
| PC 5.1 | The Contract shall be interpreted in accordance with the laws of: [insert name of Employer's country ] |
| PC 5.2 | The ruling language is: [insert one of the following: “Japanese”, “English”, “Spanish” or “French”] |
| PC 5.3 | The language for communications is: [insert the language if different from the ruling language. Otherwise, delete this Clause PC 5.3.] |
| PC 7. Scope of Facilities |  |
| PC 7.3 | The Contractor agrees to supply spare parts for a period of years: [insert the same number of years as in Clause 16.1 (b) of the BDS of the Instructions to Bidders] [Where appropriate use the following additional provision to PC 7.3, otherwise delete the provision from this Clause PC 7.3] The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the Plant. Other spare parts and components shall be supplied as promptly as possible, but at the most within six (6) months of placing the order and opening the letter of credit. In addition, in the event of termination of the production of spare parts, advance notification will be made to the Employer of the pending termination, with sufficient time to permit the Employer to procure the needed requirement. Following such termination, the Contractor will furnish to the extent possible and at no cost to the Employer the blueprints, drawings and specifications of the spare parts, if requested. |
| PC 8. Time for Commencement and Completion |  |
| PC.8.1 | The Contractor shall commence work on the Facilities within [insert number of days as appropriate, in words and figures] days from the Effective Date for determining Time for Completion as specified in the Contract Agreement. |
| PC 8.2 | The Time for Completion of the whole of the Facilities shall be [insert number of days (months) in words and figures] days from the Effective Date as described in the Contract Agreement. [Where appropriate use the following additional provision to PC 8.2, otherwise delete the provision] The Time for Completion for parts of the Facilities shall be [insert days (months) in words and figures] from the Effective Date as described in the Contract Agreement. [and where applicable] Sample Provision The Time for completion for parts of the Facilities: Description Time for completion [Each part of the Facilities subject to a specific Time for Completion shall be listed and briefly described with its respective Time for Completion specified in days, in words and figures.] |
| PC 11. Contract Price |  |
| PC 11.2 | [This provision is to be inserted only if Contract Price is subject to adjustment, otherwise delete the provision.] The Contract Price shall be adjusted in accordance with the provisions of Appendix 2 (Price Adjustment) to the Contract Agreement. |
| PC 13. Securities |  |
| PC 13.3.1 | The amount of Performance Security, as a percentage of the Contract Price for the Facility or for the part of the Facility for which a separate Time for Completion is provided, shall be: [insert amount which should be between 5 and 15% of the Contract Price]. |
| PC 13.3.2 | The Performance Security shall be in the form of [insert either “a Bank Guarantee” or “a Conditional Bank Guarantee”] as per the forms included in Section IX, Contract Forms. |
| PC 13.3.3 | [The following provision shall be used if appropriate for the type of Facilities.] The Performance Security shall not be reduced on the date of the Operational Acceptance. |
| PC 22. Installation |  |
| PC 22.2.5 | Working Hours Normal working hours are: [insert normal working hours] |
| PC 22.2.8 | Funeral Arrangements: [insert any other specific arrangements] |
| PC 25. Commissioning and Operational Acceptance |  |
| PC 25.2.2 | The Guarantee Test of the Facilities shall be successfully completed within [insert number of days, written in words and figures] from the date of Completion. [Parts and separate times for the respective Guarantee Test shall be specified where applicable.] |
| PC 26. Completion Time Guarantee |  |
| PC 26.2 | Applicable rate for liquidated damages: [insert a percentage of the Contract Price, or part thereof, in words and figures. The applicable rate should be 0.1% per 1-day delay, 0.5% per 1-week delay] Maximum deduction for liquidated damages: [insert a percentage of the Contract Price. The maximum shall not exceed ten percent (10%) of the Contract Price]. |
| PC 26.3 | Applicable (amount or rate) for the bonus for early Completion: [insert appropriate amount or rate as a percentage of the Contract Price, or part thereof, in words and figures, per week of early Completion of the Facilities or part thereof, in accordance with the Time for Completion specified in PC 8.2. ] Maximum bonus: [insert the maximum amount which should be related to the benefit the Employer will gain in operating the Facilities, or part thereof, earlier than anticipated.] [For a Contract without a bonus, the following provision should be used.] No bonus will be given for earlier Completion of the Facilities or part thereof. |
| PC 30. Limitation of Liability |  |
| PC 30.1 (b) | [Use the following provision only if the aggregate liability is different from the total Contract Price; otherwise delete the provision.] The multiplier of the Contract Price is: [insert multiplier] |
| PC 45. Disputes and Arbitration |  |
| PC 45.1 | The DB shall be appointed within 28 days after the Effective Date. The DB shall be [insert either “one sole member” or “a DB of three members”.] List of potential DB members is: [insert names of potential members, if no list is available, delete the provision] |
| PC 45.2 | Appointment (if not agreed) to be made by: [insert appointing entity or official]. |

Section IX. Contract Forms

Notes on Contract Forms

This Section contains the Letter of Acceptance, the Contract Agreement and Appendices to the Contract Agreement which, once completed, will form part of the Contract.

The Letter of Acceptance will be the basis for formation of the Contract. The Standard Form should be filled in and sent to the successful Bidder only after evaluation of Bids has been completed, subject to concurrence by JICA.

Table of Forms

Notification of Award - Letter of Acceptance	1

Contract Agreement	1

Contract Agreement	1

Appendix 1.  Terms and Procedures of Payment	1

Appendix 2.  Price Adjustment	1

Appendix 3.  Insurance Requirements	1

Appendix 4.  Time Schedule	1

Appendix 5.  List of Major Items of Plant and Installation Services and List of Approved Subcontractors	1

Appendix 6.  Scope of Works and Supply by the Employer	1

Appendix 7.  List of Documents for Approval or Review	1

Appendix 8.  Functional Guarantees	1

Performance Security Form - Bank Guarantee	1

Performance Security Form - Conditional Bank Guarantee	1

Bank Guarantee Form for Advance Payment	1

Notification of Award - Letter of Acceptance

[on letterhead paper of the Employer]

[insert date]

To:   [insert name and address of the Contractor]

Subject: Notification of Award Contract No.___

This is to notify you that your Bid dated [insert date] for execution of the [insert name of the Contract and identification number] for the Contract Price in the aggregate of [insert amount in words and figures] [insert name of currency], as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are requested to furnish the Performance Security within twenty-eight (28) days in accordance with the Conditions of Contract, using for that purpose one of the Performance Security Forms included in Section IX, Contract Forms, of the Bidding Documents.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

Attachment:  Contract Agreement

[To be used in case of Single-Stage Bidding procedure.]

Contract Agreement

THIS AGREEMENT is made the ________ day of ________________________, _____,

BETWEEN

(1) _________[insert name of Employer], a corporation incorporated under the laws of __________[insert country of Employer] and having its principal place of business at __________[insert address of Employer] (hereinafter called “the Employer”), and (2) __________[insert name of Contractor], a corporation incorporated under the laws of __________[insert country of Contractor] and having its principal place of business at __________[insert address of Contractor] (hereinafter called “the Contractor”).

WHEREAS the Employer desires to engage the Contractor to design, manufacture, test, deliver, install, complete and commission certain Facilities, viz. ___________[insert list of Facilities] (hereinafter called “the Facilities”), and the Contractor has agreed to such engagement upon and subject to the terms and conditions hereinafter appearing.

NOW IT IS HEREBY AGREED as follows:

| Article 1. Contract Documents | 1.1 Contract Documents (Reference General Conditions (“GC”) Clause 2) The following documents shall constitute the Contract between the Employer and the Contractor, and each shall be read and construed as an integral part of the Contract: (a) This Contract Agreement and the Appendices hereto (b) Letter of Technical Bid (c) Letter of Price Bid (d) Particular Conditions (e) General Conditions (f) Employer’s Requirements (g) Other completed Bidding Forms submitted with the Bid (h) Acknowledgment of Compliance with Guidelines for Procurement under Japanese ODA Loans (i) [Any other documents shall be added here] 1.2 Order of Precedence (Reference GC Clause 2) In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above. 1.3 Definitions (Reference GC Clause 1) Capitalized words and phrases used herein shall have the same meanings as are ascribed to them in the General Conditions. |
| --- | --- |
| Article 2. Contract Price and Terms of Payment | 2.1 Contract Price (Reference GC Clause 11) The Employer hereby agrees to pay to the Contractor the Contract Price in consideration of the performance by the Contractor of its obligations hereunder. The Contract Price shall be the aggregate of: ________[insert amount(s) in foreign currency(ies) in words and figures] as specified in Price Schedule No. 6 (Grand Summary), and________[insert amount in local currency in words and figures], or such other sums as may be determined in accordance with the terms and conditions of the Contract. 2.2 Terms of Payment (Reference GC Clause 12) The Contract Price shall be paid by the Employer to the Contractor at the times, in the manner, and in accordance with the provisions of Appendix 1 (Terms and Procedures of Payment) hereto. The Employer shall instruct its bank to issue an irrevocable confirmed documentary credit made available to the Contractor in a bank in the country of the Contractor. The credit shall be for an amount of ___________[insert amount equal to the total named in Schedule 1 less the advance payment to be made for Plant and Equipment supplied from abroad]; and shall be subject to the Uniform Customs and Practice for Documentary Credits 1993 Revision, ICC Publication No. 600. In the event that the amount payable under Schedule No. 1 is adjusted in accordance with GC 11.2 or with any of the other terms of the Contract, the Employer shall arrange for the documentary credit to be amended accordingly. |
| Article 3. Effective Date | 3.1 Effective Date (Reference GC Clause 1) The Effective Date from which the Time for Completion of the Facilities shall be counted is the date when this Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor. The Employer undertakes to ensure that the conditions listed below in this Article 3 (Effective Date) shall all have been fulfilled within [insert number of months, normally two (2) months] after such Effective Date: [Conditions: List any applicable conditions. If no conditions are required to be fulfilled, delete all of Article 3, except for the first sentence.] |
| Article 4. Communications | 4.1 The address of the Employer for notice purposes, pursuant to GC Clause 4.1 is: ________ [insert Employer’s address]. - The address of the Contractor for notice purposes, pursuant to GC Clause 4.1 is: __________ [insert Contractor’s address]. |
| Article 5. Appendices | 5.1 The Appendices listed in the attached List of Appendices shall be deemed to form an integral part of this Contract Agreement. - Reference in the Contract to any Appendix shall mean the Appendices attached hereto, and the Contract shall be read and construed accordingly. |

IN WITNESS WHEREOF the Employer and the Contractor have caused this Agreement to be duly executed by their duly authorized representatives the day and year first above written.

Signed by, for and on behalf of the Employer

[Signature]

[Title]

in the presence of

Signed by, for and on behalf of the Contractor

[Signature]

[Title]

in the presence of

APPENDICES

Appendix 1	Terms and Procedures of Payment

Appendix 2	Price Adjustment

Appendix 3	Insurance Requirements

Appendix 4	Time Schedule

Appendix 5	List of Major Items of Plant and Installation Services and List of Approved Subcontractors

Appendix 6	Scope of Works and Supply by the Employer

Appendix 7	List of Documents for Approval or Review

Appendix 8	Functional Guarantees

[To be used in case of Two-Stage Bidding procedure]

Contract Agreement

THIS AGREEMENT is made the ________ day of ________________________, _____,

BETWEEN

(1) _________[insert name of Employer], a corporation incorporated under the laws of __________[insert country of Employer] and having its principal place of business at __________[insert address of Employer] (hereinafter called “the Employer”), and (2) __________[insert name of Contractor], a corporation incorporated under the laws of __________[insert country of Contractor] and having its principal place of business at __________[insert address of Contractor] (hereinafter called “the Contractor”).

WHEREAS the Employer desires to engage the Contractor to design, manufacture, test, deliver, install, complete and commission certain Facilities, viz. ___________[insert list of Facilities] (hereinafter called “the Facilities”), and the Contractor has agreed to such engagement upon and subject to the terms and conditions hereinafter appearing.

NOW IT IS HEREBY AGREED as follows:

| Article 1. Contract Documents | 1.1 Contract Documents (Reference General Conditions (“GC”) Clause 2) The following documents shall constitute the Contract between the Employer and the Contractor, and each shall be read and construed as an integral part of the Contract: (a) This Contract Agreement and the Appendices hereto (b) Letter of Second Stage Bid (c) Particular Conditions (d) General Conditions (e) Employer’s Requirements (f) Other completed Bidding Forms submitted with the Bid (g) Acknowledgment of Compliance with Guidelines for Procurement under Japanese ODA Loans (h) [Any other documents shall be added here] 1.2 Order of Precedence (Reference GC Clause 2) In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above. 1.3 Definitions (Reference GC Clause 1) Capitalized words and phrases used herein shall have the same meanings as are ascribed to them in the General Conditions. |
| --- | --- |
| Article 2. Contract Price and Terms of Payment | 2.1 Contract Price (Reference GC Clause 11) The Employer hereby agrees to pay to the Contractor the Contract Price in consideration of the performance by the Contractor of its obligations hereunder. The Contract Price shall be the aggregate of: ________ [insert amount(s) in foreign currency(ies) in words and figures] as specified in Price Schedule No. 6 (Grand Summary), and________ [insert amount in local currency in words and figures], or such other sums as may be determined in accordance with the terms and conditions of the Contract. 2.2 Terms of Payment (Reference GC Clause 12) The Contract Price shall be paid by the Employer to the Contractor at the times, in the manner, and in accordance with the provisions of Appendix 1 (Terms and Procedures of Payment) hereto. The Employer shall instruct its bank to issue an irrevocable confirmed documentary credit made available to the Contractor in a bank in the country of the Contractor. The credit shall be for an amount of ___________ [insert amount equal to the total named in Schedule 1 less the advance payment to be made for Plant and Equipment supplied from abroad]; and shall be subject to the Uniform Customs and Practice for Documentary Credits 1993 Revision, ICC Publication No. 600. In the event that the amount payable under Schedule No. 1 is adjusted in accordance with GC 11.2 or with any of the other terms of the Contract, the Employer shall arrange for the documentary credit to be amended accordingly. |
| Article 3. Effective Date | 3.1 Effective Date (Reference GC Clause 1) The Effective Date from which the Time for Completion of the Facilities shall be counted is the date when this Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor. The Employer undertakes to ensure that the conditions listed below in this Article 3 (Effective Date) shall all have been fulfilled within [insert number of months, normally two (2) months] after such Effective Date: [Conditions: List any applicable conditions. If no conditions are required to be fulfilled, delete all of Article 3, except for the first sentence.] |
| Article 4. Communications | 4.1 The address of the Employer for notice purposes, pursuant to GC Clause 4.1 is: ________ [insert Employer’s address]. - The address of the Contractor for notice purposes, pursuant to GC Clause 4.1 is: __________ [insert Contractor’s address]. |
| Article 5. Appendices | 5.1 The Appendices listed in the attached List of Appendices shall be deemed to form an integral part of this Contract Agreement. - Reference in the Contract to any Appendix shall mean the Appendices attached hereto, and the Contract shall be read and construed accordingly. |

IN WITNESS WHEREOF the Employer and the Contractor have caused this Agreement to be duly executed by their duly authorized representatives the day and year first above written.

Signed by, for and on behalf of the Employer

[Signature]

[Title]

in the presence of

Signed by, for and on behalf of the Contractor

[Signature]

[Title]

in the presence of

APPENDICES

Appendix 1	Terms and Procedures of Payment

Appendix 2	Price Adjustment

Appendix 3	Insurance Requirements

Appendix 4	Time Schedule

Appendix 5	List of Major Items of Plant and Installation Services and List of Approved Subcontractors

Appendix 6	Scope of Works and Supply by the Employer

Appendix 7	List of Documents for Approval or Review

Appendix 8	Functional Guarantees

Appendix 1.  Terms and Procedures of Payment

[The following Terms and Procedures of Payment are given as a guideline suitable for Supply and Installation Contracts.  In the event that the Employer wishes to introduce different terms of payment to the following, it shall first obtain the written concurrence of JICA for the terms it intends to use.  If additional Price Schedules are introduced, suitable terms of payment in respect of such additional schedules must be added.]

In accordance with the provisions of GC Clause 12 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on Price Schedules.  Payments will be made in the currencies quoted by the Bidder.  Applications for payment in respect of part deliveries may be made by the Contractor as work proceeds.

TERMS OF PAYMENT

Schedule No. 1.  Plant and Equipment Supplied from Abroad

In respect of plant and equipment supplied from abroad, the following payments shall be made:

Ten percent (10%) of the total CIP amount as an advance payment within twenty-one (21) days after receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.  The advance payment security may be reduced in proportion to the value of the plant and equipment delivered to the site, as evidenced by shipping and delivery documents.

Eighty percent (80%) of the total or pro rata CIP amount upon Incoterm “CIP”, upon delivery to the carrier within forty-five (45) days after receipt of invoice and documents. [Employer to state the required documents, such as a negotiable bill of lading, a non-negotiable sea way bill, an airway will, a railway consignment note, a road consignment note, insurance certificate, etc.]

Five percent (5%) of the total or pro rata CIP amount upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice.

Five percent (5%) of the total or pro rata CIP amount upon issue of the Operational Acceptance Certificate, within forty-five (45) days after receipt of invoice.

Schedule No. 2.  Plant and Equipment Supplied from within the Employer’s Country

In respect of plant and equipment supplied from within the Employer’s country, the following payments shall be made:

Ten percent (10%) of the total EXW amount as an advance payment within twenty-one (21) days after receipt of invoice, and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.  The advance payment security may be reduced in proportion to the value of the plant and equipment delivered to the site, as evidenced by shipping and delivery documents.

Eighty percent (80%) of the total or pro rata EXW amount upon Incoterm “Ex-Works,” upon delivery to the carrier within forty-five (45) days after receipt of invoice and documents. [Employer to state the required documents, such as a railway consignment note, a road consignment note, insurance certificate, etc.]

Five percent (5%) of the total or pro rata EXW amount upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice.

Five percent (5%) of the total or pro rata EXW amount upon issue of the Operational Acceptance Certificate, within forty-five (45) days after receipt of invoice.

Schedule No. 3.  Design Services

In respect of design services for both the foreign currency and the local currency portions, the following payments shall be made:

Ten percent (10%) of the total design services amount as an advance payment within twenty-one (21) days after receipt of invoice, and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.

Ninety percent (90%) of the total or pro rata design services amount upon approval of design in accordance with GC Clause 20 by the Project Manager within forty-five (45) days after receipt of invoice.

Schedule No. 4.  Installation Services

In respect of installation services for both the foreign and local currency portions, the following payments shall be made:

Ten percent (10%) of the total installation services amount as an advance payment within twenty-one (21) days after receipt of invoice, and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.  The advance payment security may be reduced in proportion to the value of work performed by the Contractor as evidenced by the invoices for installation services.

Eighty percent (80%) of the measured value of work performed by the Contractor, as identified in the said Program of Performance, during the preceding month, as evidenced by the Employer’s authorization of the Contractor’s application, will be made monthly within forty-five (45) days after receipt of invoice.

Five percent (5%) of the total or pro rata value of installation services performed by the Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly applications, upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice.

Five percent (5%) of the total or pro rata value of installation services performed by the Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly applications, upon issue of the Operational Acceptance Certificate, within forty-five (45) days after receipt of invoice.

In the event that the Employer fails to make any payment on its respective due date, the Employer shall pay to the Contractor interest on the amount of such delayed payment at the rate of _____ [insert a percentage to be calculated at the annual rate of three (3) percentage points above the discount rate of the central bank in the country of the currency(ies) of payment, or if not available, the interbank offered rate] percent ( __%) per month for period of delay until payment has been made in full.

PAYMENT PROCEDURES

The procedures to be followed in applying for certification and making payments shall be as follows:

______________________________________________________________________________________________________________________________________________________

[Insert appropriate procedures, usually Letters of Credit, including forms and certificates annexed as appropriate by the Employer in the Bidding Documents.]

Appendix 2.  Price Adjustment

Where the Contract Period (excluding the Defects Liability Period) exceeds eighteen (18) months, it is normal procedure that prices payable to the Contractor shall be subject to adjustment during the performance of the Contract to reflect changes occurring in the cost of labor and material components. In such cases the Bidding Documents shall include in this Appendix 2 a formula of the following general type, pursuant to GC Sub-Clause 11.2. Where Contracts are of a shorter duration than eighteen (18) months, the following provision shall not be included. Instead, it shall be indicated under this Appendix 2 that the prices are to remain firm and fixed for the duration of the Contract. This Appendix 2. Price Adjustment shall be the same as the Price Adjustment Form in Section IV, Bidding Forms of the Bidding Documents. The formula, indices and coefficients shall be agreed at Contract Negotiations between the Employer and the awarded Contractor.

Sample Price Adjustment Formula

Prices payable to the Contractor, in accordance with the Contract, shall be subject to adjustment during performance of the Contract to reflect changes in the cost of labor and material components, in accordance with the following formula:

P1=P0´(a+bL1L0+cM1M0)−P0

in which:

P1	=	adjustment amount payable to the Contractor

P0	=	Contract Price (base price)

a	=	percentage of fixed element in Contract Price (a =   %)

b	=	percentage of labor component in Contract Price (b =  %)

c	=	percentage of material and equipment component in Contract Price (c =  %)

L0, M0	=	labor and material/equipment component indices or reference prices in the country of origin on the Base Date

L1, M1=	labor and material/equipment component indices applicable to the appropriate industry in the country of origin on the date of adjustment, for adjustments related to Plant and components supplied under Schedules No.1, No.2 and No.3; and, in case of adjustment for Installation Services provided under Schedule No.4, indices or reference prices applicable to the appropriate industry in the country of origin on the month the Installation Services were provided.

N.B.  a+b+c= 100%.

[The Bidder shall propose the coefficients b and c in its Bid. The formula, including all coefficients, shall be determined and finalized at Contract negotiations.]

Conditions Applicable To Price Adjustment

The Bidder shall indicate the source of labor and materials indices and the base date indices in its Bid.

| Item | Source of Indices Used | Base Date Indices |
| --- | --- | --- |

The base date shall be the date twenty-eight (28) days prior to: [insert “the Bid submission deadline” or “the submission deadline for Second Stage Bids”, as appropriate].

For Plant or components supplied under Schedules No.1, No.2 and No.3, the date of adjustment shall be the mid-point of the sequences shown in the Program of Performance submitted by the Bidder, pursuant to GC 18.2, for design or manufacture of the Plant or components.

In respect of Installation Services provided under Schedule No.4, the adjustment shall apply to the monthly measured value of work performed by the Contractor during the preceding month. The adjustment shall be made monthly to the payments for Installation Services effected as provided in Appendix 1 of the Contract Agreement.

The following conditions shall apply:

(a)	No price increase will be allowed beyond the original delivery date unless covered by an extension of time awarded by the Employer under the terms of the Contract.  No price increase will be allowed for periods of delay for which the Contractor is responsible.  The Employer will, however, be entitled to any price decrease occurring during such periods of delay;

(b)	If the currency in which the Contract Price, P0, is expressed is different from the currency of the country of origin of the labor and/or materials indices, a correction factor will be applied to avoid incorrect adjustments of the Contract Price.  The correction factor shall correspond to the ratio of exchange rates between the two currencies on the base date and the date for adjustment as defined above; and

(c)	No price adjustment shall be payable on the portion of the Contract Price paid to the Contractor as an advance payment.

[For complex Plant and Installation Services involving several sources of supply and/or a substantial amount of installation works, a family of formulas may be necessary, with provision for the usage of Contractor’s equipment in the works formula.]

Appendix 3.  Insurance Requirements

[Details to be completed by the Employer prior to issuing the Bidding Documents.  In the event that the Employer provides any insurance under the Contract, appropriate details must also be given.]

Insurances to be Taken Out by the Contractor

In accordance with the provisions of GC Clause 34, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified.  The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, such approval not to be unreasonably withheld.

(a)	Cargo Insurance

Covering loss or damage occurring, while in transit from the supplier’s or manufacturer’s works or stores until arrival at the Site, to the Facilities (including spare parts therefore) and to the construction equipment to be provided by the Contractor or its Subcontractors.

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

(b)	Installation All Risks Insurance

Covering physical loss or damage to the Facilities at the Site, occurring prior to Operational Acceptance of the Facilities, with an extended maintenance coverage for the Contractor’s liability in respect of any loss or damage occurring during the defect liability period while the Contractor is on the Site for the purpose of performing its obligations during the defect liability period.

| Amount | Deductible limits | Parties insured |
| --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] |

(c)	Third Party Liability Insurance

Covering bodily injury or death suffered by third parties (including the Employer’s Personnel) and loss of or damage to property (including the Employer’s property and any parts of the Facilities that have been accepted by the Employer) occurring in connection with the supply and installation of the Facilities.

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

(d)	Automobile Liability Insurance

Covering use of all vehicles used by the Contractor or its Subcontractors (whether or not owned by them) in connection with the supply and installation of the Facilities.  Comprehensive insurance in accordance with statutory requirements.

(e)	Workers’ Compensation

In accordance with the statutory requirements applicable in any country where the Facilities or any part thereof is executed.

(f)	Employer’s Liability

In accordance with the statutory requirements applicable in any country where the Facilities or any part thereof is executed.

(g)	Other Insurances

The Contractor is also required to take out and maintain at its own cost the following insurances:

Details:

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 34.1, except for the Workers’ Compensation and Employer’s Liability Insurances, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 34.1, except for the Cargo, Workers’ Compensation and Employer’s Liability Insurances.  All insurer’s rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies.

Insurances To Be Taken Out By The Employer

[If the Employer is proposing to take out any or all of the above insurances itself, or any other insurances in respect of the Facilities, either in its own name or in the joint names of itself and the Contractor, it shall give details below prior to issuing the Bidding Documents. Under the terms of the Contract, the Contractor and the Contractor’s Subcontractors shall be named as co-insured under all such policies.]

The Employer shall at its expense take out and maintain in effect during the performance of the Contract the following insurances.

Details:

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

Appendix 4.  Time Schedule

[The Employer should normally provide a Time Schedule to be followed by the Contractor during the performance of the Contract. This schedule should be provided with the Bidding Documents under this Appendix. All completion times indicated must be in accordance with the information regarding Time(s) for Completion given in the Bid Data Sheet.

Except under exceptional circumstances, the Time Schedule should indicate periods of time (e.g., weeks or months) and not specify calendar dates. All periods should be shown from the Effective Date of the Contract.

Should it become necessary to amend the Time Schedule to reflect any agreements made with the selected Bidder prior to award of Contract, the amended Time Schedule shall replace the original Time Schedule prior to signature of the Contract Agreement.

If the Bidding Documents contain no Time Schedule, the Bidder shall be required to submit with its Bid a detailed program, normally in the form of a bar chart, showing how and the order in which it intends to perform the Contract and showing the key events requiring action or decision by the Employer. In preparing this Program, the Bidder shall adhere to the Time(s) for Completion given in the Bid Data Sheet or give its reasons for not adhering thereto. The Time Schedule submitted by the selected Bidder and amended as necessary prior to award of Contract shall be included as Appendix to the Contract Agreement before the Contract is signed.]

Appendix 5.  List of Major Items of Plant and Installation Services and List of Approved Subcontractors

[Prior to issuing the Bidding Documents, the Employer has established a list of major item of Plant and Installation Services for which approval of the Employer is required.  Prior to award of Contract, the details of approved Subcontractors, including manufacturers shall be completed, indicating those Subcontractors proposed by the Bidder in the corresponding Attachment to its Bid that are approved by the Employer for engagement by the Contractor during the performance of the Contract.]

A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or manufacturers are approved for carrying out the items of the Facilities indicated below.  Where more than one Subcontractor are listed, the Contractor is free to choose between them, but it must notify the Employer of its choice in good time prior to appointing any selected Subcontractor.  In accordance with GC Sub-Clause 19.1, the Contractor is free to submit proposals for Subcontractors for additional items from time to time.  No Subcontracts shall be placed with any such Subcontractors for additional items until the Subcontractors have been approved in writing by the Employer and their names have been added to this list of Approved Subcontractors.

| Major Items of Plant and Installation Services | Approved Subcontractors/Manufacturers | Nationality |
| --- | --- | --- |

Appendix 6.  Scope of Works and Supply by the Employer

[Prior to issuing the Bidding Documents, the Employer shall indicate in this Appendix details of all Personnel and Facilities it will provide for use by the Contractor and indicate, where applicable, the charges that it will make in respect of their use.

The Employer shall also identify any part(s) of the facilities it intends to carry out itself (or by other contractors), and any plant, equipment or materials that it proposes to purchase itself and supply to the Contractor for incorporation in the facilities, indicating, where applicable, the charges that it will make in respect thereof.]

The following Personnel, Facilities, works and supplies will be provided/supplied by the Employer, and the provisions of GC Clauses 10, 21 and 24 shall apply as appropriate.

All Personnel, Facilities, works and supplies will be provided by the Employer in good time so as not to delay the performance of the Contractor, in accordance with the approved Time Schedule and Program of Performance pursuant to GC Sub-Clause 18.2.

Unless otherwise indicated, all Personnel, Facilities, works and supplies will be provided free of charge to the Contractor.

| Personnel | Charge to Contractor (if any) |
| --- | --- |

| Facilities | Charge to Contractor (if any) |
| --- | --- |

| Works | Charge to Contractor (if any) |
| --- | --- |

| Supplies | Charge to Contractor (if any) |
| --- | --- |

Appendix 7.  List of Documents for Approval or Review

Pursuant to GC Sub-Clause 20.3.1, the Contractor shall prepare, or cause its Subcontractor to prepare, and present to the Project Manager in accordance with the requirements of GC Sub-Clause 18.2 (Program of Performance), the following documents for

A.	Approval

1.

2.

3.

B.	Review

1.

2.

3.

Appendix 8.  Functional Guarantees

1.	General

This Appendix sets out:

(a)	the functional guarantees referred to in GC Clause 28 (Functional Guarantees);

(b)	the preconditions to the validity of the functional guarantees, either in production and/or consumption, set forth below;

(c)	the minimum level of the functional guarantees; and

(d)	the formula for calculation of liquidated damages for failure to attain the functional guarantees.

2.	Preconditions

The Contractor gives the functional guarantees (specified herein) for the facilities, subject to the following preconditions being fully satisfied:

[List any conditions for the carrying out of the Guarantee Test referred to in GC Clause 25.2.]

3.	Functional Guarantees

Subject to compliance with the foregoing preconditions, the Contractor guarantees are as follows:

3.1	Production Capacity: [List here the production capacity that the Contractor is to guarantee, making sure to use, as functional guarantees, the figures offered by the Contractor in its Bid]

and/or

3.2	Raw Materials and Utilities Consumption: [List here the guaranteed items of consumption per unit of production (e.g., kg, tons, kcal, kWh, etc.) that the Contractor is to guarantee, making sure to use, as functional guarantees, the figures offered by the Contractor in its Bid]

4.	Failure in Guarantees and Liquidated Damages

4.1	Failure to Attain Guaranteed Production Capacity

If the production capacity of the facilities attained in the guarantee test, pursuant to GC Sub-Clause 25.2, is less than the guaranteed figure specified in para. 3.1 above, but the actual production capacity attained in the guarantee test is not less than the minimum level specified in para. 4.3 below, and the Contractor elects to pay liquidated damages to the Employer in lieu of making changes, modifications and/or additions to the Facilities, pursuant to GC Sub-Clause 28.3, then the Contractor shall pay liquidated damages at the rate of [insert amount in the Contract currency(ies)] for every complete one percent (1%) of the deficiency in the production capacity of the Facilities, or at a proportionately reduced rate for any deficiency, or part thereof, of less than a complete one percent (1%).

4.2	Raw Materials and Utilities Consumption in Excess of Guaranteed Level

[To be specified in the appropriate wording for the type of Facilities, if there are consumption guarantees.]

If the actual measured figure of specified raw materials and utilities consumed per unit (or their average total cost of consumption) exceeds the guaranteed figure specified in para. 3.2 above (or their specified average total cost of consumption), but the actual consumption attained in the guarantee test, pursuant to GC Sub-Clause 25.2, is not more than the maximum level specified in para. 4.3 below, and the Contractor elects to pay liquidated damages to the Employer in lieu of making changes, modifications and/or additions to the Facilities pursuant to GC Sub-Clause 28.3, then the Contractor shall pay liquidated damages at the rate of [amount in the Contract currency(ies)] for every complete one percent (1%) of the excess consumption of the Facilities, or part thereof, of less than a complete one percent (1%).

[The rate of liquidated damages specified in paras. 4.1 and 4.2 above shall be at least equivalent to the rate specified in Section III, Evaluation and Qualification Criteria for the comparison of functional guarantees provided by the Bidders.]

4.3	Minimum Levels

Notwithstanding the provisions of this paragraph, if as a result of the guarantee test(s), the following minimum levels of performance guarantees (and consumption guarantees) are not attained by the Contractor, the Contractor shall at its own cost make good any deficiencies until the Facilities reach any of such minimum performance levels, pursuant to GC Sub-Clause 28.2:

(a)	production capacity of the Facilities attained in the guarantee test:  ninety-five percent (95%) of the guaranteed production capacity (the values offered by the Contractor in its Bid for functional guarantees represents 100%);

and/or

(b)	average total cost of consumption of all the raw materials and utilities of the Facilities:  one hundred and five percent (105%) of the guaranteed figures (the figures offered by the Contractor in its Bid for functional guarantees represents 100%).

4.4	Limitation of Liability

Subject to para. 4.3 above, the Contractor’s aggregate liability to pay liquidated damages for failure to attain the functional guarantees shall not exceed [insert percentage in words and figures (the percentage specified shall not exceed ten percent (10%) of the Contract Price)] ______ percent ( ___ %) of the Contract Price.

Performance Security Form - Bank Guarantee

[Guarantor letterhead or SWIFT identifier code]

Beneficiary: [insert name and address of Employer]

Date: [insert date of issue]

PERFORMANCE GUARANTEE No.: [insert guarantee reference number]

Guarantor: [insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture] (hereinafter called “the Applicant”) has entered into Contract No. [insert reference number of the Contract] dated [insert date] with the Beneficiary, for the execution of [insert name of Contract and brief description of Facilities]_ (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in words] ([insert amount in figures]), such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its obligation(s) under the Contract, without the Beneficiary needing to prove or to show grounds for its demand or the sum specified therein.

This guarantee shall be reduced by half upon our receipt of:

(a) 	a copy of the Operational Acceptance Certificate; or

(b) 	a registered letter from the Applicant (i) attaching a copy of its notice requesting issuance of the Operational Acceptance Certificate and (ii) stating that the Project Manager has failed to issue such Certificate within the time required or provide in writing justifiable reasons why such Certificate has not been issued, so that Operational Acceptance is deemed to have occurred.

This guarantee shall expire no later than the earlier of:

(a) 	twelve (12) months after our receipt of either (a) or (b) above; or

(b) 	the ____ day of _____, 2___.

Consequently, any demand for payment under this guarantee must be received by the Guarantor at its office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458, except that subparagraph (ii) of Sub-article 20(a) is hereby excluded.

_____________________ 
[signature(s)]

[Note:  All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]

Performance Security Form - Conditional Bank Guarantee

Date:	[insert date]

Loan Agreement No:	[insert number]

IFB No:	[insert number]

____________________________

To: ___________________________________

Dear Ladies and/or Gentlemen,

We refer to the Contract Agreement (“the Contract”) signed on [date] between you and ___________ [name of Contractor] (hereinafter called “the Contractor”) concerning design, execution and completion of _______________ [insert brief description of Facilities].

By this letter we, the undersigned, [insert name of Bank], a Bank (or company) organized under the laws of _________[insert country of Bank] and having its registered/principal office at _____[insert address of Bank], do hereby jointly and severally with the Contractor irrevocably guarantee payment owed to you by the Contractor, pursuant to the Contract, up to the sum of ___________[insert amount], equivalent to ________[insert number]  percent (  %) [amount shall not exceed fifteen percent (15%) in any case] of the Contract Price until the date of the Operational Acceptance Certificate and thereafter up to a sum of ____________[insert amount], equivalent to_____ [insert number] percent (  %) [amount shall not exceed half the percentage stated above, or the same percentage, if the security is not reduced by half pursuant to PC 13.3.3] of the Contract Price, until twelve (12) months after the date of Operational Acceptance.

Where it is agreed between you and the Contractor that the Facilities are to be accepted in parts, and thus where there are separate Completion and Operational Acceptance Certificates for each part, this Letter of Guarantee shall be apportioned to the value of each such part and shall reduce or expire as provided above on or following Completion or Operational Acceptance of each part.

We shall only undertake to make payment under this Letter of Guarantee upon our receipt of a written demand signed by your duly authorized officer for a specified sum, where such demand sets out the reasons for your claim under this Letter of Guarantee and is accompanied by:

(a)	a copy of the written notice sent by you to the Contractor before making the claim under this Guarantee, specifying the Contractor’s breach of contract and requesting the Contractor to remedy it;

(b)	a letter signed by your duly authorized officer certifying that the Contractor has failed to remedy the default within the period allowed for remedial action; and

(c)	a copy of your written notice to the Contractor stating your intent to claim under this Letter of Guarantee because of the Contractor’s failure to remedy the default in accordance with the request referred to in para. (a) above.

Our liability under this Letter of Guarantee shall be to pay to you whichever is the lesser of the sum so requested or the amount then guaranteed hereunder in respect of any demand duly made hereunder prior to expiry of this Letter of Guarantee, without being entitled to inquire whether or not this payment is lawfully demanded.

This Letter of Guarantee shall be valid from the date of issue until the earlier of twelve (12) months after the date of Operational Acceptance or, where the Facilities are to be accepted in parts, twelve (12) months after the date of Operational Acceptance of the last part or [insert date], whichever comes first.

Except for the documents herein specified, no other documents or other action shall be required, notwithstanding any applicable law or regulation.

If the Defect Liability Period is extended with respect to any part of the Facilities in accordance with the Contract, you shall notify us, and the validity of this Letter of Guarantee shall be extended with respect to the percentage of the Contract Price stipulated in the notification until expiry of such extended Defect Liability Period.

Our liability under this Letter of Guarantee shall become null and void immediately upon its expiry, whether it is returned or not, and no claim may be made hereunder after such expiry or after the aggregate of the sums paid by us to you shall equal the sums guaranteed hereunder, whichever is the earlier.

All notices to be given hereunder shall be given by registered (airmail) post to the addressee at the address herein set out or as otherwise advised by and between the Parties hereto.

We hereby agree that any part of the Contract may be amended, renewed, extended, modified, compromised, released or discharged by mutual agreement between you and the Contractor, and this security may be exchanged or surrendered without in any way impairing or affecting our liabilities hereunder without notice to us and without the necessity for any additional endorsement, consent or guarantee by us, provided, however, that the sum guaranteed shall not be increased or decreased.

No action, event or condition which by any applicable law should operate to discharge us from liability hereunder shall have any effect and we hereby waive any right we may have to apply such law, so that in all respects our liability hereunder shall be irrevocable and, except as stated herein, unconditional in all respects.

Yours truly,

Authorized Signature

Bank Guarantee Form for Advance Payment

[Guarantor letterhead or SWIFT identifier code]

Beneficiary: [insert name and address of the Employer]

Date: [insert date of issue]_____________

ADVANCE PAYMENT GUARANTEE No.: [insert guarantee reference number]

Guarantor: [insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture] (hereinafter called “the Applicant”) has entered into Contract No.[insert reference number of the Contract] dated [insert date] with the Beneficiary, for the execution of [insert name of Contract and brief description of Facilities]  (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum of [insert amount in words] ([insert amount in figures]) is to be made against an advance payment guarantee.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in words]([insert amount in figures] ) upon receipt by us of the Beneficiary’s first demand in writing accompanied by a written statement stating that the Applicant is in breach of its obligation under the Contract because the Applicant used the advance payment for purposes other than toward the execution of the Works.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the advance payment referred to above has been credited to the Applicant on its account number [insert number] at  [insert name and address of Applicant’s bank].

The maximum amount of this guarantee shall be progressively reduced in proportion to the value of each part-shipment or part-delivery of plant and equipment to the site, as indicated in copies of the relevant shipping and delivery documents that shall be presented to the Guarantor.  This guarantee shall expire, at the latest, upon the Guarantor’s receipt of documentation indicating full repayment by the Applicant of the amount of the advance payment, or on the ___ day of _______, 2___, whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by the Guarantor at its office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458.

_____________________ 
[signature(s)]

[Note:  All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]

Notes

?	Substitute “has applied for,” if appropriate.

Substitute “contracts” where Bids are called concurrently for multiple contracts. Add a new para. 3 and renumber paras 3 - 6 as follows: “Bidders may bid for one or several contracts, as further defined in the Bidding Documents. Bidders wishing to offer discounts in case they are awarded more than one contract will be allowed to do so, provided those discounts are included in the Letter of Bid.”

The office for inquiry and issuance of the Bidding Documents and that for Bid submission may or may not be the same.

The fee, to defray printing and mailing/ shipping costs, should be nominal.

Substitute the Employer’s address for Bid submission if different from its address for inquiry and issuance of the Bidding Documents.

The time allowed for preparation of the Bid submission should be sufficient for Bidders to gather all the information required - preferably sixty (60) days, but in any case not less than forty-five (45) days after the date when the documents are available for distribution or the date of the advertisement, whichever is later.  This period may be longer for very large projects, where time should be allowed for the formation of joint ventures and assembly of the necessary resources, and/or scrutiny of the Bidding Documents.

Delete the request for a security when the Two-Stage Bidding procedure is used, as the security is requested in the Invitation for Second Stage Bids.

Substitute “has applied for,” if appropriate.

Substitute “contracts” where Bids are called concurrently for multiple contracts. Add a new para. 3 and renumber paras 3 - 6 as follows: “Bidders may bid for one or several contracts, as further defined in the Bidding Documents. Bidders wishing to offer discounts in case they are awarded more than one contract will be allowed to do so, provided those discounts are included in the Letter of Bid.”

The office for inquiry and issuance of Bidding Documents and that for Bid submission may or may not be the same.

The fee, to defray printing and mailing/ shipping costs, should be nominal.

Substitute the Employer’s address for Bid submission if different from its address for inquiry and issuance of Bidding Documents.

The time allowed for preparation of the Bid submission should be sufficient for Bidders to gather all the information required - preferably sixty (60) days, but in any case not less than forty-five (45) days after the date when the documents are available for distribution or the date of the advertisement, whichever is later.  This period may be longer for very large projects, where time should be allowed for the formation of joint ventures and assembly of the necessary resources, and/or scrutiny of the Bidding Documents.

Delete the request for a security when the Two-Stage Bidding procedure is used, as the security is requested in the Invitation for Second Stage Bids.

Notes

?     Amendment shall be common to all Bidders invited to submit a Second Stage Bid.

A copy of the respective Annex should be attached to the letter to the corresponding Bidder.

The dates of Bid submission and Bid opening should be the same, and the time should also be the same or immediately thereafter.

The period should be sufficient to permit completion of the Second Stage Bid evaluation, review of the recommended selection by JICA, obtainment of approvals and notification of award. A realistic period should be specified in order to avoid the need for Bid validity extension.

If the most recent set of financial statements is for a period earlier than 12 months from the date of Bid, the reason for this should be justified.

1 The starting date should be revised to “request for price quotation,” if the Borrower is selected through the International Shopping”; to "appointment", if a contractor is selected through the Direct Contracting; or “Commencement of actual selection/bidding process”, if the Borrower wishes to adopt procurement procedures other than ICB, Limited International Shopping, International Shopping, or Direct Contracting.

As the case may be, ICC Publication No. 758 (or subsequent ICC Publications) may be used. In such cases, modify the Publication number.

The amount of the Bond shall be denominated in the currency of the Employer’s country or the equivalent amount in a freely convertible currency.

Cost shall be in the currencies of the Contract.

Increase and/or decrease to the Contract Price shall be in the currencies of the Contract.

The Guarantor shall insert an amount representing the percentage of the Contract Price specified in the Letter of Acceptance and denominated either in the currency(ies) of the Contract or a freely convertible currency acceptable to the Beneficiary.

This text shall be revised as and where necessary to take into account (i) partial acceptance of the Facilities in accordance with GC Sub-Clause 25.4.

Insert the date twenty-eight (28) days after the expected expiration date of the Defect Liability Period. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [e.g. six months], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

As the case may be, ICC Publication No. 758 (or subsequent ICC Publications) may be used. In such cases, modify the Publication number.

The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.

Insert the expected expiration date of the Time for Completion.  The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee.  In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [e.g. six months], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

As the case may be, ICC Publication No. 758 (or subsequent ICC Publications) may be used. In such cases, modify the Publication number.