- BIDDING DOCUMENTS

for

- Procurement of

[insert identification of the Works] ___________________________

______________________________

Employer: [insert name of Employer]

Country: [insert name of Country]

Project: [insert name of Project]

Loan No.: [insert number of Loan Agreement]

Table of Contents

Invitation for Bids	IFB-1

PART 1 – Bidding Procedures

Section I.	Instructions to Bidders	ITB-1

Section II.	Bid Data Sheet	BDS-1

Section III.	Evaluation and Qualification Criteria	EQC-1

Section IV.	Bidding Forms	BF-1

Section V.	Eligible Source Countries of Japanese ODA Loans	ESC-1

PART 2 – Works Requirements

Section VI.	Works Requirements	WR-1

PART 3 – Conditions of Contract and Contract Forms

Section VII.	General Conditions (GC)	GC-1

Section VIII.	Particular Conditions (PC)	PC-1

Section IX.	Contract Forms	CF-1

Invitation for Bids

Notes on Invitation for Bids In case Bids are invited openly from contractors, the Invitation for Bids should be issued directly to the public (see the relevant Section of the Guidelines for Procurement under Japanese ODA Loans): (a) as an advertisement in at least one newspaper of general circulation in the Borrower’s country; and (b) with sending copies of the invitation to JICA. The Invitation for Bids provides information that enables potential Bidders to decide whether to participate. Apart from a summary description of the works, the Invitation for Bids should also indicate any important Bid evaluation criteria (for example, technical alternatives) or qualification requirement (for example, a requirement for a minimum level of experience in works similar to those for which the Invitation for Bids is issued). The Invitation for Bids should be consistent with the information contained in Section II, Bid Data Sheet.

Form of Invitation for Bids

Date: [date of issuance of IFB]

Loan Agreement No: [insert Loan Agreement number]

IFB No: [insert number of Invitation for Bids]

1.	The [insert name of Borrower] has received1 a loan from Japan International Cooperation Agency (JICA) towards the cost of [insert name of Project].  It is intended that part of the proceeds of this loan will be applied to eligible payments under the Contract2 for [insert title of Contract].

2.	Bidding will be conducted through procedures in accordance with the applicable Guidelines for Procurement under Japanese ODA Loans, and is open to all Bidders from eligible source countries, as defined in the Loan Agreement.

3.	The [insert name of the Employer] now invites sealed Bids from eligible Bidders for the construction and completion of [insert brief description of the works]3 (“the Works”).

4.	Interested eligible Bidders may obtain further information from and inspect the Bidding Documents at the office of [insert name of appropriate purchasing unit]4 [insert mailing address of appropriate office for inquiry and issuance of Bidding Documents  and/or facsimile numbers].

5.	A complete set of Bidding Documents may be purchased by interested Bidders on the submission of a written application to the address above and upon payment of a non-refundable fee of [insert amount in Borrower’s currency or in a convertible currency].5

6.	The provisions in the Instructions to Bidders and in the General Conditions of Contract are the provisions of the Standard Bidding Documents under Japanese ODA Loans for the Procurement of Small Works.

7.	Bids must be delivered to the address above6 on or before [insert time] on [insert date]7 and must be accompanied by a security of [insert fixed sum].

8.	Bids will be opened in the presence of Bidders’ representatives who choose to attend at [insert time and date] at the offices of [insert address of appropriate office].

[Insert name of office]

[Insert name of person in charge officer]

[Insert postal address] and/or [Insert street address]

[Insert telephone number, indicate country and city code]

[Insert facsimile number]

[Insert E-mail address]

Notes

1.	Substitute “has applied for,” if appropriate.

2.	Substitute “contracts” where Bids are called concurrently for multiple contracts. Add a new para. 4 and renumber paras 4 - 8 as follows: “Bidders may bid for one or several contracts, as further defined in the Bidding Documents. Bidders wishing to offer discounts in case they are awarded more than one contract will be allowed to do so, provided those discounts are included in the Letter of Bid.”

3.	A brief description of the Works or Goods should be provided, including quantities, location of project, and other information necessary to enable potential Bidders to decide whether or not to respond to the invitation. Bidding Documents may require Bidders to have specialized experience or capabilities; such requirements should also be included in this paragraph.

4.	The office for inquiry and issuance of Bidding Documents and that for Bid submission may or may not be the same.

5.	The fee, to defray printing and mailing/shipping costs, should be nominal.

6.	Substitute the Employer’s address for Bid submission if different from its address for inquiry and issuance of Bidding Documents.

7.	The time allowed for preparation of the Bid submission should be sufficient for Bidders to gather all the information required - preferably sixty (60) days, but in any case not less than forty-five (45) days after the date when the documents are available for distribution or the date of the advertisement, whichever is later.

PART 1 – Bidding Procedures

Section I.	Instructions to Bidders

Notes on Instructions to Bidders Section I, Instructions to Bidders, provides the information necessary for Bidders to prepare responsive Bids in accordance with the requirements of the Employer. It also gives information on Bid submission, opening, and evaluation, and on the award of the Contract. The use of the Standard Instructions to Bidders set forth in Section I of these Standard Bidding Documents for the Procurement of Small Works (version 1.0) published by JICA in April, 2013 (hereafter referred to as “Standard ITB”), in all Bidding Documents for small construction works financed by Japanese ODA Loans is required, and they shall be used without modification. Any necessary changes, acceptable to JICA, to address specific country and project issues, shall be introduced only through the Bid Data Sheet. The Instructions to Bidders will not be part of the Contract.

Section I.  Instructions to Bidders

[Note to the Employer: The instructions to Bidders governing all bidding process for small works funded with Japanese ODA Loans are the Standard Instructions to Bidders included in the Standard Bidding Documents for Procurement of Small Works (SBD (Small Works)) (version 1.0) published by JICA in April 2013.

A copy of the Standard Instructions to Bidders may be attached to the Bidding Documents prepared by the Employer for reference purposes only. If the Instructions to Bidders in the Bidding Documents prepared by the Employer contain modifications from the Standard Instructions to Bidders, JICA will not consider them valid and the Standard Instructions to Bidders, as defined above, shall apply.

Instead of attaching a copy of the Standard Instructions to Bidders, the Employer may use the following introductory text.]

The Instructions to Bidders governing this bidding process are the “Instructions to Bidders” included in Section I of the Standard Bidding Documents for Procurement of Small Works (version 1.0), published by JICA in April, 2013. Those Instructions to Bidders are available on the JICA’s web site shown below:

http://www.jica.go.jp/english/our_work/types_of_assistance/oda_loans/oda_op_info/guide/tender/index.html

A copy of the Instructions to Bidders is not attached to these Bidding Documents.

Section II.	Bid Data Sheet

Notes on Bid Data Sheet Section II, Bid Data Sheet, shall be filled in by the Employer before issuance of the Bidding Documents. The Bid Data Sheet (BDS) contains information and provisions that are specific to a particular bidding process. The Employer must specify in the BDS only the information that the ITB request be specified in the BDS. All information shall be provided; no clause shall be left blank. To facilitate the preparation of the BDS, its clauses are numbered with the same numbers as the corresponding ITB clause.

Bid Data Sheet

| A. General |  |
| --- | --- |
| ITB 1.1 | The number of the Invitation for Bids is: [insert number of the Invitation for Bids] |
| ITB 1.1 | The Employer is: [insert name of the Employer] |
| ITB 1.1 | The name, identification and number of the lot(s) (contract(s)) comprising this bidding process are: [insert number and identification of lot(s) (contract(s))] |
| ITB 2.1 | The Borrower is: [insert name of the Borrower] |
| ITB 2.1 | The number of the Loan Agreement is: [insert Loan Agreement Number] The amount of a Japanese ODA Loan is: [insert amount in Japanese Yen] The signed date of the Loan Agreement is: [insert signed date of the Loan Agreement] |
| ITB 2.1 | The name of the Project is: [insert name of the Project] |
| ITB 2.2 | The applicable Guidelines for Procurement under Japanese ODA Loans are those published in [insert one of the following: April 2012, March 2009, or October 1999]. |
| ITB 3.1(c) | A list of debarred firms and individuals is available at the World Bank’s website: www.worldbank.org/debarr |
| B. Bidding Documents |  |
| ITB 7.1 | For clarification purposes only, the Employer’s address is: [insert the corresponding information as required below. This address may be the same as or different from that specified under ITB 22.1 for Bid submission.] Attention: [insert full name of person, if applicable] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: [insert name of country] Telephone: [insert telephone number, including country and city codes] Facsimile number: [insert facsimile number, including country and city codes] Electronic mail address: [insert email address, if applicable] |
| ITB 7.1 | Responses to any request for clarification, if any, [select “will” or “will not”, as appropriate] be published on the Employer’s web page. [Insert the Employer’s web page if responses to requests for clarifications will be published on the Employer’s web page, otherwise omit.] |
| ITB 7.4 | A Pre-bid meeting [insert “will” or “will not”, as appropriate] take place at the following date, time and place: [If a pre-bid meeting will take place, insert the date, time and place information in the spaces provided below. Otherwise, insert “Not Applicable” in the spaces provided below for the date, time and place.] Date: Time: Place: A site visit conducted by the Employer [insert “will be” or “will not be”, as appropriate] organized. |
| ITB 8.2 | Addenda, if any, [select “will” or “will not”, as appropriate] be published on the Employer’s web page. |
| C. Preparation of Bids |  |
| ITB 10.1 | The language of the Bid is: [insert one of the following: Japanese, English, Spanish or French.] |
| ITB 11.1 (b) | The following Schedules shall be submitted with the Bid: [insert schedules that must be submitted with the Bid, including the priced Bill of Quantities for admeasurement contracts and Activity Schedule for lump sum contracts.] |
| ITB 11.1 (i) | The Bidder shall submit with its Bid the following additional documents: [List any additional documents not already listed in ITB 11.1 that must be submitted with the Bid. If no additional document is to be submitted, insert “none”]. |
| ITB 13.1 | [The following provision should be included and the required corresponding information inserted only if alternative Bids will be considered. Otherwise, delete this BDS 13.1.] Alternative Bids [insert “shall be”] permitted. |
| ITB 13.2 | Alternative times for completion [insert “will be” or “will not be”, as appropriate] permitted. If alternative times for completion are permitted, the evaluation method will be as specified in Section III, Evaluation and Qualification Criteria. |
| ITB 13.4 | Alternative technical solutions shall be permitted for the following parts of the Works: [List the parts of the Works] If alternative technical solutions are permitted, the evaluation method will be as specified in Section III, Evaluation and Qualification Criteria. |
| ITB 14.5 | [Price adjustment is mandatory for contracts with longer duration than 18 months or when local or foreign inflation is expected to be high.] [The following provision should be included only if the prices quoted by the Bidder are subject to price adjustment. Otherwise, delete this BDS 14.5.] The prices quoted by the Bidder shall be subject to adjustment during the performance of the Contract. The Bidder is required to furnish the indices and weighting for the price adjustment formulae in the Schedule of Adjustment Data. |
| ITB 14.7 | [The following provision should be included and the corresponding information inserted only if duties, taxes and other levies will be exempted, reimbursed, or paid by the Employer on behalf of the Contractor. Otherwise, delete this BDS 14.7.] Duties, taxes and other levies indicated below shall be [choose one of the following: “exempted”, “reimbursed”, “paid by the Employer on behalf of the Contractor”, as appropriate.]: [List duties, taxes and other levies.] |
| ITB 15.1 | - The currency(ies) of the Bid shall be as described below: The unit rates and prices shall be quoted by the Bidder separately in the following currencies: - for those inputs to the Works that the Bidder expects to supply from within the Employer’s country, in [insert the name of the currency of the Employer’s country], and further referred to as “the local currency”; and - for those inputs to the Works that the Bidder expects to supply from outside the Employer’s country (referred to as “the foreign currency requirements”), in [insert Japanese Yen and/or other international trading currency or currencies]. |
| ITB 18.1 | The Bid validity period shall be: [insert a number of days] days. [This period should be realistic, allowing sufficient time to evaluate the Bids, bearing in mind the complexity of the Works and the time required for obtaining references, clarifications, clearances, and approvals (including JICA’s concurrence) and for notification of the award. Normally the validity period should not exceed 120 days.] |
| ITB 18.3 (a) | The Bid Price shall be adjusted by the following factor: [insert factor for adjustment] [The local currency portion of the Contract Price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract Price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] |
| ITB 18.3 (b) | The fixed portion of the Bid Price shall be adjusted by the following factor: [insert factor for adjustment] [The local currency portion of the fixed portion of the Contract Price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the fixed portion of the Contract Price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] |
| ITB 19.1 | The amount and currency of the Bid Security shall be [Insert amount and currency of the Bid Security. The amount should be approximately 2% of the estimated cost of the Contract.] |
| ITB 19.2(d) | Other types of acceptable securities: [Insert names of other acceptable securities. Insert “None” if no other forms of Bid Securities besides those listed in ITB 19.2 (a) through (c) are acceptable.] |
| ITB 20.1 | In addition to the original of the Bid, the number of copies is: [insert number of copies]. |
| ITB 20.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: [Insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the Bid.] |
| D. Submission and Opening of Bids |  |
| ITB 22.1 | For Bid submission purposes only, the Employer’s address is: [This address may be the same as or different from that specified under provision ITB 7.1 for clarifications.] Attention: [insert full name of person, if applicable] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: [insert name of country] The deadline for Bid submission is: Date: [insert day, month, and year, e.g., 15 June, 2013] Time: [insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.] [The date and time should be the same as those provided in the Invitation for Bids, unless subsequently amended pursuant to ITB 22.2.] |
| ITB 25.1 | The Bid opening shall take place at: Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City : [insert name of city or town] Country: [insert name of country] Date: [insert day, month, and year, e.g., 15 June, 2013] Time: [insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.] [The date and time should be the same as those given for the deadline for submission of Bids (ITB 22).] |
| E. Evaluation and Comparison of Bids |  |
| ITB 34.1 | The currency that shall be used for Bid evaluation and comparison purposes to convert all Bid Prices expressed in various currencies into a single currency is: [insert “Japanese Yen” or another single currency] The source of exchange rate shall be: [insert the name of the source of exchange rates (e.g., the Central Bank in the Employer’s country).] The date for the exchange rate shall be: [insert day, month and year, e.g. 15 June, 2013, the date not be earlier than 30 days prior to, nor later than, the date of Bid opening specified in ITB 25.1.] The Employer will convert the amounts in various currencies in which the Bid Price, corrected pursuant to ITB 33, is payable (excluding Provisional Sums but including Daywork where priced competitively) to the single currency identified above at the selling rates established for similar transactions by the authority specified and on the date stipulated above. |
| ITB 35.1 | [Insert the following only if the Employer intends to execute any specific elements of the Works by subcontractors selected in advance (nominated subcontractors). Otherwise, delete this BDS 35.1.] At this time the Employer intends to execute certain specific parts of the Works by subcontractors selected in advance. [List the specific parts of the Works and the respective nominated subcontractors.] |

Section III.	Evaluation and Qualification Criteria

Notes on Evaluation and Qualification Criteria This section contains all the criteria that the Employer shall use to evaluate Bids and qualify Bidders. In accordance with ITB 30 and ITB 36, no other factors, methods or criteria shall be used. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms. The Notes for the Bidders contained in this Section III should be included in the actual Bidding Documents issued by the Employer.

Evaluation and Qualification Criteria

- Evaluation

  - Evaluation of Technical Bids

    - Assessment of adequacy of Technical Proposal with Requirements

[Evaluation of the Bidder’s Technical Proposal will include an assessment of the Bidder’s technical capacity to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, and material sourcing in sufficient detail and fully in accordance with the requirements stipulated in Section VI, Works Requirements.]

    - Personnel

The Bidder must demonstrate that it has the personnel for the key positions that meet the following requirements:

| No. | Position | Total Work Experience (years) | Experience in Similar Works (years) |
| --- | --- | --- | --- |
| 1 | Project Manager |  |  |
| 2 | e.g. Chief Engineer(s)1 |  |  |
| 3 | e.g. Health & Safety (Accident Prevention)2 Officer |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| Notes for the Employer: - Chief Engineer(s) or Section Manager(s) who is(are) responsible for the major activities should be evaluated. - The personnel for the key position include an accident prevention officer, as appropriate. Alternative candidates for key positions should not be evaluated. Insert requirements for multiple contracts, if necessary. |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in Form PER-1 and Form PER 2 in Section IV, Bidding Forms.

    - Equipment

The Bidder must demonstrate that it has the key equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| Notes for the Employer: The items listed shall be limited to major items of equipment that are crucial to the proper and timely execution of the contract, and items that Bidders may not readily be able to purchase, hire, or lease in the required time frame. Insert requirements for multiple contracts, if necessary. |  |  |

The Bidder shall provide further details of proposed items of equipment using Form EQU in Section IV, Bidding Forms.

  - Evaluation of Price Bids

[Any adjustments in price that result from the procedures outlined below shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.”  Bid Prices quoted by Bidders shall remain unaltered.]

In addition to the criteria listed in ITB 36.2 (a) – (c) the following criteria shall apply

    - Quantifiable Nonmaterial Nonconformities and Omissions

[The evaluated cost of quantifiable nonconformities is determined as follows:

Pursuant to ITB 32.3 and ITB 36.2 (d), the cost of all quantifiable nonmaterial nonconformities or omissions shall be evaluated. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of Bids, except for the omissions stated in ITB 14.2 which shall be treated in accordance with said clause.]

    - Other Factors

The following factors and methods will apply under ITB 36.2 (f):

The following additional criteria will be used in the evaluation: [If applicable, insert a list of additional criteria.]

…………………………………………………………………………………………………………………………………………………………………............................

The relevant evaluation method shall be as follows: [Insert the evaluation method.]

…………………………………………………………………………………………………………………………………………………………………............................

    - Award Criteria for Multiple Contracts (ITB 36.4):

[Insert the following text in case of multiple contracts, as necessary. Otherwise delete this EQC clause.

“Lots/Packages:

Bidders have the option to bid for any one or more lots/packages. Bids will be evaluated lot/package-wise, taking into account discounts offered, if any, for combined lots/packages. The contract(s) will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer for combined lots/packages, subject to the selected Bidder(s) meeting the required qualification criteria for lot or combination of lots/packages as the case may be.”]

  - Alternative Completion Times, if permitted under ITB 13.2, will be evaluated as follows:

…………………………………………………………………………………………………………………………………………………………………............................

  - Alternative Technical Solutions for Specified Parts, if permitted under ITB 13.4, will be evaluated as follows:

…………………………………………………………………………………………………………………………………………………………………............................

- Qualification

- Exchange Rate for Qualification Criteria

Wherever a Form in Section IV, Bidding Forms, requires a Bidder to state a monetary amount, Bidders should indicate the USD equivalent using the rate of exchange determined as follows:

  - For construction turnover or financial data required for each year - Exchange rate prevailing on the last day of the respective calendar year.

  - Value of single contract - Exchange rate prevailing on the date of the contract.

Exchange rates shall be taken from the publicly available source identified in BDS 34.1 or, in case such rates are not available in the source identified above, any other publicly available source acceptable to the Employer. Any error in determining the exchange rates may be corrected by the Employer.

- Qualification Criteria for Multiple Contracts: [Insert the following text in case of Multiple Contracts. Otherwise delete this EQC clause.

“Criteria for qualification are the aggregate minimum requirement, or any other reasonable requirements set forth by the Employer, for respective lots as specified under Sub-Factors 2.3.2, 2.4.2(a), 2.4.2(b), 2.5.1(i), 2.5.1(ii) below.”]

| Eligibility and Qualification Criteria |  |  |  |  | Compliance Requirements |  |  |  |  |  |  |  | Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor | Requirement |  |  | Single Entity | Joint Venture (existing or intended) |  |  |  |  |  |  | Submission Requirements |
|  |  |  |  |  |  | All Parties Combined |  | Each Member |  |  | One Member |  |  |
| 2.1. Eligibility |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Nationality | Nationality in accordance with ITB 4.3 |  | Must meet requirement |  | N/A |  | Must meet requirement |  |  | N/A | Forms ELI – 1 and 2, with attachments |  |
| 2.1.2 | Conflict of Interest | No conflicts of interest in ITB 4.2 |  | Must meet requirement |  | N/A |  | Must meet requirement |  |  | N/A | Letter of Bid |  |
| 2.1.3 | JICA Ineligibility | Not having been declared ineligible by JICA, as described in ITB 4.4 |  | Must meet requirement |  | N/A |  | Must meet requirement |  |  | N/A | Letter of Bid Form ACK |  |
| Eligibility and Qualification Criteria |  |  |  | Compliance Requirements |  |  |  |  |  |  |  | Documentation |  |
| No. | Factor |  | Requirement | Single Entity |  |  | Joint Venture (existing or intended) |  |  |  |  | Submission Requirements |  |
|  |  |  |  |  |  |  | All Parties Combined |  | Each Member | One Member |  |  |  |
| 2.2. Historical Contract Non-Performance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | History of Non-Performing Contracts |  | Non-performance of a contract (i) did not occur as a result of contractor’s default since 1st January [insert year].1 | Must meet requirement (ii) |  |  | N/A |  | Must meet requirement (ii) | N/A |  | Form CON |  |
| 2.2.2 | Pending Litigation |  | All pending litigation shall in total not represent more than [insert percentage figure] 2 % of the Bidder’s net worth and shall be treated as resolved against the Bidder. | Must meet requirement (ii) |  |  | N/A |  | Must meet requirement (ii) | N/A |  | Form CON |  |
| 2.2.3 | Litigation History |  | No consistent history of court/arbitral award decisions 3 against the Bidder (iii) since 1st January [insert year]. 4 | Must meet requirement (ii) |  |  | N/A |  | Must meet requirement (ii) | N/A |  | Form CON |  |
| Notes for the Bidder - Non-performance, as decided by the Employer, shall include all contracts (a) where non-performance was not challenged by the contractor, including through referral to the dispute resolution mechanism under the respective contract, and (b) that were so challenged but fully settled against the contractor. Non-performance shall not include contracts where Employer’s decision was overruled by the dispute resolution mechanism. Non-performance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective contract and where all appeal instances available to the Bidder have been exhausted. - This requirement also applies to contracts executed by the Bidder as a JV member. - The Bidder shall provide accurate information on the related Bidding Form about any litigation or arbitration resulting from contracts completed or ongoing under its execution over the last five (5) years. A consistent history of awards against the Bidder or any member of a joint venture may result in failure of the Bid. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notes for the Employer 1. Year should usually be one (1) or two (2) years prior to the Bid submission deadline. 2. The percentage should be normally within the range of 50% to 100% of a Bidder’s net worth. 3. The criterion for rejection should be that of numerous arbitral awards or court decisions against the Bidder, taking the number and amount of contracts executed. As an indicative example, the occurrence of one (1) or two (2) adverse cases over five (5) years for a contractor handling, on average, ten (10) construction jobs simultaneously, should not be a cause for rejection. If dispute resolution is found relatively frequently in the business of the Bidder, it may indicate an attitude of the management of the firm that could be dangerous for the Employer if the Bidder were awarded the contract, and further investigation with previous Employers may be warranted. 4. Year should usually be five (5) years prior to the Bid submission deadline. |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Eligibility and Qualification Criteria |  |  | Compliance Requirements |  |  |  | Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor | Requirement | Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.3. Financial Situation |  |  |  |  |  |  |  |
| 2.3.1 | Financial Performance | The audited balance sheets or, if not required by the laws of the Bidder’s country, other financial statements acceptable to the Employer, for the last [insert number of years] years1 shall be submitted and must demonstrate the current soundness of the Bidder’s financial position and indicate its prospective long-term profitability. As the minimum requirement, a Bidder’s net worth calculated as the difference between total assets and total liabilities should be positive.2 | Must meet requirement | N/A | Must meet requirement | N/A | Form FIN – 1 with attachments |
| 2.3.2 | Average Annual Construction Turnover | Minimum average annual construction turnover of USD [insert amount in USD] 3, calculated as total certified payments received for contracts in progress and/ or completed, within the last [insert number] years,4 divided by [insert number] years.5 [insert requirements for multiple contracts, if necessary.] | Must meet requirement | Must meet requirement | Must meet [insert number] % 6 of the requirement | Must meet [insert number] % 7 of the requirement | Form FIN – 2 |
| Notes for the Employer 1. Time period usually specified is five (5) years; it may be reduced to three (3) years minimum (in agreement with JICA) under special country circumstances, such as to provide opportunity for a newly privatized construction industry with limited period of existence, but with suitable experience, etc. Firms owned by individuals and partnerships may not be required to maintain audited balance sheets by the laws of their countries of origin; in such cases, the Employer may relax the audit requirement, but should request other acceptable financial statements. 2. The financial information provided by a Bidder should be reviewed in its entirety to allow a truly informed judgment, and the pass-fail decision on the financial position of the Bidder should be given on this basis. Any abnormal features which may lead to financial problems should alert the Employer to seek expert professional advice for further review and interpretation. 3. The amount stated should normally not be less than twice the estimated annual turnover in the proposed Works contract (based on a straight-line projection of the Employer’s estimated cost, including contingencies, over the contract duration). The multiplier of 2 may be reduced for very large contracts but should not be less than 1.5. 4. The time period is normally five (5) years or more, but may be reduced to not less than three (3) years (in agreement with JICA) under special country circumstances, such as to provide opportunities for a newly privatized construction industry with only a short record of experience, etc. 5. Same number of years as in 4 above. 6. Usually not less than 25% of the requirement for each member of a JV. 7. Usually not less than 40% of the requirement for one member of a JV. |  |  |  |  |  |  |  |

| Eligibility and Qualification Criteria |  |  |  | Compliance Requirements |  |  |  | Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor |  | Requirement | Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.4. Experience |  |  |  |  |  |  |  |  |
| ### 2.4.1 |  | ### General Construction Experience | ### Experience under construction contracts in the role of prime contractor (single entity or JV member), subcontractor, or management contractor(i) for at least the last [insert number] years1, starting 1st January [insert year]. | ### Must meet requirement | ### N/A | ### Must meet requirement | ### N/A | ### Form ### EXP – 1 |
| 2.4.2 (a) |  | Specific Construction Experience | A minimum number of [insert number of contracts]2 similar (ii) contracts that have been satisfactorily and substantially (iii) completed as a prime contractor (single entity or JV member) (iv) between 1st January [insert year] 3 and Bid submission deadline. [insert requirements for multiple contracts, if necessary.] | Must meet requirement | Must meet requirement (v) | N/A | N/A | Form EXP – 2 (a) |
| 2.4.2 (b) |  |  | For the above or other contracts completed and under implementation as prime contractor (single entity or JV member), management contractor or subcontractor (vi) between 1st January [insert year] 4 and Bid submission deadline, a minimum construction experience in the following key activities successfully completed (vii) [list activities indicating volume, number or rate of production as applicable.] 5 [insert requirements for multiple contracts, if necessary.] (viii) | Must meet requirement (can be a specialist subcontractor) | Must meet requirement (can be a specialist subcontractor) | N/A | N/A | Form EXP – 2 (b) |
| Notes for the Bidder - A management contractor is a firm which takes on the role of contract management as a “general” contractor of sort could do. It does not normally perform directly the construction work(s) associated with the contract. Rather, it manages the work of other (sub) contractors while bearing full responsibility and risk for price, quality, and timely performance of the work contract. - The similarity shall be based on the physical size, complexity, methods/technology and/or other characteristics described in Section VI, Works Requirements. Summation of number of small value contracts (less than the value specified under requirement) to meet the overall requirement will not be accepted. - Substantial completion shall be based on 80% or more of the works completed under the contract. - For contracts under which the Bidder participated as a JV member, only the Bidder’s share, by value, shall be considered to meet this requirement. - In case of a JV, the value of contracts completed by its members shall not be aggregated to determine whether the requirement of the minimum value of a single contract has been met. Instead, each contract performed by each member shall satisfy the minimum value of a single contract as required for single entity. In determining whether the JV meets the requirement of total number of contracts, only the number of contracts completed by all members, each of value equal or more than the minimum value required, shall be aggregated. - For contracts under which the Bidder participated as a JV member or subcontractor, only the Bidder’s share, by value, shall be considered to meet this requirement. - Volume, number or rate of production of any key activity can be demonstrated in one or more contracts combined if executed during same time period. The rate of production shall be the annual production rate for the key construction activity (or activities). For the rate of production, either the average during the entire period or in any one or more years during the period should be specified. - The minimum experience requirement for multiple contracts will be the sum of the minimum requirements for respective individual contracts. |  |  |  |  |  |  |  |  |
| Notes for the Employer 1. The time period is normally five (5) years or more, but may be reduced to not less than three (3) years (in agreement with JICA) under special country circumstances, such as to provide opportunities for a newly privatized construction industry with only a short record of experience. 2. The range of contract numbers should be one (1) to three (3), depending on the size, value, nature and complexity of the subject contract, the exposure of the Employer to risk of contractor default, country conditions and history of similar works constructed in the past. 3. The time range is normally five (5) years, and may be extend up to a period of ten (10) years for large-scale projects. 4. Same as that stipulated in Sub-Factor 2.4.2 (a) above. 5. List the monthly or annual production rate for the key construction activity (or activities) in the proposed contract or works, e.g., “one million m3 of rock placed in rockfill dams in one year; X tons of asphalt concrete per month place in road paving; Y m3 of concrete place in … etc.” The rates should be a percentage (say about 80 percent) of the estimated production rate of the key activity (or activities) in the contract or Works as needed to meet the expected construction schedule with due allowance for adverse climatic condition. |  |  |  |  |  |  |  |  |

| Eligibility and Qualification Criteria |  |  | Compliance Requirements |  |  |  | Documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Factor | Requirement | Single Entity | Joint Venture (existing or intended) |  |  | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 2.5. Financial Resources |  |  |  |  |  |  |  |
| 2.5.1 | Financial Resources | (i) The Bidder shall demonstrate that it has access to, or has available, liquid assets, unencumbered real assets, lines of credit, and other financial means (independent of any contractual advance payment) sufficient to meet the construction cash flow requirements estimated as USD [insert amount in USD]1 for the subject contract(s) net of the Bidders other commitments. [insert requirements for multiple contracts, if necessary] | Must meet requirement | Must meet requirement | Must meet [insert number]2 % of the requirement | Must meet [insert number]3 % of the requirement | Form FIR – 1 |
|  |  | (ii) The Bidders shall also demonstrate, to the satisfaction of the Employer, that it has adequate sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments. [insert requirements for multiple contracts, if necessary] | Must meet requirement | Must meet requirement | N/A | N/A | Form FIR – 1 and FIR – 2 |
| Notes for the Employer 1. Indicate the construction cash flow requirement for a number of months, determined as the total time needed by the Employer to pay a contractor’s invoice, allowing for (a) the actual time consumed for construction, from the beginning of the month invoiced, (b) the time needed by the Project Manager to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delays. The total period should not exceed six (6) months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated contract cost. 2. Usually not less than 25% of the requirement for each member of a JV. 3. Usually not less than 40% of the requirement for one member of a JV. |  |  |  |  |  |  |  |

Section IV.	Bidding Forms

Notes on Bidding Forms The Employer shall include in the Bidding Documents all Bidding Forms that the Bidder shall fill out and include in its Bid. As specified in this section, these forms are the Letter of Bid and relevant Schedules, the Bid Security, the Technical Proposal Form, and the Bidder’s Qualification Information Forms.

Table of Forms

Letter of Bid	3

Schedule of Adjustment Data	5

Schedules	7

Technical Proposal	8

Site Organization	9

Method Statement	10

Mobilization Schedule	11

Construction Schedule	12

Safety Plan	13

Form PER -1: Proposed Personnel	14

Form PER -2: Resume of Proposed Personnel	15

Form EQU: Equipment	17

Bidder’s Qualification	18

Form ELI - 1: Bidder Information Form	19

Form ELI - 2: Bidder's Party Information Form	20

Form CON: Historical Contract Non-Performance	21

Form FIN - 1: Financial Situation	24

Form FIN - 2: Average Annual Construction Turnover	26

Form FIR - 1: Financial Resources	27

Form FIR - 2: Current Contract Commitments	28

Form EXP - 1: General Construction Experience	29

Form EXP - 2(a): Specific Construction Experience	30

Form EXP - 2(b): Construction Experience in Key Activities	32

Form ACK Acknowledgement of Compliance with Guidelines for Procurement under Japanese ODA Loans	34

Form of Bid Security	36

Letter of Bid

Date: [insert date of Bid submission]

Loan Agreement No.: [insert No of Loan]

IFB No.: [insert number]

Alternative No.: [insert identification No. if this is a Bid for an alternative]

To: [insert full name of Employer]

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including addenda issued in accordance with Instructions to Bidders (ITB 8). [Insert the number and issuing date of each addendum];

- We, including subcontractors meet the eligibility requirements in accordance with ITB 4 and ITB 5;

- We, including subcontractors have no conflict of interest in accordance with ITB 4;

- We offer to execute in conformity with the Bidding Documents the following Works: [insert a brief description of the Works];

- The total price of our Bid, excluding any discounts offered in item (f) below is:

[In case of only one lot, insert the total price of the Bid in words and figures, indicating the various amounts and the respective currencies];

[In case of multiple lots, insert the total price of each lot];

[In case of multiple lots, insert the total price of all lots (sum of all lots)];

- The discounts offered and the methodology for their application are:

The discounts offered are: [specify in detail each discount offered.]

The exact method of calculations to determine the net price after application of discounts is shown below: [specify in detail the method that shall be used to apply the discounts.];

- Our Bid shall be valid for a period of [specify the number of calendar days] days from the date fixed for the Bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- If our Bid is accepted, we commit to obtain a Performance Security in accordance with the Bidding Documents;

- We are not participating, as a Bidder or as a subcontractor, in more than one Bid in this bidding process in accordance with ITB 4.2(c), other than alternative Bids submitted in accordance with ITB 13;

(j)	We understand that this Bid, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding contract between us, until a formal contract is prepared and executed;

(k)	We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive; and

(l)  We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

- Name of the Bidder*[insert name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder**[insert complete name of person duly authorized to sign the Bid]

- Title of the person signing the Bid [insert complete title of the person signing the Bid]

Signature of the person named above [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

*:	In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder.

**:	Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Schedule of Adjustment Data

Table A.  Local Currency

[In this Table A, the Employer shall indicate the necessary information in columns (a), (b), (c) and (d), and shall also provide a fixed value in A and a range of values in B, C, D and E of column (f). For complex works contracts, it may be necessary to specify several families of price adjustment formulae for the different works involved and to prepare the corresponding adjustment tables.]

| (a) | (b) | (c) | (d) | (e) | (f) |
| --- | --- | --- | --- | --- | --- |
| Index code | Index description | Source of index | Base value and date | Bidder’s related currency amount | Bidder’s proposed weighting |
|  | Nonadjustable | — | — | — | A: B: C: D: E: |
|  |  |  | Total |  | 1.00 |

The Bidder shall fill in column (e) and specify a value within the ranges given by the Employer in B, C, D and E of column (f), so that the total weighting equals 1.00.

Table B.  Foreign Currency (FC)

[In this Table B, the Employer shall indicate the necessary information in columns (a) and (b), and shall also provide a fixed value in A and a range of values in B, C, D and E of column (g). For complex works contracts, it may be necessary to specify several families of price adjustment formulae for the different works involved and to prepare the corresponding adjustment tables.]

Currency: __________[Insert name of currency; if the Bidder wishes to quote in more than one foreign currency then this table should be repeated for each foreign currency.]

| (a) | (b) | (c) | (d) | (e) | (f) | (g) |
| --- | --- | --- | --- | --- | --- | --- |
| Index code | Index description | Source of index | Base value and date | Bidder’s related source currency in type/amount | Equivalent in FC for payment | Bidder’s proposed weighting |
|  | Nonadjustable | — | — | — |  | A: B: C: D: E: |
|  |  |  |  | Total |  | 1.00 |

The Bidder shall indicate the type of currency and columns (c), (d), (e) and (f), and specify a value within the ranges given by the Employer in B, C, D and E of column (g), so that the total weighting equals 1.00.

Schedules

Bill of Quantities [Admeasurement Contract]

Activity Schedule [Lump sum Contract]

[For a sample of the Bill of Quantities, in the case of unit price contracts, refer to Section IV. Bidding Forms of the Standard Bidding Documents for Procurement of Works, October 2012.]

Technical Proposal

-Site Organization

- Method Statement

- Mobilization Schedule

- Construction Schedule

- Safety Plan

- Personnel

- Equipment

- [Others]

Site Organization

[Insert Organization Information]

Method Statement

[Insert Method of Statement]

Mobilization Schedule

[Insert Mobilization Schedule]

Construction Schedule

[Insert Construction Schedule]

Safety Plan

[Insert Safety Plan]

Form PER -1: Proposed Personnel

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

[The Bidder shall provide the names of suitably qualified personnel to meet the specified requirements stated in Section III, Evaluation and Qualification Criteria, Clause 1.1.2.]

| 1. | Title of position* |
| --- | --- |
|  | Name |
| 2. | Title of position* |
|  | Name |
| 3. | Title of position* |
|  | Name |
| 4. | Title of position* |
|  | Name |

*As listed in Section III.

Form PER -2: Resume of Proposed Personnel

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

[The Bidder shall provide the data on the experience of the personnel indicated in Form PER-1, in the form below:]

Name of Bidder

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

[Summarize professional experience over the last 20 years, in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.]

| From | To | Company / Project / Position / Relevant technical and management experience |
| --- | --- | --- |

Form EQU: Equipment

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Joint Venture Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

[The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III, Evaluation and Qualification Criteria, Clause 1.1.3. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.]

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

- Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

Bidder’s Qualification

To establish its qualifications to perform the Contract in accordance with Section III, Evaluation and Qualification Criteria, the Bidder shall provide the information requested in the corresponding Forms included hereunder:

Form ELI -1:	Bidder Information Form

Form ELI -2:	Bidder’s Party Information Form

Form CON:	Historical Contract Non-Performance

Form FIN -1:	Financial Situation

Form FIN -2:	Average Annual Construction Turnover

Form FIR -1:	Financial Resources

Form FIR -2:	Current Contract Commitments

Form EXP -1:	General Construction Experience

Form EXP -2(a):	Specific Construction Experience

Form EXP -2(b):	Construction Experience in Key Activities

Form ELI - 1: Bidder Information Form

Date: [insert day, month, year]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

[Bidders shall provide the following information:]

Bidder’s legal name [insert full name]

In case of a JV, legal name of the representative member and of each member: [insert full name of each member in the JV and specify the representative member]

Bidder’s actual or intended country of registration: [insert country of registration]

Bidder’s actual or intended year of incorporation: [insert year of incorporation]

Bidder’s legal address in country of registration: [insert street/ number/ town or city/ country]

Bidder’s authorized representative information Name: [insert full name] Address: [inset street/ number/ town or city/ country] Telephone/Fax numbers: [insert telephone/fax numbers, including country and city codes] E-mail address: [insert E-mail address]

1. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above, in accordance with ITB 4.3.  In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB 4.1. 2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form ELI - 2: Bidder's Party Information Form

Date: [insert day, month, year]
IFB No.: [insert number]
Page [insert page number] of [insert total number] pages

[The following form is additional to Form ELI-1, and shall be completed to provide information relating to each JV member (in case the Bidder is a JV) as well as any specialist subcontractor proposed to be used by the Bidder for any part of the Contract resulting from this process.]

Bidder’s legal name: [insert full name]

Bidder’s Party legal name: [insert full name of Bidder’s party]

Bidder’s Party country of registration: [insert country of registration]

Bidder’s Party year of incorporation: [insert year of incorporation]

Bidder’s Party legal address in country of registration: [insert street/ number/ town or city/ country]

Bidder’s Party authorized representative information Name: [insert full name] Address: [insert street/ number/ town or city/ country] Telephone/Fax numbers: [insert telephone/fax numbers, including country and city codes] E-mail address: [insert E-mail address]

1. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above, in accordance with ITB 4.3. 2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form CON: Historical Contract Non-Performance

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] pages

[The following table shall be filled in for the Bidder and for each member of a JV.]

1.  History of Non-Performing Contracts

| Non-Performing Contracts |  |  |  |
| --- | --- | --- | --- |
|  Contract non-performance did not occur since 1st January [insert year], in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.1.  Contract(s) not performed since 1st January [insert year], in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.1 is (are) indicated below: |  |  |  |
| Year | Non- performed portion of contract | Contract Identification | Total Contract Amount (current value, currency, exchange rate and USD equivalent) |
| [insert year] | [insert amount and percentage] | Contract Identification: [insert complete contract name, number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/city/country] Reason(s) for non-performance: [indicate main reason(s)] | [insert amount] |

2.  Pending Litigation

| Pending Litigation |  |  |  |  |
| --- | --- | --- | --- | --- |
|  No pending litigation in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.2. |  |  |  |  |
|  Pending litigation in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.2 is indicated below: |  |  |  |  |
| Year of dispute | Amount in dispute (currency) | Outcome as Percentage of Net Worth | Contract Identification | Total Contract Amount (current value, currency, exchange rate and USD equivalent) |
| [insert year] | [insert amount] | [insert percentage] | Contract Identification: [indicate complete contract name, number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/ city/ country] Matter in dispute: [indicate main issues in dispute] Status of dispute: [Indicate if it is being treated by the Adjudicator, under Arbitration or being dealt with by the Judiciary] | [insert amount] |

3.  Litigation History

| Litigation History |  |  |
| --- | --- | --- |
|  No court/arbitral award decisions against the Bidder since 1st January [insert year], in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.3. |  |  |
|  Court/ arbitral award decisions against the Bidder since 1st January [insert year], in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.2.3, are indicated below: |  |  |
| Year of award | Contract Identification | Total Contract Amount (current value, currency, exchange rate and USD equivalent) |
| [insert year] | Contract Identification: [indicate complete contract name, number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/city/country] Matter in dispute: [indicate main issues in dispute] Party who initiated the dispute: [indicate “Employer” or “Contractor”] Status of dispute: [Indicate if it is being treated by the Adjudicator, under Arbitration or being dealt with by the Judiciary] | [insert amount] |

Form FIN - 1: Financial Situation

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

1. Financial data

| Type of Financial information in (currency) | Historic information for previous [insert number] years (amount in currency, currency, exchange rate, USD equivalent) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| Statement of Financial Position (Information from Balance Sheet) |  |  |  |  |  |
| Total Assets (TA) |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |
| Information from Income Statement |  |  |  |  |  |
| Total Revenue (TR) |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |
| Profits After Taxes (PAT) |  |  |  |  |  |

2. Financial documents

The Bidder and its parties shall provide copies of the financial statements for [number of years] years pursuant Section III, Evaluation and Qualification Criteria Sub-Factor 2.3.1. The financial statements shall:

(a)	reflect the financial situation of the Bidder or in case of JV, of each member, and not of an affiliated entity (such as parent company or group member).

(b)	be independently audited or certified in accordance with local legislation.

(c)	be complete, including all notes to the financial statements.

(d)	correspond to accounting periods already completed and audited.

	Attached are copies of financial statements* for the [number of years] years required above; and complying with the requirements.

*	If the most recent set of financial statements is for a period earlier than 12 months from the date of Bid, the reason for this should be justified.

Form FIN - 2: Average Annual Construction Turnover

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

| Annual Turnover Data (Construction only) |  |  |  |
| --- | --- | --- | --- |
| Year | Amount and Currency | Exchange rate | USD equivalent |
| [indicate year] | [insert amount and indicate currency] | [insert applicable exchange rate] | [insert amount in USD equivalent] |
| Average Annual Construction Turnover * |  |  |  |

*	Total USD equivalent for all years divided by the total number of years, in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.3.2.

Form FIR - 1: Financial Resources

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

[Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as specified in Section III, Evaluation and Qualification Criteria, Sub-Factor 2.5.1.]

| Financial Resources |  |  |
| --- | --- | --- |
| No. | Source of financing | Amount (USD equivalent) |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |

Form FIR - 2: Current Contract Commitments

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

[Bidders and each member of a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued, in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.5.1.]

| Current Contract Commitments |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Name of Contract | Employer’sContact Address, Tel, Fax | Value of Outstanding Work[Current USD Equivalent] | Estimated Completion Date | Average Monthly Invoicing Over Last Six Months [USD/month)] |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |

Form EXP - 1: General Construction Experience

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

[Identify contracts that demonstrate continuous construction work over the past [number] years pursuant to Section III, Evaluation and Qualification Criteria, Sub-Factor 2.4.1. List contracts chronologically, according to their commencement (starting) dates.]

| General Construction Experience |  |  |  |
| --- | --- | --- | --- |
| Starting Year | Ending Year | Contract Identification | Role of Bidder |
| [indicate year] | [indicate year] | Contract name: [insert full name] Brief description of the Works performed by the Bidder: [describe Works performed briefly] Amount of contract: [insert amount in currency, mention currency used, exchange rate and USD equivalent] Name of Employer: [indicate full name] Address: [indicate street/number/town or city/country] | [insert "Prime Contractor (Single entity or JV member) or "Subcontractor” or "Management Contractor”] |

Form EXP - 2(a): Specific Construction Experience

[The following table shall be filled in for contracts performed by the Bidder and by each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]
IFB No. [insert number]
Page [insert page number] of [insert total number] page

[Fill out one (1) form per contract, in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.4.2(a).]

| Contract of Similar Size and Nature |  |  |  |
| --- | --- | --- | --- |
| Similar Contract No. [insert number] of [insert number of similar contracts required] | Information |  |  |
| Contract Identification | [insert contract name and reference identification number, if applicable] |  |  |
| Award Date | [insert day, month, year, e.g., 15 June, 2015] |  |  |
| Completion Date | [insert day, month, year, e.g., 03 October, 2017] |  |  |
| Role in Contract [check the appropriate box] | Prime Contractor |  |  |
|  | Single entity  |  | JV member  |
| Total Contract Amount | [insert total contract amount and currency(ies)] |  | USD [insert exchange rate and total contract amount in USD equivalent] |
| If member in a JV, specify participation in total Contract amount | [insert a percentage of participation] | [insert amount(s) and currency(ies) of participation] | USD [insert exchange rate and amount of participation in USD equivalent] |
| Employer’s Name: | [insert full name] |  |  |
| Address: Telephone/fax number E-mail: | [indicate street / number / town or city / country] [insert telephone/fax numbers, including country and city area codes] [insert E-mail address, if available] |  |  |

| Similar Contract No. [insert number] of [insert number of similar contracts required] | Information |
| --- | --- |
| Description of the similarity in accordance with Sub-Factor 2.4.2(a) of Section III: |  |
| 1. Physical size of required works items | [insert physical size of items] |
| 2. Complexity | [insert description of complexity] |
| 3. Methods/Technology | [insert specific aspects of the methods/ technology involved in the contract] |
| 4. Other Characteristics | [insert other characteristics as described in Section VI, Works Requirements] |

Form EXP - 2(b): Construction Experience in Key Activities

[The following table shall be filled in for Contracts performed by the Bidder and by each member of a JV.]

Date: [insert day, month, year]
Bidder’s Legal Name: [insert full name]
Bidder’s Party Legal Name:[insert full name]

Subcontractor’s Legal Name [insert full name]
IFB No.: [insert number]

Page [insert page number] of [insert total number] pages

[Fill out one (1) form per contract, in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.4.2(b).]

1.	Key Activity No (1): ______: [insert brief description of the Activity, emphasizing its specificity]

Total Quantity of Activity under the contract: _____________________________________

| Contract with Similar Key Activities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Item | Information |  |  |  |  |
| Contract Identification | [insert contract name and number, if applicable] |  |  |  |  |
| Award Date | [insert day, month, year, e.g., 15 June, 2015] |  |  |  |  |
| Completion Date | [insert day, month, year, e.g., 03 October, 2017] |  |  |  |  |
| Role in Contract [check the appropriate box] | Prime Contractor |  |  | Management Contractor  | Sub-contractor  |
|  | Single entity  | JV member  |  |  |  |
| Total Contract Amount | [insert total contract amount and currency(ies)] |  |  | USD [insert Exchange rate and total contract amount in USD equivalent] |  |
| Quantity (Volume, number or rate of production, as applicable) performed under the contract per year or part of the year [Insert extent of participation indicating actual quantity of key activity successfully completed in the role performed] | Total quantity in the contract (i) |  | Percentage participation (ii) |  | Actual Quantity Performed (i) x (ii) |
| Year 1 |  |  |  |  |  |
| Year 2 |  |  |  |  |  |
| Year 3 |  |  |  |  |  |
| Year 4 |  |  |  |  |  |
| Employer’s Name: | [insert full name] |  |  |  |  |
| Address: Telephone/fax number E-mail: | [indicate street / number / town or city / country] [insert telephone/fax numbers, including country and city area codes] [insert E-mail address, if available] |  |  |  |  |

2.  Activity No. (2) _____

3.  Activity No. (3) _____

Form ACK
Acknowledgement of Compliance with Guidelines for Procurement under Japanese ODA Loans

A) I, [insert name and position of authorized signatory], being duly authorized by [insert name of Bidder/members of joint venture (“JV”)] (hereinafter referred to as the “Bidder”) to execute this Acknowledgement of Compliance with Guidelines for Procurement under Japanese ODA Loans, hereby certify on behalf of the Bidder and myself that all information provided in the Bid submitted by the Bidder for [insert Loan No and name of the Project] is true, correct and accurate to the best of the Bidder’s and my knowledge and belief.  I further certify, on behalf of the Bidder, that:

    - the Bid has been prepared and submitted in full compliance with the terms and conditions set forth in the Guidelines for Procurement under Japanese ODA Loans (hereinafter referred to as the “Guidelines”); and

    - the Bidder has not, directly or indirectly, taken any action which is or constitutes a corrupt, fraudulent, collusive or coercive act or practice in violation of the Guidelines and is not subject to any conflict of interest as stipulated in the relevant section of the Guidelines.

<If debarment for more than one year by the World Bank Group is NOT imposed, use the following sentence B).>

B)	I certify that the Bidder has NOT been debarred by the World Bank Group for more than one year since the date of issuance of Invitation for Bids.

<If debarment for more than one year by the World Bank Group has been imposed BUT three (3) years have passed since the date of such debarment decision, use the following sentence B’).>

B’)	I certify that the Bidder has been debarred by the World Bank Group for a period more than one year BUT that on the date of issuance of Invitation for Bids at least three (3) years had passed since the date of such debarment decision.  Details of the debarment are as follows:

| name of the debarred firm | starting date of debarment | ending date of debarment | reason for debarment |
| --- | --- | --- | --- |

- I certify that the Bidder will not enter into a subcontract with a firm which has been debarred by the World Bank Group for a period more than one year, unless on the date of the subcontract at least three (3) years have passed since the date of such debarment decision.

- I certify, on behalf of the Bidder, that if selected to undertake services in connection with the Contract, the Bidder shall carry out such services in continuing compliance with the terms and conditions of the Guidelines.

- I further certify, on behalf of the Bidder, that if the Bidder is requested, directly or indirectly, to engage in any corrupt or fraudulent action under any applicable law, such as the payment of a rebate, at any time during a process of public procurement,  negotiations, execution or implementation of contract (including amendment thereof), the Bidder shall report all relevant facts regarding such request to the relevant section in JICA (details of which are specified below) in a timely manner.

JICA’s information desk on fraud and corruption (A report can be made to either of the offices identified below.)

(1)  JICA Headquarters: Legal Affairs Division, General Affairs Department

URL: https://www2.jica.go.jp/en/odainfo/index.php

Tel: +81 (0)3 5226 8850

(2) JICA XX office

Tel:

The Bidder acknowledges and agrees that the reporting obligation stated above shall NOT in any way affect the Bidder’s responsibilities, obligations or rights, under relevant laws, regulations, contracts, guidelines or otherwise, to disclose or report such request or other information to any other person(s) or to take any other action, required to or allowed to, be taken by the Bidder. The Bidder further acknowledges and agrees that JICA is not involved in or responsible for the procurement process in any way.

- If any of the statements made herein  is subsequently proven to be untrue or incorrect based on facts subsequently determined, or if any of the warranties or covenants made herein is not complied with, the Bidder will accept, comply with, and not object to any remedies taken by the Employer  and any sanctions imposed by or actions taken by JICA.

_____________________________ Authorized Signatory

[Insert name of signatory; title]

For and on behalf of [Insert name of the Bidder]

Date:

Form of Bid Security

(Bank Guarantee)

[Guarantor letterhead or SWIFT identifier code]

Beneficiary: [Employer to insert its name and address]

IFB No.: [Employer to insert number of Invitation for Bids]

Date:  [Insert date of issue]

BID GUARANTEE No.: [Insert guarantee reference number]

Guarantor: [Insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of the Bidder, which in the case of a joint venture shall be the name of the joint venture (whether legally constituted or prospective) or the names of all members thereof] (hereinafter called “the Applicant”) has submitted or will submit to the Beneficiary its Bid (hereinafter called “the Bid”) for the execution of [insert description of Contract] under the Loan Agreement No.[insert Loan Agreement Number] (“the L/A”).

Furthermore, we understand that, according to the Beneficiary’s conditions, Bids must be supported by a bid guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in words] ([insert amount in figures]) upon receipt by us of the Beneficiary’s complying demand, supported by the Beneficiary’s statement, whether in the demand itself or a separate signed document accompanying or identifying the demand, stating that either the Applicant:

(a)	has withdrawn its Bid during the period of Bid validity set forth in the Applicant’s Letter of Bid (hereinafter called “the Bid Validity Period”), or any extension thereto provided by the Applicant; or

(b)	having been notified of the acceptance of its Bid by the Beneficiary during the Bid Validity Period or any extension thereto provided by the Applicant,  (i) has failed to execute the Contract Agreement, or (ii) has failed to furnish the Performance Security, in accordance with the Instructions to Bidders of the Beneficiary’s Bidding Documents.

This guarantee will expire and shall be returned to the Applicant: (a) if the Applicant is the successful Bidder, upon our receipt of copies of the Contract Agreement signed by the Applicant and the Performance Security issued to the Beneficiary in relation to such contract agreement; or (b) if the Applicant is not the successful Bidder, upon the earlier of (i) our receipt of a copy of the Beneficiary’s notification to the Applicant of the results of the bidding process; or (ii) twenty-eight (28) days after the end of the Bid Validity Period.

Consequently, any demand for payment under this guarantee must be received by us at the office as indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458 .

_____________________________

[signature(s)]

[Note: All italicized text is for use in preparing this form and shall be deleted from the final product.]

Form of Bid Security (Bid Bond)

BOND NO. [insert Bond No.]

BY THIS BOND [name of Bidder] as Principal (hereinafter called “the Principal”), and [name, legal title, and address of surety], authorized to transact business in [name of country of Employer], as Surety (hereinafter called “the Surety”), are held and firmly bound unto [name of Employer] as Obligee (hereinafter called “the Employer”) in the sum of [amount of Bond] [amount in words], for the payment of which sum, well and truly to be made, we, the said Principal and Surety, bind ourselves, our successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Principal has submitted a written Bid to the Employer dated the [insert day] day of [insert month], 20 [insert year], for the construction of [name of Contract] (hereinafter called the “Bid”).

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that if the Principal:

- withdraws its Bid during the period of Bid validity specified in the Form of Bid; or

- having been notified of the acceptance of its Bid by the Employer during the period of Bid validity; (i) fails or refuses to execute the Contract Form, if required; or (ii) fails or refuses to furnish the Performance Security in accordance with the Instructions to Bidders;

then the Surety undertakes to immediately pay to the Employer up to the above amount upon receipt of the Employer’s first written demand, without the Employer having to substantiate its demand, provided that in its demand the Employer shall state that the demand arises from the occurrence of any of the above events, specifying which event(s) has occurred.

The Surety hereby agrees that its obligation will remain in full force and effect up to and including the date 28 days after the date of expiration of the Bid validity as stated in the Invitation to Bid or extended by the Employer at any time prior to this date, notice of which extension(s) to the Surety being hereby waived.

IN TESTIMONY WHEREOF, the Principal and the Surety have caused these presents to be executed in their respective names this [insert day] day of [insert month] ,20 [insert year].

Principal: _______________________	Surety: _____________________________
	Corporate Seal (where appropriate)

_______________________________	____________________________________
(Signature)	(Signature)

Section V.	Eligible Source Countries of 
Japanese ODA Loans

[Specify the Eligible Source Countries]

PART 2 – Works Requirements

Section VI.	Works Requirements

Contents

Scope of Works	2

Specifications	3

Drawings	6

Supplementary Information	7

Scope of Works

Specifications

Notes for Preparing Technical Specifications These Notes for Preparing Specifications are intended only as information for the Employer or the person drafting the Bidding Documents. They should not be included in the final documents. Precise and clear Specifications are a prerequisite for Bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their Bids. In the context of international competitive bidding, the Specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of the goods and services to be procured. Only if this is done will the objectives of economy, efficiency, and equality in procurement be realized, responsiveness of Bids be ensured, and the subsequent task of Bid evaluation facilitated. The Specifications should require that all goods and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract. A clause setting out the scope of the Works is often included at the beginning of the Specifications, and it is customary to give a list of the Drawings. Where the Contractor is responsible for the design of any part of the Permanent Works, the extent of his obligations must be stated. Samples of Specifications from previous similar projects in the same country are useful in this respect. The metric units should be used. Most Specifications are normally written specially by the Employer or Project Manager to suit the contracts for Works in hand. There are no standard Specifications for universal application in all sectors in all countries, but there are established principles and practices that are reflected in these documents. There are considerable advantages in standardizing General Specifications for repetitive Works in recognized public sectors, such as highways, ports, railways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract. Deletions or addenda should then adapt the General Specifications to the particular Works. Care must be taken in drafting Specifications to ensure that they are not restrictive. In the specification of standards for goods, materials, and workmanship, recognized international standards should be used as much as possible. Where other particular standards are used, whether national standards of the Borrower’s country or other standards, the Specifications should state that goods, materials, and workmanship meeting other authoritative standards that ensure substantially equal or higher quality than the standards mentioned, will also be acceptable. To that effect, the following clause may be inserted in the Particular Conditions or Specifications. Sample Clause: “Equivalency of Standards and Codes Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract. Where such standards and codes are national, or relate to a particular country or region, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified will be accepted subject to the Project Manager’s prior review and written consent. Differences between the standards specified and the proposed alternative standards must be fully described in writing by the Contractor and submitted to the Project Manager at least twenty-eight (28) days prior to the date when the Contractor desires the Project Manager’s consent. In the event the Project Manager determines that such proposed deviations do not ensure substantially equal or higher quality, the Contractor shall comply with the standards specified in the documents.” Alternative Technical Proposals Employers should decide whether technical solutions to specified parts of the Works are to be permitted. Alternatives are appropriate in cases where obvious (and potentially less costly) alternatives are possible to the technical solutions specified in the Bidding Documents for certain elements of the Works, taking into consideration the comparative specialized advantage of potential Bidders. For example: • pile foundations (proprietary methods and different material) • bridge foundations (open well, caissons, piles, etc.) • columns, beams, decking (reinforced concrete, prestressed concrete, steel, etc.) • proprietary methods for post-tensioning concrete • lining of canals • pipeline materials, coating, jointing • road surfacing (asphalt, concrete, etc.) • transmission tower design and erection • street lighting • offshore foundations • offshore trestle spans The Employer should provide a description of the selected parts of the Works with appropriate references to Drawings, Specifications, Bill of Quantities, and Design or Performance criteria, stating that the alternative solutions shall be at least structurally and functionally equivalent to the basic design parameters and specifications. Such alternative solutions shall be accompanied by all information necessary for a complete evaluation by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, proposed construction methodology, and other relevant details. Technical alternatives permitted in this manner shall be considered by the Employer each on its own merits and independently of whether the Bidder has priced the item as described in the Employer’s design included with the Bidding Documents.

Drawings

[Insert here a list of Drawings.  The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder.]

Supplementary Information

PART 3 – Conditions of Contract and Contract Forms

Section VII.	General Conditions (GC)

Notes on Conditions of Contract The Conditions of Contract comprises two parts: - Standard General Conditions – GC (Section VII of the Bidding Documents); and - Particular Conditions – PC (Section VIII of the Bidding Documents). The use of the Standard GC, in all Bidding Documents/Contracts for small construction works financed by Japanese ODA Loans is required, and they shall be used without any modification. A copy of the Standard GC may be attached to the Bidding Documents/Contract prepared by the Employer for reference purposes only. If the General Conditions in the Bidding Documents/Contract prepared by the Employer contain modifications from the Standard GC, JICA will not consider them valid and the Standard GC, as defined above, shall apply. The Standard GC can be used for both smaller admeasurement contracts and lump sum contracts and have been developed on the basis of considerable international experience in the drafting and management of contracts, bearing in mind a trend in the construction industry towards simpler, more straightforward language. The use of these standard conditions of contract for all small works will ensure comprehensiveness of coverage, better balance of rights or obligations between Employer and Contractor, general acceptability of its provisions, and savings in time and cost for Bid preparation and review, leading to more economical prices. Any amendments and additions to the General Conditions, specific to the contract in hand, should be introduced in the Particular Conditions. The Standard GC, read in conjunction with the Particular Conditions and other documents listed therein, should be a complete document expressing fairly the rights and obligations of both parties. Whoever drafts the PC should be thoroughly familiar with the provisions of the GC and with any specific requirements of the Contract. Legal advice is recommended when amending provisions or drafting new ones. Note that the PC provisions take precedence over those in the GC. Clause numbers in the PC correspond to those in the GC.

Section VII.	General Conditions (GC)

[Note to the Employer: The General Conditions governing Contracts funded with Japanese ODA Loans are the Standard General Conditions of Contract (hereinafter referred to as “Standard GC”) set forth in Part 3, Section VII of these Standard Bidding Documents for Procurement of Small Works (version 1.0) (SBD (Small Works) published by JICA in April, 2013.

A copy of the Standard GC may be attached to Bidding Documents/Contracts prepared by the Employer for reference purposes only. If the General Conditions in the Bidding Documents/Contracts prepared by the Employer contain modifications from the Standard GC, JICA will not consider these General Conditions valid and the Standard GC, as defined above, shall apply.

Instead of attaching a copy of the Standard GC, the Employer may use the following introductory text.]

The General Conditions governing this Contract are the Standard General Conditions of Contract set forth in Part 3, Section VII of the Standard Bidding Documents for Procurement of Small Works (version 1.0)) published by JICA in April, 2013. Those General Conditions of Contract are available on the JICA’s web site shown below:

http://www.jica.go.jp/english/our_work/types_of_assistance/oda_loans/oda_op_info/guide/tender/index.html

A copy of these General Conditions is not attached to these Bidding Documents/this Contract.

Section VIII.	Particular Conditions (PC)

Notes on Particular Conditions The PC complement the GC to specify data and contractual requirements linked to the special circumstances of the country, the Employer, the Project Manager, the sector, the overall project, and the Works. Whenever there is a conflict, the provisions herein shall prevail over those in the GC. Note that the PC provisions take precedence over those in the GC. Clause numbers in the PC correspond to those in the GC. Except where otherwise indicated, all PC should be filled in by the Employer prior to issuance of the Bidding Documents. Schedules and reports to be provided by the Employer should be annexed.

Particular Conditions (PC)

| A. General |  |  |
| --- | --- | --- |
| GC 1.1 (q) | The Employer is [insert name, address, and name of authorized representative]. |  |
| GC 1.1 (t) | The Intended Completion Date for the whole of the Works shall be [insert date] [If different dates are specified for completion of the Works by section (“sectional completion” or milestones), these dates should be listed here.] |  |
| GC 1.1 (y) | The Project Manager is [insert name, address, and name of authorized representative]. |  |
| GC 1.1 (aa) | The Site is located at [insert address of Site ] and is defined in drawings No. [insert numbers] |  |
| GC 1.1 (dd) | The Start Date shall be [insert date]. |  |
| GC 2.2 | Sectional Completions are: [insert nature and dates, if appropriate] |  |
| GC 2.3 (i) | The following documents also form part of the Contract: [list documents] |  |
| GC 3.1 | The language of the Contract is [insert one of the following: “Japanese”, “English”, “Spanish” or “French”]. The law that applies to the Contract is the law of [insert name of country]. |  |
| GC 5.1 | [The following provision should be included only if the Project Manager may not delegate any of his duties and responsibilities. Otherwise, delete this PC 5.1. ] The Project manager may not delegate any of his duties and responsibilities. |  |
| GC 8.1 | Schedule of Other Contractors: [insert Schedule of Other Contractors, if appropriate] |  |
| GC 13.1 | The minimum insurance amounts and deductibles shall be: (a) for loss or damage to the Works, Plant and Materials: [insert amounts]. (b) for loss or damage to Equipment: [insert amounts]. (c) for loss or damage to property (except the Works, Plant, Materials, and Equipment) in connection with Contract: [insert amounts]. (d) for personal injury or death: - of the Contractor’s employees: [insert amounts]. - of other people: [insert amounts]. |  |
| GC 14.1 | Site Data are: [list Site Data] |  |
| GC 18.2 | Appointment of an accident prevention officer [“is” or “is not”] necessary under the Contract. [If the Employer considers it necessary to appoint an accident prevention officer under the subject Contract, the following statement should be added to Sub-Clause 18.2: “This person shall be qualified for this responsibility, and shall have the authority to issue instructions and take protective measures to prevent accidents. Throughout the execution of the Works, the Contractor shall provide whatever is required by this person to exercise this responsibility and authority. The Contractor shall send, to the Project Manager, details of any accident as soon as practicable after its occurrence. The Contractor shall maintain records and make reports concerning health, safety and welfare of persons and damage to property, as the Project Manager may reasonably require.”] |  |
| GC 18.3 | Appropriate measures for HIV-AIDS prevention at the project site [“are” or “are not”] necessary under the Contract. [The following clauses may be added to Sub-Clause 18.3 in order to help contain the spread of HIV/AIDS, considering circumstances particular to each individual project: “The Contractor shall conduct an HIV-AIDS awareness program via an approved service provider, and shall undertake such other measures as are specified in the Contract to reduce the risk of the transfer of the HIV virus between and among the Contractor’s personnel and the local community, to promote early diagnosis and to assist affected individuals. The Contractor shall throughout the Contract (including the Defects Liability Period): (i) conduct Information, Education and Consultation Communication (IEC) campaigns, at least every other month, addressed to all the Site staff and labor (including all the Contractor's employees, all subcontractors and Consultants' employees, and all truck drivers and crew making deliveries to Site for construction activities) and to the immediate local communities, concerning the risks, dangers and impact, and appropriate avoidance behavior with respect to Sexually Transmitted Diseases (STD)—or Sexually Transmitted Infections (STI) in general and HIV/AIDS in particular; (ii) provide male or female condoms for all Site staff and labor as appropriate; and (iii) provide for STI and HIV/AIDS screening, diagnosis, counseling and referral to a dedicated national STI and HIV/AIDS program, (unless otherwise agreed) of all Site staff and labor. The Contractor shall include in the program to be submitted for the execution of the Works under Clause 25 an alleviation program for Site staff and labor and their families in respect of STI and STD including HIV/AIDS. The STI, STD and HIV/AIDS alleviation program shall indicate when, how and at what cost the Contractor plans to satisfy the requirements of this Sub-Clause and the related specification. For each component, the program shall detail the resources to be provided or utilized and any related subcontracting proposed. The program shall also include provision of a detailed cost estimate with supporting documentation. Payment to the Contractor for preparation and implementation of this program shall not exceed the Provisional Sum dedicated for this purpose.”] |  |
| GC 20.1 | The Site Possession Date(s) shall be: [insert location(s) and date(s)] |  |
| GC 23.1 & GC 23.2 | Appointing Authority for the Adjudicator: [insert name of Authority]. |  |
| GC 24.3 | Hourly rate and types of reimbursable expenses to be paid to the Adjudicator: [insert hourly fees and reimbursable expenses]. |  |
| B. Time Control |  |  |
| GC 25.1 |  | The Contractor shall submit for approval a Program for the Works within [insert number] days from the date of the Letter of Acceptance. |
| GC 25.3 |  | The period between Program updates is [insert number] days. |
| C. Quality Control |  |  |
| GC 33.1 |  | [The following provision should be included only if the Defect Liability Period extends over a period other than 365 days starting from the Completion Date. Otherwise, delete this PC 33.1.] The Defects Liability Period is: [insert number] days. |
| D. Cost Control |  |  |
| GC 40.1 |  | [The following provision should be included only if the interest rate is different from 3 percentage points above the discount rate of the central bank in the country of the currency(ies) of payment. Otherwise, delete this PC 40.1.] The interest rate is: [insert rate] |
| GC 44.1 |  | The Contract [insert “is” or “is not”] subject to price adjustment in accordance with Clause 44, and the following information regarding coefficients [specify “does” or “does not”] apply. The coefficients for adjustment of prices are: (a) For currency [insert name of currency]: (i) [insert percentage] percent non adjustable element (coefficient A). (ii) [insert percentage] percent adjustable element (coefficient B). (b) For currency [insert name of currency]: (i) [insert percentage] percent non adjustable element (coefficient A). (ii) [insert percentage] percent adjustable element (coefficient B). The Index I for local currency shall be [insert index]. The Index I for the specified international currency shall be [insert index]. [These proxy indices shall be proposed by the Contractor, subject to acceptance by the Project Manager] The Index I for currencies other than the local currency and the specified international currency shall be [insert index]. [These proxy indices shall be proposed by the Contractor, subject to acceptance by the Project Manager.] |
| GC 45.1 |  | The proportion of payments retained is: [insert percentage] [The retention amount is usually close to 5% and in no case exceeds 10% of each payment.] |
| GC 46.1 |  | The liquidated damages for the whole of the Works are [insert percentage of the final Contract Price] per day. The maximum amount of liquidated damages for the whole of the Works is [insert percentage] of the final Contract Price. [Usually liquidated damages are set about 0.10% per day, and the total amount shall not exceed 10% of the Contract Price. If Sectional Completion and Damages per Section have been agreed, the latter should be specified here.] |
| GC 47.1 |  | [The following clauses may be added to Sub-Clause 47.1.] The Bonus for the whole of the Works is [insert percentage of final Contract Price] per day. The maximum amount of Bonus for the whole of the Works is [insert percentage] of the final Contract Price. [If early completion would provide benefits to the Employer, this Clause should remain; otherwise delete. The Bonus is usually numerically equal to the liquidated damages.] |
| GC 48.1 |  | The Advance Payments shall be: [insert amount(s)] and shall be paid to the Contractor no later than [insert date(s)]. |
| GC 49.1 |  | The Performance Security will be in the form of a demand guarantee in the amount(s) of [insert percentage. An amount of 5 to 10% of the Contract Price is commonly specified for Performance Bank Guarantee.] percent of the Accepted Contract Amount. |
| E. Finishing the Contract |  |  |
| GC 55.1 |  | The date by which operating and maintenance manuals are required is [insert date]. The date by which “as built” drawings are required is [insert date]. |
| GC 56.2 (g) |  | The maximum number of days is: [insert number; consistent with Sub-Clause 46.1 on liquidated damages]. |
| GC 58.1 |  | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is [insert percentage]. |

Section IX.	Contract Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after Contract award.

Table of Forms

Letter of Acceptance	2

Contract Agreement	3

Performance Security	5

Advance Payment Security	7

Letter of Acceptance

[letterhead paper of the Employer]

[insert date]

To: [insert name and address of the Contractor]

Subject: [Notification of Award Contract No]

This is to notify you that your Bid dated [insert date] for execution of the [insert name of the Contract and identification number, as given in the Bid Data Sheet] for the Accepted Contract Amount of the equivalent of [insert amount in numbers and words] [insert name of currency], as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are requested to furnish the Performance Security within 28 days in accordance with the Conditions of Contract, using for that purpose the of the Performance Security Form included in Section IX (Contract Forms) of the Bidding Documents.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

Attachment:  Contract Agreement

Contract Agreement

THIS AGREEMENT made the [insert date] day of [insert month], [insert year], between [insert name of the Employer] (hereinafter “the Employer”), of the one part, and [insert name of the Contractor] (hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as [name of the Contract].should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1.	In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement. This Agreement shall prevail over all other Contract documents.

    - the Letter of Acceptance;

    - the Letter of Bid;

    - the Addenda Nos [insert addenda numbers if any];

    - the Particular Conditions;

    - the General Conditions;

    - the Specification;

    - the Drawings;

    - the completed Schedules; and

    - Acknowledgement of Compliance with Guidelines for Procurement under Japanese ODA Loans

- For the purpose of interpretation, the priority of the listed documents shall be in accordance with the above listed order.

3.	In consideration of the payments to be made by the Employer to the Contractor as indicated in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of [insert name of the borrowing country] on the day, month and year indicated above.

| Signed by: |  | Signed by: |  |
| --- | --- | --- | --- |
| for and on behalf of the Employer |  | for and on behalf the Contractor |  |
| in the presence of: |  | in the presence of: |  |
|  |  | : |  |
| Witness, Name, Signature, Address, Date |  | Witness, Name, Signature, Address, Date |  |

Performance Security

(Demand Guarantee)

[Insert Guarantor letterhead or SWIFT identifier code]

Beneficiary: [Insert name and Address of the Employer]

Date: [Insert date of issue]

PERFORMANCE GUARANTEE No.: [Insert guarantee reference number]

Guarantor: [Insert name and address of place of issue, unless indicated in the letterhead]

- We have been informed that [insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture] (hereinafter called “the Applicant”) has entered into Contract No. [insert reference number of the Contract] dated [insert date] with the Beneficiary, for the execution of [insert name of the Contract and brief description of the Works] (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in figures] ([insert amount in words]), such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its obligation(s) under the Contract, without the Beneficiary needing to prove or to show grounds for its demand or the sum specified therein.

This guarantee shall expire, no later than the [insert the day] day of [insert month], [insert year], and any demand for payment under it must be received by us at this office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 458, except that the supporting statement under Article 15(a) is hereby excluded.

_____________________ 
[signature(s)]

[Note:  All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]

Advance Payment Security

- (Demand Guarantee)

[Insert Guarantor letterhead or SWIFT identifier code]

Beneficiary: [Insert name and address of the Employer]

Date: [Insert date of issue]

ADVANCE PAYMENT GUARANTEE No.: [Insert guarantee reference number]

Guarantor: [Insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture] (hereinafter called “the Applicant”) has entered into Contract No. [insert reference number of the Contract] dated [insert date of the Contract] with the Beneficiary, for the execution of [insert name of Contract and brief description of Works] (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum [insert amount in figures] ([insert amount in words]) is to be made against an advance payment guarantee.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in figures] ([insert amount in words]) upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating either that the Applicant:

    - has used the advance payment for purposes other than the costs of mobilization in respect of the Works; or

    - has failed to repay the advance payment in accordance with the Contract conditions, specifying the amount which the Applicant has failed to repay.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the advance payment referred to above has been credited to the Applicant on its account number [insert number] at [insert name and address of Applicant’s bank].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Applicant as specified in copies of interim statements or payment certificates which shall be presented to us. This guarantee shall expire, at the latest, upon our receipt of documentation indicating full repayment by the Contractor of the amount of the advance payment, or on the [insert day] day of [insert month], [insert year], whichever is earlier. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 458 , except that the supporting statement under Article 15(a) is hereby excluded.

____________________ 
[signature(s)]

[Note:  All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]

Retention Money Security

- (Demand Guarantee)

[Insert Guarantor letterhead or SWIFT identifier code]

Beneficiary: [Insert name and Address of Employer]

Date: [Insert date of issue]

RETENTION MONEY GUARANTEE No.: [Insert guarantee reference number]

Guarantor: [Insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture] (hereinafter called “the Applicant”) has entered into Contract No. [insert reference number of the Contract] dated [insert date] with the Beneficiary, for the execution of [insert name of Contract and brief description of Works] (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, the Beneficiary retains moneys up to the limit set forth in the Contract (“the Retention Money”), and that when the Taking-Over Certificate has been issued under the Contract and the first half of the Retention Money has been certified for payment, payment of the second half is to be made against a Retention Money guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in figures] ([insert amount in words]) upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its obligation(s) under the Contract, without the Beneficiary needing to prove or show grounds for its demand or the sum specified therein.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the second half of the Retention Money as referred to above has been credited to the Applicant on its account number [insert account’s number] at [insert name and address of Applicant’s bank].

This guarantee shall expire no later than the [insert day] day of [insert month], [insert year] , and any demand for payment under it must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 458 , except that the supporting statement under Article 15(a) is hereby excluded.

____________________ 
[signature(s)]

[Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]

1 The starting date should be revised to “request for price quotation,” if the Borrower is selected through the International Shopping”; to "appointment", if a contractor is selected through the Direct Contracting; or “Commencement of actual selection/bidding process”, if the Borrower wishes to adopt procurement procedures other than ICB, Limited International Shopping, International Shopping, or Direct Contracting.

As the case may be, ICC Publication No. 758 (or subsequent ICC Publications) may be used. In such cases, modify the Publication number.

The amount of the Bond shall be denominated in the currency of the Employer’s country or the equivalent amount in a freely convertible currency.

The Guarantor shall insert an amount representing the percentage of the Accepted Contract Amount specified in the Letter of Acceptance, less provisional sums, if any, and denominated either in the currency(cies) of the Contract or a freely convertible currency acceptable to the Beneficiary.

Insert the date twenty-eight (28) days after the expected expiration date of the Defect Liability Period. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

As the case may be, ICC Publication No. 758 (or subsequent ICC Publications) may be used. In such cases, modify the Publication number.

The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.

Insert the expected expiration date of the time for completion of the Contract.  The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

As the case may be, ICC Publication No. 758 (or subsequent ICC Publications) may be used. In such cases, modify the Publication number.

The Guarantor shall insert an amount representing the amount of the second half of the Retention Money denominated either in the currency(ies) of the second half of the Retention Money as specified in the Contract, or in a freely convertible currency acceptable to the Beneficiary.

Insert the same expiry date as set forth in the Performance Security, representing the date twenty-eight days (28) after the expected expiration date of the Defect Liability Period.  The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

As the case may be, ICC Publication No. 758 (or subsequent ICC Publications) may be used. In such cases, modify the Publication number.