## Slide 1: KAIZEN Step 5: “Implementation of countermeasure”
KAIZEN Training of Trainers
2015
KAIZEN Facilitators’ Guide
Page __ to __ .

## Slide 2: Objectives of the session
At the end of the session, trainees are able to:
Describe process of developing an action plan on the feasible countermeasures
Describe importance of monitoring implementation progress of the feasible countermeasures
Demonstrate the process of developing the action plan and monitoring checklist

## Slide 3: KAIZEN Process
Root Cause Analysis
Selection of KAIZEN theme
Situation Analysis
Identification of countermeasure
Check effectiveness of countermeasure
Standardization
Implementation of countermeasure
STEP
1
STEP
2
STEP
7
STEP
6
STEP
5
STEP
4
STEP
3

## Slide 4: Process of Step 5: Countermeasures Implementation
 | Importance | Urgent | Difficulty | Total
CM 1 | ◎ | ◎ | ○ | 13
CM 2 | ○ | ▲ | ▲ | 9
CM 3 | ○ | ○ | ◎ | 11
Action plan development with 5W1H
Implement countermeasures
Check effectiveness
Sharing action plan with QIT
Monitoring progress of intervention
Step４
Step 6
Step 5
Sharing action plan with section staff

## Slide 5: Cont.
Implement ALL the countermeasures identified as feasible measures in Step 4
Develop an action plan and possible to complete the countermeasures within one to three months
Share the action plan with:
  All section staff (Participatory implementation)
  QIT (Seek technical inputs)
Monitor progress of implementation of the countermeasures

## Slide 6: Time allocation for Step 5
KAIZEN Process
Step 1
Step 2
KAIZEN Process
Step 3
Step 4
KAIZEN Process
Step 5
KAIZEN Process
Step 5
KAIZEN Process
Step 5
KAIZEN Process
Step 6
Step 7
Remember “proper time allocation” for whole process of KAIZEN is maximum６months
Implementation of countermeasure must be done within 2-3 months
2 months
2 - 3 months
1 month

## Slide 7: Benefit of development of action plan
Developing a action plan with “5W1H” will be of benefit to;
  Define detailed actions to implement the countermeasures with “5W1H”
  Improve communication among section staff
  Unify the sense of purpose of the staff in implementation of KAIZEN
  Simplify a progress monitoring

## Slide 8: Clarification of “5W1H”
“5W1H” | Clarification | Example
Why? | Why we need to take this countermeasure | To strengthen stock management of medicines
Who? | Who is the responsible person of the countermeasure | Ward in-charge and KAIEN team
When? | Timing or period (deadline) of the countermeasure | By 27th of October 2015
Where? | Place where the countermeasure taken | At the ward
What? | What is objective of the countermeasure | Rules and regulation of storage of the medicines
How? | How do you do for the countermeasure (action, verb) | Develop

## Slide 9: Example of Action plan format
 | Counter measure | Who | What | Where | When | Why | How
1 | Develop of storage rules with pharmacists | Ward In-charge, ward pharmacist | Storage rules and regulations | At the ward | By Dec. 01 | Strengthen stock management of the medicines | Develop
2 | Develop checklist and handing over note | WIT, Ward In-charge | Checklist and handing over note | At the ward | By Dec. 15 | Reduce miscommunication among shifts | Develop
3 | …… |  |  |  |  |  | 
4 | …… |  |  |  |  |  | 

## Slide 10: Monitoring a progress of the implementation
Develop a monitoring checklist by clarifying:
  Date of monitoring
  Responsible person(s) of the monitoring
  Progress of monitoring
Utilize the checklist
Utilize the results of the monitoring
  Proper implementation: continue
  Delay of the implementation: re-plan and implement
  Impossible to implement: clarify the reasons of why not implemented

## Slide 11: Example of action plan with progress checklist
 | Counter measures | Who | What | Where | When | Why | How | Date of monitoring | Who checked | Progress
1 | ………… |  |  |  |  |  |  | ／ |  | 
2 | ……………… |  |  |  |  |  |  | ／ |  | 
3 | ………. |  |  |  |  |  |  | ／ |  | 
4 | ……………. |  |  |  |  |  |  | ／ |  | 
5 | ………… |  |  |  |  |  |  | ／ |  | 
Keys for progress check
G: According the plan
D: Delay
N: Not implemented

## Slide 12: Tips for successful implementation
It needs to check again whether all countermeasures are possible to be carried out within the section or not
Remember “KAIZEN is participatory activities”
  “WHO” in your plan is not only “in-charge”
  Sharing the plan with all section staff

## Slide 13: Cont.
Action plan must be displayed on the notice board for staff
  To remind staff of implementation of KAIZEN
  To promote participatory implementation of KAIZEN
Conduct periodical monitoring with progress checklist

## Slide 14: Thank you for listening