## Sheet1
Action Plan
■Basic information | [7 empty] | ■Baseline Survey |  |  | ■Market Survey
Country: |  |  | Ethiopia |  |  |  |  | Narrative Activity (objective) | To know intial situation of farmers under considaration |  | Narrative Activity (objective) | [6 empty] | To know current situation and forcast future trends.
Name of trainee: |  |  |  |  | Abate Kidida
[8 empty] | When/Duration | Late June |  | When/Duration | [6 empty] | Early July
Organization Responsible |  |  |  |  | ABOA | OIDA ( irriga. Office at d/t lev. |  | Where/Venue | At each targate area |  | Where/Venue | [6 empty] | At the local market
Target group(number of members) |  |  |  |  | 89 persons |  |  | Organizer | Irrigation office & jica |  | Organizer | [6 empty] | OIDA ( Oromia Irrigation DevElopment autoriry )& JICA.
Target area |  |  |  |  | Keresa & S.Chokrsa.district.
Objective |  |  |  |  | To Promote Market-Oriented Agriculture |  |  | Implementer | OIDA & JICA |  | Implementer | [6 empty] | OIDA ( Oromia Irrigation DevElopment autoriry ) & JICA
Source of budget. |  |  |  |  | JICA
the period |  |  |  |  | June 2017-May 2018 |  |  | Participants | farmers and extenetion staff |  | Participants | [6 empty] | farmers (technically sapported by DAs ).
Section responsible for supervision |  |  |  |  | OIDA (Region,Zone ,Woreda), &JICA
[8 empty] | Budget (source of budget) | JICA . |  | Budget (source of budget) | [6 empty] | JICA.
Section responsible for implementation |  |  |  | Central: | OIDA &,JICA (Zone ,Woreda) related organizations
|  |  |  | Local: |  |  |  | Tips for Implementation | simplified format for data collection, partcipant orientation , |  | Tips for Implementation | [6 empty] | Appropriate Market day arranged and Farmers orientation,role division among partcipants( who do what….? )
Others (Related organizations) | [5 empty] | Cooperative , Agricultureal office, AGP and other stake holders.
■Action Plan
No. | Activity |  |  |  |  | Implementer | Partcipants (targets ) |  |  | Tips for Implementation |  |  | 2017 | [6 empty] | 2018
[12 empty] | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | Sensitization work shop for high official |  |  |  |  | OIDA & JICA | Oromia burae0 of admin. & OIDA |  |  | Introduce what concepts of SHEP is all about & takinig opportunity of report session of this training | bar: 2017 JUN
2 | Sensitization work shop at Zone level |  |  |  |  | JICA. | OIDA, Coop, Woman Affaire,Trade &Market dev .Agency , Admini ,Ag input supply offices & Agre.office at Zone & district level . |  |  | Introduce what concepts of SHEP is all about | bar: 2017 JUN to 2017 JUL
3 | Selection of Beneficiaries |  |  |  |  | JICA team and farmers group theme selves | Irrigation & Admin.office at woreda level &JICA |  |  | Criteria of selection has been set and conducted to identify beneficiary farmers | bar: 2017 JUN to 2017 JUL
4 | Sensitization work shop at target area |  |  |  |  | OIDA &JICA | Farmers in target areae orselected farmer group |  |  | Issues discussed :SHEP concept,Gender isues,Water use association ,Agriculture cooperative | bar: 2017 JUN to 2017 JUL
5 | Baseline survey |  |  |  |  | OIDA &JICA | Farmers supported by extention staff |  |  | Simplified format is prepared,Farmers are oriented,,Illiterate farmers are supported by litterate farmers | bar: 2017 JUN to 2017 JUL
8 | FABLIST Forum |  |  |  |  | OIDA JICA | Input Supply,Cooperative,Unions,Private trdes,Saving & Credit etc… |  |  | Appropriate meeting day set,Invitation letter for stakeholder prepared,Venue arranged ,Attendance list preapred | bar: 2017 AUG to 2017 SEP
6 | Training on market survey, crop selection and action plan making |  |  |  |  | OIDA & JICA | District technical staff |  |  | Presentation material is prepared ,Venue is arranged ,,participants are invited | bar: 2017 JUL to 2017 AUG
7 | Market survey |  |  |  |  | OIDA & JICA | Farmers (supported by extenetion staff |  |  | Appropriate Market day arranged and Farmers orientation | bar: 2017 AUG to 2017 SEP
| crop selection |  |  |  |  | OIDA & JICA | farmers ( supported) by extenetion staff |  |  | Data collection format Preparation & technical advise by extenetion staff | bar: 2017 AUG to 2017 SEP
| cropping calander |  |  |  |  | OIDA &JICA | farmers ( supported) by extenetion staff |  |  | Technical advice and orientation hav been given by extenetion staff | bar: 2017 AUG to 2017 SEP
|  | Action plan. |  |  |  | OIDA&JICA | farmers ( supported) by extenetion staff |  |  | Orientation & techenical advise by extenetion staff | bar: 2017 AUG to 2017 SEP
9 | ToT training |  |  |  |  | OIDA & JICA | Dist.irrig. Extention staff,DA's & model farmers from each group |  |  | Presentation material prepared,Venue arranged ,participants are invited | bar: 2017 SEP
10 | In-Field Training |  |  |  |  | OIDA & & JICA | Farmers & irrigation. Extention staff &DAs. |  |  | Back- stoping of field ext workers by the subject matter specialist &other stalk holders | bar: 2017 OCT to 2017 DEC
12 | Monitoring & evaluation |  |  |  |  | SHEP team | Jica team & farmer's group representatives |  |  | prepare appropriate M & E fomat, discribe the role of each member and carryout M&E and,give timely feed back | bar: 2017 OCT; 2017 DEC
13 | End line serevey |  |  |  |  | SHEP team | Farmer supported by Extention officer |  |  | Simplified format is prepared and partcipant farmers will be selectd, M &E will be carried out. | bar: 2018 FEB to 2018 MAR