## Summary
Progress Report after SHEP KCCP in Japan and Kenya
Country: Ethiopia
| Name: Mr. Abate Kedida | Date:6 December 2017
Updated Summary:
1. Are you implementing your Action Plan?
Yes or No
2. Which activity did you implement? Or, are you implementing? (Please write down the name(s) of Step and the narrative explanation on the progress briefly.) 2.1 We have implemented activities described insequantial order as below 1. Sensitization workshop at Zonal level 2.Target site and beneficiary selected respectively. 3. Sensitization work shop at target site ( far target beneficiary ) 4. Participatory base line and G20 questionnaire data survey 5. Training on market survey and market survey carried out by target group farmers. - Training and practical exercise on priority crop selection,crop calendar and action plan making - Training and practical exercise on priority crop ( Tomato, Potato and peeper ) cultivation and Bokashi ( organic fertilizer ) making for experts & target group farmers . -In field training on the priority crop mentioned above cultivated for demonstration ( particularly peeper & Tomato ) and soil sterilization and, 6. Fabulist ( Farmer's stake holders linkage ) forum is under taken.
2.2 Narrative explanation for major implemented activities Step 1: Select target farmers and share aims Selection of target site and target beneficiaries is carried out after sensitization ( launching work shop ) conducted at JImma zone inviting and involving all concerned stake holders from the zone zone and from( the proposed) district level . On the sensitization work shop brief explanation about the " SHEP" project all about is given for participants. Following sensitization( Ethio-SHEP launching) work shop at zonal level two irrigation beneficiary farmer groups were selected as a target group and introduced on the sensitization work shop briefly about " SHEP " that the project stands to providing technical support for small holder horticulture farmer to grow market oriented agriculture and promote their produce to maximizing their profit. The target group farmers explained their interest and commitment to work with and implement the project in group guided by the technical aid provided from the project. Step 2: Create opportunities for awareness the target group farmers got the opportunities to rise their awareness while the project together with them under take project implementation activities like: Participatory base line survey ( after creating awareness for stake holders & target groups on how to carry out the survey ) which helped the target group recognize/observe their actual farming status , the importance of farm record keeping , deeply observe their current ( actual ) level of yield & income .......... Market survey : target group farmers and concerned stake holders provided one day training before undertake the actual market survey. Market survey carried out by the target group farmers ( in Jimmaa city , in Bishishe specific market center ) for one day , and as result, the farmers able to understanding the market requirements, what vegetable crop is when, with what quality ? how much who ( costumer ) where etc. : what is meant by costumer oriented production. Step 3: Farmer-led decision-making Crop selection & crop action plan : Based on the data/information obtained from the market survey The two target group farmers got a short time training on how to undertake the priority crop selection and proceed in to crop selection : the target group farmers decision making realized Accordingly. the two target group farmers : Birbirsa selected potato & Peeper , and Deti-duke target group selected Tomato & Potato vegetable crops as their priority crops for the first irrigation season of 2017/2018.they prepared crop action plan and /or cropping colander for the selected priority crops adjusting their cultivation and harvesting season to the peak market demand from the usual/trend cropping calendar. Here is the pace were target group farmers started shifting their production strategy from " Grow and sell to Grow to sell."Business linkage ( FABLIST ) forum conducted . The farm business linkage forum which mainly focused on farm input supply is carried out for one day between farmers and farmers stake holders like agro. input ( vegetable seeds & agro. chemical ) dealers, cooperative onions, Concerned GOs & NGOs, and research and educational institutions ( JImma University). The forum provided the farmers for face to face communication and discuss with their stake holders and able to verify legal ( licensed) illegal traders of agro input, effort and or contribution of other stake holders on improved agricultural technology access. Generally the forum provided the target group farmers obtain the un touched knowledge about the agricultural input supply and obtain the opportunity to creating direct link with the important stake holders. Step 4: Providing technical solutions AS being mentioned above in order to optimize productivity of the selected target site the project has been providing technical support in all its effort. to increase the productivity/hectare of the selected crops from the target site continuous training on how to grow and manage is given for experts d (DAs)envelopment agents and for the target group farmers
(e.g.)
Step 2: Baseline Survey
Department of Agriculture in cooperation with District Agricultural Extension Officers conducted the baseline survey with the target farmers group on XXXXXX. The preliminary meeting was held one month before the survey and XX members of the group participated in the survey. The major findings from the survey are XXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. The question is not clear but if I am not mistaken and the question is about the r/ship between agrecultural and OIDA office , the structure of OIDA office is not extended to kebele ( village ) level. Hence this organization works in cooperation with agricultural office. The DAs assigned at the village level are responsible and accountable to undertake all agrecultural development activities.
3-1. Which activity is the one you planned but could not implemented?
Nothing, all planned activities are carried out but some from the planned activities like demonstration for the selected crop and soil sterilization are not carried as per the schedule because of the extended rainy season that adversely affected the cropping calendar of the target site.
3-2. Please explain about the reasons and the countermeasures.
It mentioned on question No. 3-1
4. Please explain about the activities that you are going to implement in the coming two months.
Technical training on basic plant physiology ,soil management, nursery and soil management and advanced Bokashi preparation post harvest handling techniques, and in field training on techniques of priority crops production and marketing in general and Monitoring and evaluation.
Please also kindly fill in other sheets of this Excel file as much as possible. If necessary, please add sheet(s) and explain the progress according to the structure of your Action Plan.

## 1.Group Profile
SHEP Profile
Profile
Province |  | The two target sites are found in Jimma Zone Oromia National Regional State
Team | Provincial | ------------------------------
| District | Seka-chokorsa For Deti-duke, and Kersa district for Birbirsa
| Municipality | Seka -chokorsa for seka-chokorsa, and Serbo for Kersa are manicipals
Target Group |  | Deti-duke and Birbirsa user groups
Establishment |  | 2017 and 2002 respectively
Location |  | D.duke to the south direction 7 & 29 km away from seksa district center town and Jimma city respectively
Membership | Total | 58 | Male | 37 | Female | 21
Number of farmers involved in SHEP
Land-Ownership |  | They all have their own irrigable land from the site with a maximum land holding size of 0.25 hectare for each member
Mother Language |  | Both target group members language Oromiffaa ( afan oromo )
Main Crops |  | Maize Teff sorghum from the field croup for the two target site.
Remarks
Activity
Date | Activity |  |  |  | Attendance
[5 empty] | Official | Farmer
[6 empty] | M | F | M/F*
* M/F means total number of farmers if it can not be divided into male/female from attendance register.
Core Activity
Market Survey
Place (Formal)
Place (In-formal)
FABLIST Forum
Place (Formal)
Place (In-formal)
Crop Selection
Target Crops

## 2.Activity Plan
Activity Plan
|  | 2017 | [6 empty] | 2018
|  | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
1
2
4
6
7 | Monitoring and Evaluation (including Endline Survey)

## 3.Sensitization
SHEP Activity Monitoring Sheet
Sensitization
Title of Activity
Date
Venue
Participants | Officials | Farmers
|  | Male | Female
Time table | Time | Activity | Responsibility
Outcome
Reaction of participants

## 4.Baseline Survey
SHEP Activity Monitoring Sheet
Baseline Survey
Title of Activity
Date
Venue
Participants | Officials | Farmers
|  | Male | Female
Time table | Activity |  | Responsibility
Outcome
Reaction of participants

## 5.Market Survey
SHEP Activity Monitoring Sheet
Market Survey
Title of Activity
Date
Venue
Participants | Officials | Farmers
|  | Male | Female
Time table | Activity |  | Responsibility
Outcome
Reaction of participants

## 6.Crop Selection
SHEP Activity Monitoring Sheet
Crop Selection
Title of Activity
Date
Venue
Participants | Officials | Farmers
|  | Male | Female
Time table | Activity |  | Responsibility
Outcome
Reaction of participants

## 7.Cropping Calendar
SHEP Activity Monitoring Sheet
Cropping Calendar
Title of Activity
Date
Venue
Participants | Officials | Farmers
|  | Male | Female
Time table | Activity |  | Responsibility
Outcome
Reaction of participants

## 8.In-fiield Trainig
SHEP Activity Monitoring Sheet
In-field Training
Title of Activity
Date
Venue
Participants | Officials | Farmers
|  | Male | Female
Time table | Activity |  | Responsibility
Outcome
Reaction of participants

## 9.Monitoring and Evaluation
SHEP Activity Monitoring Sheet
Monitoring and Evaluation
Title of Activity
Date
Venue
Participants | Officials | Farmers
|  | Male | Female
Time table | Activity |  | Responsibility
Outcome
Reaction of participants